## Cover Page (hidden)
South Pars Gas Field Development Phases 14
Invoice No. 13
Work Statement Ticket
Package Number 2
|  |  | Cut of Date : |  |  | 2014-05-01
|  |  |  | Client : | IPMI Co.
|  |  |  | Contractor : | MAROON KARAN Co.

## Planning (hidden)
South Pars Gas Field Development Phase 14 Package Number 2
|  | Cut Of Date : | 2013-09-30
Description |  |  | Quantity |  |  |  |  | Progress | Quantity Approved Planning | Price
|  |  | Unit | Estimate | Up To Last | This Month | Work Performed
|  | Package NO.2 | [7 empty] | 273000000000
|  | Procurement | [7 empty] | #REF!
|  | fire proof | [7 empty] | #REF!
|  | PO Placement | m2 | 200 |  | 0 |  | 0%
|  | Fabrication & Test | m2 | 200 |  | 0 |  | 0%
|  | Delivery | m2 | 200 |  | 0 |  | 0%
|  | Rebar | [7 empty] | #REF!
|  | PO Placement | Kg | 308693 | 308693 | 0 | 308693 | 100%
|  | Fabrication & Test | Kg | 308693 | 308693 | 0 | 308693 | 100%
|  | Delivery | Kg | 308693 | 308693 | 0 | 308693 | 100%
|  | Piping Support | [7 empty] | #REF!
|  | PO Placement | Kg | 72000 | 72000 | 0 | 72000 | 100%
|  | Fabrication & Test | Kg | 72000 | 72000 | 0 | 72000 | 100%
|  | Delivery | Kg | 72000 |  | 8500 | 8500 | 11.81%
|  | Cold Insulating | [7 empty] | #REF!
|  | PO Placement | m2 | 5862 |  | 0 |  | 0%
|  | Fabrication & Test | m2 | 5862 |  | 0 |  | 0%
|  | Delivery | m2 | 5862 |  | 0 |  | 0%
|  | Warm Insulating | [7 empty] | #REF!
|  | PO Placement | m2 | 2937 |  | 0 |  | 0%
|  | Fabrication & Test | m2 | 2937 |  | 0 |  | 0%
|  | Delivery | m2 | 2937 |  | 0 |  | 0%
|  | Paint | [7 empty] | #REF!
|  | PO Placement | Kg | 56000 | 43900 | 0 | 43900 | 78.39%
|  | Delivery | Kg | 56000 | 12730 | 31170 | 43900 | 78.39%
|  | Electrode | [7 empty] | #REF!
|  | PO Placement | Kg | 27000 | 18080 | 2920 | 21000 | 77.78%
|  | Fabrication & Test | Kg | 27000 | 18080 | 2920 | 21000 | 77.78%
|  | Delivery | Kg | 27000 | 18080 | 2920 | 21000 | 77.78%
|  | Plant Construction | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | General | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | mobolization | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | primary mobilozation | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | countiuse mobilization | % | 100 | 21 | 4 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 20 | -5
|  | Demobilizaton | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Demobilizaton | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Gate House | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | civil | [7 empty] | #REF! |  |  |  | 0 |  | 0
| ` | Foundation | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | columns | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Wall | % | 100 | 0 | 6 | 6 | 6% |  | #REF! |  |  | 0 | -6 | 0 | -6
|  | Floor | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Roof | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 95 | -5
|  | Mechanical | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Piping | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Installation | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | electrical | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Cabling | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Installation | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | telecom | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | telecom | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | architect | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | architect | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | final works | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | final works | % | 100 | 0 | 13.4 | 13.4 | 13.4% |  | #REF! |  |  | 0 | -13.4 | 0 | -13.4
|  | Unit 140 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Welding & NDT Procedures | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Prepare and qualify welding procedures (welding procedures qualfication tests (WPQT) including lab. Tests) for structural and pipe welding | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Qualification of welders including lab testing for structural and pipe welding | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Qualification of welding equipment | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Maintaining welder qualification records | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Monitoring welder performance | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Prepare and NDT Procedures and obtain certification | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Qualification of NDT equipment and dimensional control (UT, RT, MT,...) | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Qualification of equipment operators for NDT and dimensional control | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Perform NDT as per the procedures | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Supply of associated Elec. Power, consumables, Materials construction equipments | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Prepare PWHT procedure and obtain certification | % | 100 | 0 | 40 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Perform PWHT testing | % | 100 | 0 | 40 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 20 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Civil | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Plat Form | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | West HP | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 1385 | 1385 | 0 | 1385 | 100% |  | #REF! |  |  | 1385 | 0 | 1385 | 0
|  | level&compact | m2 | 588 | 588 | 0 | 588 | 100% |  | #REF! |  |  | 588 | 0 | 588 | 0
|  | lean | m3 | 40 | 40 | 0 | 40 | 100% |  | #REF! |  |  | 40 | 0 | 40 | 0
|  | footing rebar | Kg | 27084 | 27084 | 0 | 27084 | 100% |  | #REF! |  |  | 27084 | 0 | 27084 | 0
|  | footing form | m2 | 210 | 210 | 0 | 210 | 100% |  | #REF! |  |  | 210 | 0 | 210 | 0
|  | foting concrete | m3 | 369 | 369 | 17.5 | 386.5 | 104.7% |  | #REF! |  |  | 369 | -17.5 | 369 | -17.5
|  | ped rebar | Kg | 14583 | 14583 | 0 | 14583 | 100% |  | #REF! |  |  | 14583 | 0 | 14583 | 0
|  | ped form | m2 | 259 | 259 | 0 | 259 | 100% |  | #REF! |  |  | 259 | 0 | 250 | -9
|  | anchor | NO. | 274 | 274 | 0 | 274 | 100% |  | #REF! |  |  | 274 | 0 | 238 | -36
|  | ped concrete | m3 | 121 | 115 | 34 | 149 | 123.1% |  | #REF! |  |  | 115 | -34 | 73 | -76
|  | curing | % | 100 | 85 | 15 | 100 | 100% |  | #REF! |  |  | 85 | -15 | 85 | -15
|  | coating | m2 | 850 | 722.5 | 127.5003 | 850.0003 | 100% |  | #REF! |  |  | 420 | -430.0003 | 420 | -430.0003
|  | back fill | m3 | 998 | 199.6 | 689.2 | 888.8 | 89.06% |  | #REF! |  |  | 182 | -706.8 | 182 | -706.8
|  | Final Certificate | % | 100 | 59 | 5 | 64 | 64% |  | #REF! |  |  | 53 | -11 | 53 | -11
|  | East HP | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 1358 | 1358 | 0 | 1358 | 100% |  | #REF! |  |  | 1358 | 0 | 1358 | 0
|  | level&compact | m2 | 575 | 575 | 0 | 575 | 100% |  | #REF! |  |  | 575 | 0 | 575 | 0
|  | lean | m3 | 39 | 39 | 6 | 45 | 115.4% |  | #REF! |  |  | 39 | -6 | 39 | -6
|  | footing rebar | Kg | 26445 | 26445 | 0 | 26445 | 100% |  | #REF! |  |  | 26445 | 0 | 26445 | 0
|  | footing form | m2 | 200 | 200 | 0 | 200 | 100% |  | #REF! |  |  | 200 | 0 | 200 | 0
|  | foting concrete | m3 | 362 | 362 | 7.5 | 369.5 | 102.1% |  | #REF! |  |  | 362 | -7.5 | 362 | -7.5
|  | ped rebar | Kg | 14239 | 14239 | 0 | 14239 | 100% |  | #REF! |  |  | 14189 | -50 | 14189 | -50
|  | ped form | m2 | 255 | 255 | 0 | 255 | 100% |  | #REF! |  |  | 250 | -5 | 250 | -5
|  | anchor | NO. | 262 | 262 | 0 | 262 | 100% |  | #REF! |  |  | 262 | 0 | 178 | -84
|  | ped concrete | m3 | 120 | 84.996 | 16.004 | 101 | 84.17% |  | #REF! |  |  | 80 | -21 | 80 | -21
|  | curing | % | 100 | 85 | 0 | 85 | 85% |  | #REF! |  |  | 85 | 0 | 85 | 0
|  | coating | m2 | 830 | 581 | 249.0003 | 830.0003 | 100% |  | #REF! |  |  | 550 | -280.0003 | 550 | -280.0003
|  | back fill | m3 | 976.7 | 217.9994 | 583.0006 | 801 | 82.01% |  | #REF! |  |  | 40 | -761 | 40 | -761
|  | Final Certificate | % | 100 | 56 | 8 | 64 | 64% |  | #REF! |  |  | 53 | -11 | 53 | -11
|  | West LP | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 145 | 145 | 0 | 145 | 100% |  | #REF! |  |  | 145 | 0 | 145 | 0
|  | level&compact | m2 | 99 | 99 | 0 | 99 | 100% |  | #REF! |  |  | 99 | 0 | 99 | 0
|  | lean | m3 | 5 | 5 | 0 | 5 | 100% |  | #REF! |  |  | 5 | 0 | 5 | 0
|  | footing rebar | Kg | 7978 | 7978 | 0 | 7978 | 100% |  | #REF! |  |  | 7978 | 0 | 7978 | 0
|  | footing form | m2 | 77 | 77 | 0 | 77 | 100% |  | #REF! |  |  | 77 | 0 | 77 | 0
|  | foting concrete | m3 | 48 | 48 | 0 | 48 | 100% |  | #REF! |  |  | 48 | 0 | 48 | 0
|  | ped rebar | Kg | 4296 | 4296 | 0 | 4296 | 100% |  | #REF! |  |  | 4296 | 0 | 4296 | 0
|  | ped form | m2 | 61 | 61 | 0 | 61 | 100% |  | #REF! |  |  | 61 | 0 | 61 | 0
|  | anchor | NO. | 72 | 72 | 0 | 72 | 100% |  | #REF! |  |  | 56 | -16 | 56 | -16
|  | ped concrete | m3 | 26 | 26 | 0 | 26 | 100% |  | #REF! |  |  | 23 | -3 | 23 | -3
|  | curing | % | 100 | 90 | 0 | 90 | 90% |  | #REF! |  |  | 65 | -25 | 65 | -25
|  | coating | m2 | 181 | 117.65 | 32.35 | 150 | 82.87% |  | #REF! |  |  | 0 | -150 | 0 | -150
|  | back fill | m3 | 135.9 | 135.9 | 0.1 | 136 | 100.1% |  | #REF! |  |  | 0 | -136 | 0 | -136
|  | Final Certificate | % | 100 | 55 | 9 | 64 | 64% |  | #REF! |  |  | 54 | -10 | 54 | -10
|  | East LP | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 214 | 214 | 0 | 214 | 100% |  | #REF! |  |  | 214 | 0 | 214 | 0
|  | level&compact | m2 | 138 | 138 | 0 | 138 | 100% |  | #REF! |  |  | 138 | 0 | 138 | 0
|  | lean | m3 | 7 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | footing rebar | Kg | 9287 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | footing form | m2 | 102 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | foting concrete | m3 | 65 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | ped rebar | Kg | 5000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | ped form | m2 | 84 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | anchor | NO. | 72 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | ped concrete | m3 | 30 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | curing | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | coating | m2 | 248.02 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | back fill | m3 | 195.4 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 10 | 0 | 10 | 10% |  | #REF! |  |  | 10 | 0 | 10 | 0
|  | Retaining wall | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Retaining wall 7 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 1705 | 852.5 | 852.5 | 1705 | 100% |  | #REF! |  |  | 0 | -1705 | 0 | -1705
|  | level&compact | m2 | 472 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | lean | m3 | 21 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | footing rebar | Kg | 36150 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | footing form | m2 | 218 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | foting concrete | m3 | 444 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | Wall rebar | Kg | 36200 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | Wall form | m2 | 780 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Wall concrete | m3 | 385 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | curing | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | coating | m2 | 1263 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | back fill | m3 | 798 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Retaining wall 9 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 316 | 316 | 0 | 316 | 100% |  | #REF! |  |  | 316 | 0 | 316 | 0
|  | level&compact | m2 | 128 | 128 | 0 | 128 | 100% |  | #REF! |  |  | 128 | 0 | 128 | 0
|  | lean | m3 | 4 | 4 | 0 | 4 | 100% |  | #REF! |  |  | 4 | 0 | 4 | 0
|  | footing rebar | Kg | 10025 | 10025 | 0 | 10025 | 100% |  | #REF! |  |  | 10025 | 0 | 10025 | 0
|  | footing form | m2 | 45 | 45 | 0.2 | 45.2 | 100.4% |  |  |  |  | 45.2 | 0 | 45.2 | 0
|  | foting concrete | m3 | 50 | 50 | 8 | 58 | 116% |  |  |  |  | 58 | 0 | 22 | -36
|  | Wall rebar | Kg | 10100 | 10100 | 0 | 10100 | 100% |  |  |  |  | 10100 | 0 | 0 | -10100
|  | Wall form | m2 | 195 | 185 | 10 | 195 | 100% |  |  |  |  | 195 | 0 | 0 | -195
|  | Wall concrete | m3 | 50 | 23 | 33 | 56 | 112% |  | #REF! |  |  | 48 | -8 | 0 | -56
|  | curing | % | 100 | 65 | 35 | 100 | 100% |  | #REF! |  |  | 95 | -5 | 15 | -85
|  | coating | m2 | 145 | 0 | 145 | 145 | 100% |  | #REF! |  |  | 0 | -145 | 0 | -145
|  | back fill | m3 | 166 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 51 | 6 | 57 | 57% |  | #REF! |  |  | 24 | -33 | 24 | -33
|  | Retaining wall 11 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 336 | 0 | 240 | 240 | 71.43% |  | #REF! |  |  | 0 | -240 | 0 | -240
|  | level&compact | m2 | 88 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | lean | m3 | 4 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | footing rebar | Kg | 5610 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | footing form | m2 | 50 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | foting concrete | m3 | 73 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | Wall rebar | Kg | 5240 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Wall form | m2 | 167 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Wall concrete | m3 | 76 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | curing | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | coating | m2 | 263 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | back fill | m3 | 166 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Retaining wall 12 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 316 | 316 | 0 | 316 | 100% |  | #REF! |  |  | 316 | 0 | 316 | 0
|  | level&compact | m2 | 128 | 128 | 0 | 128 | 100% |  | #REF! |  |  | 128 | 0 | 128 | 0
|  | lean | m3 | 4 | 4 | 1 | 5 | 125% |  |  |  |  | 5 | 0 | 5 | 0
|  | footing rebar | Kg | 10025 | 10025 | 0 | 10025 | 100% |  |  |  |  | 10025 | 0 | 10025 | 0
|  | footing form | m2 | 45 | 45 | 0 | 45 | 100% |  |  |  |  | 45 | 0 | 45 | 0
|  | foting concrete | m3 | 50 | 50 | 0 | 50 | 100% |  |  |  |  | 50 | 0 | 0 | -50
|  | Wall rebar | Kg | 10100 | 10100 | 0 | 10100 | 100% |  | #REF! |  |  | 10100 | 0 | 0 | -10100
|  | Wall form | m2 | 195 | 195 | 0 | 195 | 100% |  | #REF! |  |  | 195 | 0 | 0 | -195
|  | Wall concrete | m3 | 50 | 50 | 14 | 64 | 128% |  | #REF! |  |  | 64 | 0 | 0 | -64
|  | curing | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 95 | -5 | 0 | -100
|  | coating | m2 | 145 | 145 | 0 | 145 | 100% |  | #REF! |  |  | 0 | -145 | 0 | -145
|  | back fill | m3 | 166 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 56 | 1 | 57 | 57% |  | #REF! |  |  | 7 | -50 | 7 | -50
|  | Retaining wall 13 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | excavation | m3 | 180 | 0 | 180 | 180 | 100% |  | #REF! |  |  | 0 | -180 | 0 | -180
|  | level&compact | m2 | 72 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | lean | m3 | 3 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | footing rebar | Kg | 4520 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | footing form | m2 | 30 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | foting concrete | m3 | 35 | 0 | 0 | 0 | 0% |  |  |  |  | 0 | 0 | 0 | 0
|  | Wall rebar | Kg | 4280 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Wall form | m2 | 103 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Wall concrete | m3 | 28 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | curing | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | coating | m2 | 170 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | back fill | m3 | 95 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Base |  |  |  | 0 | [7 empty] | 0 |  | 0
|  | Base | m3 | 560 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Piping | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | AG Piping | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Shop | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Carbon Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 42944 | 9850 | 15748 | 25598 | 59.61% |  | #REF! |  | 14499 | 9850 | -15748 | 4984 | -20614
|  | Cutting & Bevelling & Fit Up | ID | 12883 | 226 | 6707 | 6933 | 53.82% |  | #REF! |  | 6368 | 434 | -6499 | 36 | -6897
|  | Welding | ID | 12883 | 99 | 5758 | 5857 | 45.46% |  | #REF! |  | 5473 | 344 | -5513 | 0 | -5857
|  | NDT | ID | 12883 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | PWHT | ID | 12883 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 20 | 0 | 20 | 20% |  | #REF! |  | 0 | 20 | 0 | 20 | 0
|  | Low Temperature CS | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 27889 | 0 | 1248 | 1248 | 4.475% |  | #REF! |  |  | 0 | -1248 | 0 | -1248
|  | Cutting & Bevelling & Fit Up | ID | 8367 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 8367 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 8367 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 8367 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 20 | 0 | 20 | 20% |  | #REF! |  |  | 20 | 0 | 20 | 0
|  | Stainless Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 13845 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 4154 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 4154 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 4154 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 4154 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 20 | 0 | 20 | 20% |  | #REF! |  |  | 20 | 0 | 20 | 0
|  | Galva | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 2645 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 794 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 794 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 794 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 794 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 20 | 0 | 20 | 20% |  | #REF! |  |  | 20 | 0 | 20 | 0
|  | Field | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Carbon Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 42944 | 4391 | 1616 | 6007 | 13.99% |  | #REF! |  | 4391 | 1616 | -4391 | 1029 | -4978
|  | Scaffolding | m2 | 8000 | 5245 | 2104 | 7349 | 91.86% |  | #REF! |  | 5245 | 2104 | -5245 | 3332.95 | -4016.05
|  | Erection & Fit Up | ID | 30060 | 947 | 2672 | 3619 | 12.04% |  | #REF! |  | 947 | 2672 | -947 | 909 | -2710
|  | Valve Installation | ID | 280 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | Welding | ID | 30060 | 826 | 2605 | 3431 | 11.41% |  | #REF! |  | 826 | 2605 | -826 | 659 | -2772
|  | NDT | ID | 30060 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | PWHT | ID | 30060 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | Hydro test | ID | 30060 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  | 40 | 0 | -40 | 20 | -20
|  | Low Temperature CS | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 27889 | 0 | 496 | 496 | 1.778% |  | #REF! | 0 | 496 | 0 | -496 | 0 | -496
|  | Scaffolding | m2 | 8000 | 5245 | 2103.5 | 7348.5 | 91.86% |  | #REF! | 5245 | 2103.5 | 5245.45 | -2103.05 | 3332.95 | -4015.55
|  | Erection & Fit Up | ID | 19522 | 0 | 384 | 384 | 1.967% |  | #REF! | 0 | 384 | 0 | -384 | 0 | -384
|  | Valve Installation | ID | 280 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding | ID | 19522 | 0 | 240 | 240 | 1.229% |  | #REF! | 0 | 240 | 0 | -240 | 0 | -240
|  | NDT | ID | 19522 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | PWHT | ID | 19522 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Hydro test | ID | 19522 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 | 20 | -20 | 20 | -20
|  | Stainless Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 13845 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Scaffolding | m2 | 8000 | 5245 | 2103.5 | 7348.5 | 91.86% |  | #REF! | 5245 | 2103.5 | 5245.45 | -2103.05 | 3332.95 | -4015.55
|  | Erection & Fit Up | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 280 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | NDT | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | PWHT | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Hydro test | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 | 20 | -20 | 20 | -20
|  | Galva | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 2645 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | m2 | 8000 | 5245 | 2103.5 | 7348.5 | 91.86% |  | #REF! |  |  | 5245.45 | -2103.05 | 3332.95 | -4015.55
|  | Erection & Fit Up | ID | 1852 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 280 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 1852 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 1852 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 1852 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 1852 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | Pipe Support | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Shop | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 43200 | 0 | 43200 | 43200 | 100% |  | #REF! |  |  | 0 | -43200 | 0 | -43200
|  | shop drawing | Kg | 43200 | 0 | 100 | 100 | 0.2315% |  | #REF! |  |  | 0 | -100 | 0 | -100
|  | Cutting & assembling | Kg | 43200 | 0 | 35000 | 35000 | 81.02% |  | #REF! |  |  | 0 | -35000 | 0 | -35000
|  | Welding | Kg | 43200 | 0 | 35000 | 35000 | 81.02% |  | #REF! |  |  | 0 | -35000 | 0 | -35000
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Field | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | Kg | 43200 | 0 | 8500 | 8500 | 19.68% |  | #REF! |  |  | 0 | -8500 | 0 | -8500
|  | Erection | Kg | 43200 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | Kg | 43200 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | Kg | 43200 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Painting & Sandblasting | [11 empty] | 0 |  | 0
|  | Pipe |  |  |  | 0 | [7 empty] | 0 |  | 0
|  | Sand Blast | m2 | 39250 | 7465 | 7085.78 | 14550.78 | 37.07% |  |  |  |  | 746494% | -7085.84 | 2703.1 | -11847.68
|  | Primer | m2 | 39250 | 7465 | 7085.78 | 14550.78 | 37.07% |  |  |  |  | 746494% | -7085.84 | 2703.1 | -11847.68
|  | Middle Paint | m2 | 39250 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Paint | m2 | 39250 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Touch Up & Punch | m2 | 39250 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Support |  |  |  | 0 | [7 empty] | 0 |  | 0
|  | Sand Blast | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Primer | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Middle Paint | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Paint | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Touch Up & Punch | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Steel Structure | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Installation Steel Structure | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | 140-IM-A1 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 93234 | 93234 | 0 | 93234 | 100% |  | #REF! |  |  | 94004 | 770 | 94004 | 770
|  | Chip&Padding | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! |  |  | 14 | 0 | 14 | 0
|  | Erection | Kg | 93234 | 93234 | 0 | 93234 | 100% |  | #REF! |  |  | 93969 | 735 | 93969 | 735
|  | Alignment | Kg | 93234 | 93234 | 0 | 93234 | 100% |  | #REF! |  |  | 93969 | 735 | 93969 | 735
|  | Bolt Tightening & Test | Kg | 93234 | 93234 | 0 | 93234 | 100% |  | #REF! |  |  | 93969 | 735 | 93969 | 735
|  | Grouting | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! |  |  | 14 | 0 | 14 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 67 | 0 | 67 | 0
|  | 140-IM-A2 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 135197 | 135197 | 0 | 135197 | 100% |  | #REF! |  |  | 136607 | 1410 | 136607 | 1410
|  | Chip&Padding | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! |  |  | 16 | 2 | 16 | 2
|  | Erection | Kg | 135197 | 135197 | 0 | 135197 | 100% |  | #REF! |  |  | 136607 | 1410 | 136607 | 1410
|  | Alignment | Kg | 135197 | 135197 | 0 | 135197 | 100% |  | #REF! |  |  | 136147.8 | 950.8 | 136147.8 | 950.8
|  | Bolt Tightening & Test | Kg | 135197 | 135197 | 0 | 135197 | 100% |  | #REF! |  |  | 136147.8 | 950.8 | 136147.8 | 950.8
|  | Grouting | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! |  |  | 16 | 2 | 16 | 2
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 63 | -4 | 63 | -4
|  | 140-IM-A3 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 83004 | 83004 | 0 | 83004 | 100% |  | #REF! |  |  | 80800 | -2204 | 80800 | -2204
|  | Chip&Padding | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! |  |  | 16 | 0 | 16 | 0
|  | Erection | Kg | 83004 | 83004 | 0 | 83004 | 100% |  | #REF! |  |  | 80800 | -2204 | 80800 | -2204
|  | Alignment | Kg | 83004 | 83004 | 0 | 83004 | 100% |  | #REF! |  |  | 80800 | -2204 | 80800 | -2204
|  | Bolt Tightening & Test | Kg | 83004 | 83004 | 0 | 83004 | 100% |  | #REF! |  |  | 80800 | -2204 | 80800 | -2204
|  | Grouting | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! |  |  | 16 | 0 | 16 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 63 | -4 | 63 | -4
|  | 140-IM-A4 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 62652 | 62652 | 0 | 62652 | 100% |  | #REF! |  |  | 62652 | 0 | 62652 | 0
|  | Chip&Padding | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! |  |  | 14 | 0 | 14 | 0
|  | Erection | Kg | 62652 | 62652 | 0 | 62652 | 100% |  | #REF! |  |  | 62652 | 0 | 62652 | 0
|  | Alignment | Kg | 62652 | 62652 | 0 | 62652 | 100% |  | #REF! |  |  | 62652 | 0 | 62652 | 0
|  | Bolt Tightening & Test | Kg | 62652 | 62652 | 0 | 62652 | 100% |  | #REF! |  |  | 62652 | 0 | 62652 | 0
|  | Grouting | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! |  |  | 14 | 0 | 14 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 62 | -5 | 62 | -5
|  | 140-IM-A5 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 179726 | 179726 | 0 | 179726 | 100% |  | #REF! |  |  | 179726 | 0 | 179726 | 0
|  | Chip&Padding | NO | 32 | 32 | 0 | 32 | 100% |  | #REF! |  |  | 32 | 0 | 32 | 0
|  | Erection | Kg | 179726 | 179726 | 0 | 179726 | 100% |  | #REF! |  |  | 179726 | 0 | 179726 | 0
|  | Alignment | Kg | 179726 | 179726 | 0 | 179726 | 100% |  | #REF! |  |  | 179726 | 0 | 179726 | 0
|  | Bolt Tightening & Test | Kg | 179726 | 179726 | 0 | 179726 | 100% |  | #REF! |  |  | 179726 | 0 | 179726 | 0
|  | Grouting | NO | 32 | 32 | 0 | 32 | 100% |  | #REF! |  |  | 32 | 0 | 32 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 62 | -5 | 62 | -5
|  | 140-IM-A6 & A6-1 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 160153 | 160153 | 0 | 160153 | 100% |  | #REF! |  |  | 135576 | -24577 | 135576 | -24577
|  | Chip&Padding | NO | 33 | 33 | 0 | 33 | 100% |  | #REF! |  |  | 33 | 0 | 33 | 0
|  | Erection | Kg | 160153 | 160040 | 0 | 160040 | 99.93% |  | #REF! |  |  | 135476 | -24564 | 135476 | -24564
|  | Alignment | Kg | 160153 | 160040 | 0 | 160040 | 99.93% |  | #REF! |  |  | 135475.6 | -24564.4 | 135475.6 | -24564.4
|  | Bolt Tightening & Test | Kg | 160153 | 160040 | 0 | 160040 | 99.93% |  | #REF! |  |  | 135475.6 | -24564.4 | 135475.6 | -24564.4
|  | Grouting | NO | 85 | 85 | 0 | 85 | 100% |  | #REF! |  |  | 33 | -52 | 33 | -52
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 63 | -4 | 63 | -4
|  | 140-IM-A7 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 58446 | 58446 | 0 | 58446 | 100% |  | #REF! |  |  | 58396 | -50 | 58396 | -50
|  | Chip&Padding | NO | 16 | 8 | 0 | 8 | 50% |  | #REF! |  |  | 8 | 0 | 8 | 0
|  | Erection | Kg | 58446 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Alignment | Kg | 58446 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Bolt Tightening & Test | Kg | 58446 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Grouting | NO | 16 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final test & Documents | % | 100 | 10 | 0 | 10 | 10% |  | #REF! |  |  | 10 | 0 | 10 | 0
|  | 140-IM-B1 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 65946 | 65946 | 0 | 65946 | 100% |  | #REF! |  |  | 64131 | -1815 | 64131 | -1815
|  | Chip&Padding | NO | 10 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection | Kg | 65946 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Alignment | Kg | 65946 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Bolt Tightening & Test | Kg | 65946 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Grouting | NO | 10 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final test & Documents | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | 140-IM-B2 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 171694 | 170741 | 0 | 170741 | 99.44% |  | #REF! |  |  | 170741 | 0 | 170741 | 0
|  | Chip&Padding | NO | 12 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection | Kg | 171694 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Alignment | Kg | 171694 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Bolt Tightening & Test | Kg | 171694 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Grouting | NO | 12 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final test & Documents | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | 140-IM-B3 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 169239 | 169239 | 0 | 169239 | 100% |  | #REF! |  |  | 169239 | 0 | 169239 | 0
|  | Chip&Padding | NO | 28 | 28 | 0 | 28 | 100% |  | #REF! |  |  | 28 | 0 | 28 | 0
|  | Erection | Kg | 169239 | 169238.6 | 0 | 169238.6 | 100% |  | #REF! |  |  | 169238.6 | 0 | 169238.6 | 0
|  | Alignment | Kg | 169239 | 169239 | 0 | 169239 | 100% |  | #REF! |  |  | 169239 | 0 | 169239 | 0
|  | Bolt Tightening & Test | Kg | 169239 | 169239 | 0 | 169239 | 100% |  | #REF! |  |  | 169239 | 0 | 169239 | 0
|  | Grouting | NO | 28 | 28 | 0 | 28 | 100% |  | #REF! |  |  | 28 | 0 | 28 | 0
|  | Final test & Documents | % | 100 | 58 | 4 | 62 | 62% |  | #REF! |  |  | 62 | 0 | 62 | 0
|  | 140-IM-B4 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 115066 | 115066 | 0 | 115066 | 100% |  | #REF! |  |  | 115066 | 0 | 115066 | 0
|  | Chip&Padding | NO | 20 | 20 | 0 | 20 | 100% |  | #REF! |  |  | 20 | 0 | 20 | 0
|  | Erection | Kg | 115066 | 114950.6 | 0 | 114950.6 | 99.9% |  | #REF! |  |  | 114950.6 | 0 | 114950.6 | 0
|  | Alignment | Kg | 115066 | 114951 | 0 | 114951 | 99.9% |  | #REF! |  |  | 114951 | 0 | 114951 | 0
|  | Bolt Tightening & Test | Kg | 115066 | 114951 | 0 | 114951 | 99.9% |  | #REF! |  |  | 114951 | 0 | 114951 | 0
|  | Grouting | NO | 20 | 20 | 0 | 20 | 100% |  | #REF! |  |  | 20 | 0 | 20 | 0
|  | Final test & Documents | % | 100 | 63 | 0 | 63 | 63% |  | #REF! |  |  | 62 | -1 | 62 | -1
|  | 140-IM-B5 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 72006 | 72006 | 0 | 72006 | 100% |  | #REF! |  |  | 72807 | 801 | 72807 | 801
|  | Chip&Padding | NO | 10 | 10 | 0 | 10 | 100% |  | #REF! |  |  | 10 | 0 | 10 | 0
|  | Erection | Kg | 72006 | 71608 | 0 | 71608 | 99.45% |  | #REF! |  |  | 72407 | 799 | 72407 | 799
|  | Alignment | Kg | 72006 | 71608 | 0 | 71608 | 99.45% |  | #REF! |  |  | 72407 | 799 | 72407 | 799
|  | Bolt Tightening & Test | Kg | 72006 | 71608 | 0 | 71608 | 99.45% |  | #REF! |  |  | 72407 | 799 | 72407 | 799
|  | Grouting | NO | 10 | 10 | 0 | 10 | 100% |  | #REF! |  |  | 10 | 0 | 10 | 0
|  | Final test & Documents | % | 100 | 63 | 0 | 63 | 63% |  | #REF! |  |  | 63 | 0 | 63 | 0
|  | 140-IM-B6 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 161771 | 161771 | 0 | 161771 | 100% |  | #REF! |  |  | 161771 | 0 | 161771 | 0
|  | Chip&Padding | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! |  |  | 26 | 0 | 26 | 0
|  | Erection | Kg | 161771 | 161544.3 | 0 | 161544.3 | 99.86% |  | #REF! |  |  | 161544.3 | 0 | 161544.3 | 0
|  | Alignment | Kg | 161771 | 161544 | 0 | 161544 | 99.86% |  | #REF! |  |  | 161544 | 0 | 161544 | 0
|  | Bolt Tightening & Test | Kg | 161771 | 161544 | 0 | 161544 | 99.86% |  | #REF! |  |  | 161544 | 0 | 161544 | 0
|  | Grouting | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! |  |  | 26 | 0 | 26 | 0
|  | Final test & Documents | % | 100 | 63 | 0 | 63 | 63% |  | #REF! |  |  | 63 | 0 | 63 | 0
|  | 140-IM-B7 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 85977 | 85977 | 0 | 85977 | 100% |  | #REF! |  |  | 85977 | 0 | 85977 | 0
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 12 | 0
|  | Erection | Kg | 85977 | 85876.7 | 0 | 85876.7 | 99.88% |  | #REF! |  |  | 85876.7 | 0 | 85876.7 | 0
|  | Alignment | Kg | 85977 | 85877 | 0 | 85877 | 99.88% |  | #REF! |  |  | 85877 | 0 | 85877 | 0
|  | Bolt Tightening & Test | Kg | 85977 | 85877 | 0 | 85877 | 99.88% |  | #REF! |  |  | 85877 | 0 | 85877 | 0
|  | Grouting | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 12 | 0
|  | Final test & Documents | % | 100 | 63 | 0 | 63 | 63% |  | #REF! |  |  | 62 | -1 | 62 | -1
|  | 140-IM-B8 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 98013 | 98013 | 0 | 98013 | 100% |  | #REF! |  |  | 98013 | 0 | 98013 | 0
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 12 | 0
|  | Erection | Kg | 98013 | 97714 | 0 | 97714 | 99.69% |  | #REF! |  |  | 97713.1 | -0.9 | 97713.1 | -0.9
|  | Alignment | Kg | 98013 | 97714 | 0 | 97714 | 99.69% |  | #REF! |  |  | 97713 | -1 | 97713 | -1
|  | Bolt Tightening & Test | Kg | 98013 | 97714 | 0 | 97714 | 99.69% |  | #REF! |  |  | 97713 | -1 | 97713 | -1
|  | Grouting | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 12 | 0
|  | Final test & Documents | % | 100 | 65 | 0 | 65 | 65% |  | #REF! |  |  | 65 | 0 | 65 | 0
|  | 140-IM-B9 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 59040 | 59040 | 0 | 59040 | 100% |  | #REF! |  |  | 59500 | 460 | 59500 | 460
|  | Chip&Padding | NO | 8 | 8 | 0 | 8 | 100% |  | #REF! |  |  | 8 | 0 | 8 | 0
|  | Erection | Kg | 59040 | 59040 | 0 | 59040 | 100% |  | #REF! |  |  | 59500 | 460 | 59500 | 460
|  | Alignment | Kg | 59040 | 59040 | 0 | 59040 | 100% |  | #REF! |  |  | 59500 | 460 | 59500 | 460
|  | Bolt Tightening & Test | Kg | 59040 | 59040 | 0 | 59040 | 100% |  | #REF! |  |  | 59500 | 460 | 59500 | 460
|  | Grouting | NO | 8 | 8 | 0 | 8 | 100% |  | #REF! |  |  | 8 | 0 | 8 | 0
|  | Final test & Documents | % | 100 | 63 | 0 | 63 | 63% |  | #REF! |  |  | 62 | -1 | 62 | -1
|  | 140-IM-B10 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 101233 | 101233 | 0 | 101233 | 100% |  | #REF! |  |  | 101700 | 467 | 101700 | 467
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 12 | 0
|  | Erection | Kg | 101233 | 80020 | 0 | 80020 | 79.05% |  | #REF! |  |  | 74869.5 | -5150.5 | 74869.5 | -5150.5
|  | Alignment | Kg | 101233 | 80020 | 0 | 80020 | 79.05% |  | #REF! |  |  | 74483 | -5537 | 74483 | -5537
|  | Bolt Tightening & Test | Kg | 101233 | 63843 | 10290 | 74133 | 73.23% |  | #REF! |  |  | 74483 | 350 | 74483 | 350
|  | Grouting | NO | 12 | 7 | 5 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 0 | -12
|  | Final test & Documents | % | 100 | 46 | 0 | 46 | 46% |  | #REF! |  |  | 42 | -4 | 42 | -4
|  | 140-IM-B11 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 142969 | 142969 | 0 | 142969 | 100% |  | #REF! |  |  | 142783 | -186 | 142783 | -186
|  | Chip&Padding | NO | 24 | 24 | 0 | 24 | 100% |  | #REF! |  |  | 24 | 0 | 24 | 0
|  | Erection | Kg | 142969 | 142969 | 0 | 142969 | 100% |  | #REF! |  |  | 142783 | -186 | 142783 | -186
|  | Alignment | Kg | 142969 | 142969 | 0 | 142969 | 100% |  | #REF! |  |  | 142783 | -186 | 142783 | -186
|  | Bolt Tightening & Test | Kg | 142969 | 142969 | 0 | 142969 | 100% |  | #REF! |  |  | 142783 | -186 | 142783 | -186
|  | Grouting | NO | 24 | 24 | 0 | 24 | 100% |  | #REF! |  |  | 24 | 0 | 24 | 0
|  | Final test & Documents | % | 100 | 63 | 0 | 63 | 63% |  | #REF! |  |  | 62 | -1 | 62 | -1
|  | 140-IM-B12 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 81227 | 81227 | 673 | 81900 | 100.8% |  | #REF! |  |  | 81900 | 0 | 81900 | 0
|  | Chip&Padding | NO | 6 | 6 | 0 | 6 | 100% |  | #REF! |  |  | 6 | 0 | 6 | 0
|  | Erection | Kg | 81227 | 81227 | 673 | 81900 | 100.8% |  | #REF! |  |  | 81900 | 0 | 81900 | 0
|  | Alignment | Kg | 81227 | 0 | 25000 | 25000 | 30.78% |  | #REF! |  |  | 25000 | 0 | 25000 | 0
|  | Bolt Tightening & Test | Kg | 81227 | 0 | 25000 | 25000 | 30.78% |  | #REF! |  |  | 25000 | 0 | 25000 | 0
|  | Grouting | NO | 6 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final test & Documents | % | 100 | 41 | 3 | 44 | 44% |  | #REF! |  |  | 44 | 0 | 44 | 0
|  | 140-IM-B13 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 115037 | 115037 | 0 | 115037 | 100% |  | #REF! |  |  | 115037 | 0 | 115037 | 0
|  | Chip&Padding | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! |  |  | 14 | 0 | 14 | 0
|  | Erection | Kg | 115037 | 75808 | 0 | 75808 | 65.9% |  | #REF! |  |  | 75807.5 | -0.5 | 75807.5 | -0.5
|  | Alignment | Kg | 115037 | 0 | 40000 | 40000 | 34.77% |  | #REF! |  |  | 40000 | 0 | 0 | -40000
|  | Bolt Tightening & Test | Kg | 115037 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Grouting | NO | 14 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final test & Documents | % | 100 | 31 | 0 | 31 | 31% |  | #REF! |  |  | 31 | 0 | 31 | 0
|  | 140-IM-C1 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 34919 | 34919 | 0 | 34919 | 100% |  | #REF! |  |  | 33400 | -1519 | 33400 | -1519
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 12 | 0
|  | Erection | Kg | 34919 | 34919 | 0 | 34919 | 100% |  | #REF! |  |  | 33399.6 | -1519.4 | 33399.6 | -1519.4
|  | Alignment | Kg | 34919 | 34919 | 0 | 34919 | 100% |  | #REF! |  |  | 33400 | -1519 | 33400 | -1519
|  | Bolt Tightening & Test | Kg | 34919 | 34919 | 0 | 34919 | 100% |  | #REF! |  |  | 33400 | -1519 | 33400 | -1519
|  | Grouting | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 0 | -12
|  | Final test & Documents | % | 100 | 56 | 0 | 56 | 56% |  | #REF! |  |  | 55 | -1 | 55 | -1
|  | 140-IM-C2 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 63237 | 63237 | 0 | 63237 | 100% |  | #REF! |  |  | 63000 | -237 | 63000 | -237
|  | Chip&Padding | NO | 22 | 22 | 0 | 22 | 100% |  | #REF! |  |  | 22 | 0 | 22 | 0
|  | Erection | Kg | 63237 | 63237 | 0 | 63237 | 100% |  | #REF! |  |  | 63000 | -237 | 63000 | -237
|  | Alignment | Kg | 63237 | 63237 | 0 | 63237 | 100% |  | #REF! |  |  | 63000 | -237 | 63000 | -237
|  | Bolt Tightening & Test | Kg | 63237 | 63237 | 0 | 63237 | 100% |  | #REF! |  |  | 63000 | -237 | 63000 | -237
|  | Grouting | NO | 22 | 22 | 0 | 22 | 100% |  | #REF! |  |  | 22 | 0 | 22 | 0
|  | Final test & Documents | % | 100 | 63 | 0 | 63 | 63% |  | #REF! |  |  | 61 | -2 | 61 | -2
|  | 140-IM-C3 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 32631 | 32631 | 0 | 32631 | 100% |  | #REF! |  |  | 31800 | -831 | 31800 | -831
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 12 | 0
|  | Erection | Kg | 32631 | 32631 | 0 | 32631 | 100% |  | #REF! |  |  | 31800 | -831 | 31800 | -831
|  | Alignment | Kg | 32631 | 32631 | 0 | 32631 | 100% |  | #REF! |  |  | 31800 | -831 | 31800 | -831
|  | Bolt Tightening & Test | Kg | 32631 | 32631 | 0 | 32631 | 100% |  | #REF! |  |  | 31800 | -831 | 31800 | -831
|  | Grouting | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! |  |  | 12 | 0 | 12 | 0
|  | Final test & Documents | % | 100 | 63 | 0 | 63 | 63% |  | #REF! |  |  | 61 | -2 | 61 | -2
|  | 140-IM-D1 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 57553 | 57553 | 0 | 57553 | 100% |  | #REF! |  |  | 57553 | 0 | 57553 | 0
|  | Chip&Padding | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! |  |  | 18 | 0 | 18 | 0
|  | Erection | Kg | 57553 | 57553 | 0 | 57553 | 100% |  | #REF! |  |  | 57553 | 0 | 57553 | 0
|  | Alignment | Kg | 57553 | 57553 | 0 | 57553 | 100% |  | #REF! |  |  | 57553 | 0 | 57553 | 0
|  | Bolt Tightening & Test | Kg | 57553 | 57553 | 0 | 57553 | 100% |  | #REF! |  |  | 57553 | 0 | 57553 | 0
|  | Grouting | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! |  |  | 18 | 0 | 18 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 46 | -21 | 46 | -21
|  | 140-IM-D2 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 51015 | 51015 | 0 | 51015 | 100% |  | #REF! |  |  | 50938 | -77 | 50938 | -77
|  | Chip&Padding | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! |  |  | 16 | 0 | 16 | 0
|  | Erection | Kg | 51015 | 51015 | 0 | 51015 | 100% |  | #REF! |  |  | 51015 | 0 | 51015 | 0
|  | Alignment | Kg | 51015 | 51015 | 0 | 51015 | 100% |  | #REF! |  |  | 51015 | 0 | 51015 | 0
|  | Bolt Tightening & Test | Kg | 51015 | 51015 | 0 | 51015 | 100% |  | #REF! |  |  | 51015 | 0 | 51015 | 0
|  | Grouting | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! |  |  | 16 | 0 | 16 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 62 | -5 | 62 | -5
|  | 140-IM-D3 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 67658 | 67658 | 0 | 67658 | 100% |  | #REF! |  |  | 67658 | 0 | 67658 | 0
|  | Chip&Padding | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! |  |  | 26 | 0 | 26 | 0
|  | Erection | Kg | 67658 | 67658 | 0 | 67658 | 100% |  | #REF! |  |  | 67658 | 0 | 67658 | 0
|  | Alignment | Kg | 67658 | 67658 | 0 | 67658 | 100% |  | #REF! |  |  | 67658 | 0 | 67658 | 0
|  | Bolt Tightening & Test | Kg | 67658 | 67658 | 0 | 67658 | 100% |  | #REF! |  |  | 67658 | 0 | 67658 | 0
|  | Grouting | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! |  |  | 26 | 0 | 26 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 62 | -5 | 62 | -5
|  | 140-IM-D4 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 58695 | 58695 | 0 | 58695 | 100% |  | #REF! |  |  | 58695 | 0 | 58695 | 0
|  | Chip&Padding | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! |  |  | 18 | 0 | 18 | 0
|  | Erection | Kg | 58695 | 58695 | 0 | 58695 | 100% |  | #REF! |  |  | 58695 | 0 | 58695 | 0
|  | Alignment | Kg | 58695 | 58695 | 0 | 58695 | 100% |  | #REF! |  |  | 58695 | 0 | 58695 | 0
|  | Bolt Tightening & Test | Kg | 58695 | 58695 | 0 | 58695 | 100% |  | #REF! |  |  | 58695 | 0 | 58695 | 0
|  | Grouting | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! |  |  | 18 | 0 | 0 | -18
|  | Final test & Documents | % | 100 | 56 | 0 | 56 | 56% |  | #REF! |  |  | 54 | -2 | 54 | -2
|  | 140-IM-E1 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 53769 | 53769 | 0 | 53769 | 100% |  | #REF! |  |  | 50500 | -3269 | 50500 | -3269
|  | Chip&Padding | NO | 20 | 20 | 0 | 20 | 100% |  | #REF! |  |  | 20 | 0 | 20 | 0
|  | Erection | Kg | 53769 | 43169 | 1560.2 | 44729.2 | 83.19% |  | #REF! |  |  | 42011.2 | -2718 | 42011.2 | -2718
|  | Alignment | Kg | 53769 | 32718 | 12011.2 | 44729.2 | 83.19% |  | #REF! |  |  | 42011 | -2718.2 | 42011 | -2718.2
|  | Bolt Tightening & Test | Kg | 53769 | 32718 | 12011.2 | 44729.2 | 83.19% |  | #REF! |  |  | 42011 | -2718.2 | 42011 | -2718.2
|  | Grouting | NO | 20 | 12 | 8 | 20 | 100% |  | #REF! |  |  | 20 | 0 | 0 | -20
|  | Final test & Documents | % | 100 | 48 | 0 | 48 | 48% |  | #REF! |  |  | 47 | -1 | 47 | -1
|  | 140-IM-E2 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 64679 | 64679 | 0 | 64679 | 100% |  | #REF! |  |  | 64679 | 0 | 64679 | 0
|  | Chip&Padding | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! |  |  | 26 | 0 | 26 | 0
|  | Erection | Kg | 64679 | 64679 | 0 | 64679 | 100% |  | #REF! |  |  | 64679 | 0 | 64679 | 0
|  | Alignment | Kg | 64679 | 64679 | 0 | 64679 | 100% |  | #REF! |  |  | 64679 | 0 | 64679 | 0
|  | Bolt Tightening & Test | Kg | 64679 | 64679 | 0 | 64679 | 100% |  | #REF! |  |  | 64679 | 0 | 64679 | 0
|  | Grouting | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! |  |  | 26 | 0 | 26 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 62 | -5 | 62 | -5
|  | 140-IM-E3 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 38932 | 38932 | 0 | 38932 | 100% |  | #REF! |  |  | 40000 | 1068 | 40000 | 1068
|  | Chip&Padding | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! |  |  | 16 | 0 | 16 | 0
|  | Erection | Kg | 38932 | 38457 | 475 | 38932 | 100% |  | #REF! |  |  | 40000 | 1068 | 40000 | 1068
|  | Alignment | Kg | 38932 | 38457 | 475 | 38932 | 100% |  | #REF! |  |  | 40000 | 1068 | 40000 | 1068
|  | Bolt Tightening & Test | Kg | 38932 | 24332 | 0 | 24332 | 62.5% |  | #REF! |  |  | 25000 | 668 | 25000 | 668
|  | Grouting | NO | 16 | 0 | 16 | 16 | 100% |  | #REF! |  |  | 0 | -16 | 0 | -16
|  | Final test & Documents | % | 100 | 52 | 0 | 52 | 52% |  | #REF! |  |  | 49 | -3 | 49 | -3
|  | 140-IM-E4 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 14165 | 14130 | 35 | 14165 | 100% |  | #REF! |  |  | 14200 | 35 | 14200 | 35
|  | Chip&Padding | NO | 6 | 6 | 0 | 6 | 100% |  | #REF! |  |  | 6 | 0 | 6 | 0
|  | Erection | Kg | 14165 | 14165 | 0 | 14165 | 100% |  | #REF! |  |  | 14200.4 | 35.4 | 14200.4 | 35.4
|  | Alignment | Kg | 14165 | 14130 | 35 | 14165 | 100% |  | #REF! |  |  | 14200 | 35 | 14200 | 35
|  | Bolt Tightening & Test | Kg | 14165 | 14130 | 35 | 14165 | 100% |  | #REF! |  |  | 14200 | 35 | 14200 | 35
|  | Grouting | NO | 6 | 0 | 6 | 6 | 100% |  | #REF! |  |  | 0 | -6 | 0 | -6
|  | Final test & Documents | % | 100 | 54 | 0 | 54 | 54% |  | #REF! |  |  | 54 | 0 | 54 | 0
|  | 140-IM-F1 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 36958 | 36958 | 0 | 36958 | 100% |  | #REF! |  |  | 35800 | -1158 | 35800 | -1158
|  | Chip&Padding | NO | 20 | 20 | 0 | 20 | 100% |  | #REF! |  |  | 20 | 0 | 20 | 0
|  | Erection | Kg | 36958 | 36958 | 0 | 36958 | 100% |  | #REF! |  |  | 35800.2 | -1157.8 | 35800.2 | -1157.8
|  | Alignment | Kg | 36958 | 0 | 36958 | 36958 | 100% |  | #REF! |  |  | 35800 | -1158 | 35800 | -1158
|  | Bolt Tightening & Test | Kg | 36958 | 0 | 36958 | 36958 | 100% |  | #REF! |  |  | 35800 | -1158 | 35800 | -1158
|  | Grouting | NO | 20 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final test & Documents | % | 100 | 48 | 6 | 54 | 54% |  | #REF! |  |  | 54 | 0 | 54 | 0
|  | 140-IM-F2 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 57287 | 57287 | 0 | 57287 | 100% |  | #REF! |  |  | 54300 | -2987 | 54300 | -2987
|  | Chip&Padding | NO | 22 | 22 | 0 | 22 | 100% |  | #REF! |  |  | 22 | 0 | 22 | 0
|  | Erection | Kg | 57287 | 57287 | 0 | 57287 | 100% |  | #REF! |  |  | 54300 | -2987 | 54300 | -2987
|  | Alignment | Kg | 57287 | 57287 | 0 | 57287 | 100% |  | #REF! |  |  | 54300 | -2987 | 54300 | -2987
|  | Bolt Tightening & Test | Kg | 57287 | 57287 | 0 | 57287 | 100% |  | #REF! |  |  | 54300 | -2987 | 54300 | -2987
|  | Grouting | NO | 22 | 22 | 0 | 22 | 100% |  | #REF! |  |  | 22 | 0 | 22 | 0
|  | Final test & Documents | % | 100 | 67 | 0 | 67 | 67% |  | #REF! |  |  | 62 | -5 | 62 | -5
|  | Fireproofing | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Fireproofing | m2 | 200 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Insulation | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Cold Insulation | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hot Insulation | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Equipment Packages | [11 empty] | 0 |  | 0
|  | Static Equipment | [11 empty] | 0 |  | 0
|  | HP FLARE 140-X-101 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP FLARE 140-X-201 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LP FLARE 140-X-102 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 22000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 22000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 22000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 22000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LP FLARE 140-X-202 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 22000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 22000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 22000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 22000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | MP FLARE 140-X-103 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | MP FLARE 140-X-203 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 190000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-101 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-103 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Cold Flare K.O. Drum Heater 140-DH-104 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 249 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 249 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 249 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 249 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-201 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | MP Flare K.O. Drum Heater 140-DH-203 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Cold Flare K.O. Drum Heater 140-DH-204 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 249 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 249 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 249 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 249 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-105 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-106 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-205 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-206 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 12000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Rotary Equipment | [11 empty] | 0 |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-104A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP FLARE STACKS PUMPS, 140-P-104B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LP FLARE STACKS PUMPS, 140-P-105A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LP FLARE STACKS PUMPS, 140-P-105B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | MP FLARE STACKS PUMPS, 140-P-106A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | MP FLARE STACKS PUMPS, 140-P-106B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP FLARE STACKS PUMPS, 140-P-204A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HP FLARE STACKS PUMPS, 140-P-204B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LP FLARE STACKS PUMPS, 140-P-205A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LP FLARE STACKS PUMPS, 140-P-205B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | MP FLARE STACKS PUMPS, 140-P-206A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | MP FLARE STACKS PUMPS, 140-P-206B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1183 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Unit 143 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Welding & NDT Procedures | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Qualification of Welding Equipments | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Maintaining Welder Qualification Records | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Monitoring Welder Performance | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Prepare NDT Procedures & Obtain Certification | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Perform NDT as per the Procedures | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 50 | -50
|  | Prepare PWHT Procedures & Obtain Certification | % | 100 | 0 | 40 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Perform PWHT Testing | % | 100 | 0 | 40 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 20 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Piping | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | AG Piping | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Shop | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Carbon Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 26984 | 5220 | 8776 | 13996 | 51.87% |  | #REF! | 5220 | 8776 | 5220 | -8776 | 4780 | -9216
|  | Cutting & Bevelling & Fit Up | ID | 8095 | 1172 | 2899 | 4071 | 50.29% |  | #REF! | 1172 | 2899 | 1458 | -2613 | 900 | -3171
|  | Welding | ID | 8095 | 900 | 2636 | 3536 | 43.68% |  | #REF! | 900 | 2636 | 1116 | -2420 | 576 | -2960
|  | NDT | ID | 8095 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | PWHT | ID | 8095 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 | 25 | 0 | 25 | 0
|  | Low Temperature CS | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 93 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 28 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 28 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 28 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 28 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 25 | 0
|  | Stainless Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 41 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 12 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 12 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 12 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 12 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 25 | 0
|  | Galva | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 1971 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 591 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 591 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 591 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 591 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 25 | 0
|  | CU-NI | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 5256 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 1577 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 1577 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 1577 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 1577 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 25 | 0
|  | Field | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Carbon Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 26984 | 1488 | 1400 | 2888 | 10.7% |  | #REF! | 1488 | 1400 | 1488 | -1400 | 1072 | -1816
|  | Scaffolding | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 18889 | 966 | 861 | 1827 | 9.672% |  | #REF! | 966 | 861 | 1455 | -372 | 756 | -1071
|  | Valve Installation | ID | 380 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Welding | ID | 18889 | 706 | 1118 | 1824 | 9.656% |  | #REF! | 706 | 1118 | 1328 | -496 | 756 | -1068
|  | NDT | ID | 18889 | 540 | 0 | 540 | 2.859% |  | #REF! | 540 | 0 | 540 | 0 | 540 | 0
|  | PWHT | ID | 18889 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Hydro test | ID | 18889 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 | 25 | 0 | 25 | 0
|  | Low Temperature CS | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 93 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 380 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 25 | 0
|  | Stainless Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 41 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 380 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 25 | 0
|  | Galva | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 1971 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 25 | 0
|  | CU-NI | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 5256 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 380 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! |  |  | 25 | 0 | 25 | 0
|  | Pipe Support | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Shop | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 10800 | 0 | 10800 | 10800 | 100% |  | #REF! |  |  | 0 | -10800 | 0 | -10800
|  | shop drawing | Kg | 10800 | 0 | 10800 | 10800 | 100% |  | #REF! |  |  | 0 | -10800 | 0 | -10800
|  | Cutting & assembling | Kg | 10800 | 0 | 10000 | 10000 | 92.59% |  | #REF! |  |  | 0 | -10000 | 0 | -10000
|  | Welding | Kg | 10800 | 0 | 5000 | 5000 | 46.3% |  | #REF! |  |  | 0 | -5000 | 0 | -5000
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Field | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | Kg | 10800 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection | Kg | 10800 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | Kg | 10800 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | Kg | 10800 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Painting & Sandblasting | [11 empty] | 0 |  | 0
|  | Pipe |  |  |  | 0 | [7 empty] | 0 |  | 0
|  | Sand Blast | m2 | 11000 | 4663.99 | 1255.3 | 5919.29 | 53.81% |  |  |  |  | 466399% | -1255.3 | 4240.99 | -1678.3
|  | Primer | m2 | 11000 | 4663.99 | 1255.3 | 5919.29 | 53.81% |  |  |  |  | 466399% | -1255.3 | 4240.99 | -1678.3
|  | Middle Paint | m2 | 11000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Paint | m2 | 11000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Touch Up & Punch | m2 | 11000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Support |  |  |  | 0 | [7 empty] | 0 |  | 0
|  | Sand Blast | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Primer | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Middle Paint | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Paint | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Touch Up & Punch | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Certificate | % | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Insulation | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Cold Insulation | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hot Insulation | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Equipment Packages | [11 empty] | 0 |  | 0
|  | Static Equipment | [11 empty] | 0 |  | 0
|  | Sump Drum 143-D-101 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 10338 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 10338 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 10338 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 10338 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Degassing Boot 143-D-102 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 2920 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 2920 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 2920 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 2920 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Rotary Equipment | [11 empty] | 0 |  | 0
|  | Pump 143-P-101 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1433 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1433 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1433 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1433 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 143-P-102 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 2634 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 2634 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 2634 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 2634 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 143-P-103 A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 143-P-103 B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 143-P-103 C | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 143-P-104 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 879 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 879 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 879 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 879 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Unit 147/148 | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Welding & NDT Procedures | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Qualification of Welding Equipments | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 50 | -50 | 50 | -50
|  | Maintaining Welder Qualification Records | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Monitoring Welder Performance | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 100 | 0
|  | Prepare NDT Procedures & Obtain Certification | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Perform NDT as per the Procedures | % | 100 | 20 | 80 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 0 | -100
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  |  | 100 | 0 | 50 | -50
|  | Prepare PWHT Procedures & Obtain Certification | % | 100 | 0 | 40 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Perform PWHT Testing | % | 100 | 0 | 40 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 20 | 40 | 40% |  | #REF! |  |  | 0 | -40 | 0 | -40
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100.0001 | 0 | 100.0001 | 100% |  | #REF! |  |  | 100.0001 | 0 | 100.0001 | 0
|  | Piping | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | AG Piping | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Shop | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Carbon Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 4934 | 1369 | 64 | 1433 | 29.04% |  | #REF! |  |  | 1369 | -64 | 600 | -833
|  | Cutting & Bevelling & Fit Up | ID | 1480 | 80 | 487 | 567 | 38.31% |  | #REF! |  |  | 231 | -336 | 0 | -567
|  | Welding | ID | 1480 | 0 | 374 | 374 | 25.27% |  | #REF! |  |  | 236 | -138 | 0 | -374
|  | NDT | ID | 1480 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 1480 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | Low Temperature CS | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 36676 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 11003 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 11003 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 11003 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 11003 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | Galva | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 544 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 163 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 163 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 163 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 163 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | GRE & Stainless Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Lay down To Shop | ID | 578 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & Bevelling & Fit Up | ID | 173 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 173 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 173 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 173 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | Field | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Carbon Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 6223 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 4045 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 4045 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 4045 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 4045 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 4045 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | Low Temperature CS | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 36676 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 611 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | Galva | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 544 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 611 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | GRE | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Scoffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Material Handling To Field | ID | 386 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fittup | ID | 270 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Bonding | ID | 270 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 270 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | Stainless Steel | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | ID | 192 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Scaffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection & Fit Up | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Valve Installation | ID | 611 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | PWHT | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hydro test | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! |  |  | 20 | -20 | 20 | -20
|  | Pipe Support | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Shop | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Handling | Kg | 18000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | shop drawing | Kg | 18000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Cutting & assembling | Kg | 18000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | Kg | 18000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Field | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Material Handling From Shop To Field | Kg | 18000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Erection | Kg | 18000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Welding | Kg | 18000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | NDT | Kg | 18000 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Painting & Sandblasting | [11 empty] | 0 |  | 0
|  | Pipe |  |  |  | 0 | [7 empty] | 0 |  | 0
|  | Sand Blast | m2 | 5200 | 429 | 400.5 | 829.5 | 15.95% |  |  |  |  | 42900% | -400.5 | 415 | -414.5
|  | Primer | m2 | 5201 | 429 | 400.5 | 829.5 | 15.95% |  |  |  |  | 42900% | -400.5 | 415 | -414.5
|  | Middle Paint | m2 | 5202 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Paint | m2 | 5203 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Touch Up & Punch | m2 | 5204 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Support |  |  |  | 0 | [7 empty] | 0 |  | 0
|  | Sand Blast | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Primer | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Middle Paint | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Paint | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Touch Up & Punch | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Certificate | % | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Insulation | [7 empty] | #REF! |  |  |  | 0 |  | 0
|  | Cold Insulation | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Hot Insulation | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  |  | 0 | 0 | 0 | 0
|  | Equipment Packages | [11 empty] | 0 |  | 0
|  | Static Equipment | [11 empty] | 0 |  | 0
|  | Air cooler 147-A-101 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Vert.) 147-D-101 A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 20450 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 20450 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 20450 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 20450 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Vert.) 147-D-101 B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 20450 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 20450 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 20450 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 20450 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Vert.) 147-D-102 A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 10750 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 10750 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 10750 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 10750 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Vert.) 147-D-102 B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 10750 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 10750 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 10750 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 10750 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Vert.) 147-D-103 A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 11100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 11100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 11100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 11100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Vert.) 147-D-103 B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 11100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 11100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 11100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 11100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Hori) 147-D-104 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 60900 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 60900 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 60900 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 60900 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Vert.) 147-D-105 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 13200 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 13200 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 13200 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 13200 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Hori) 147-D-106 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 6800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 6800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 6800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 6800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Hori) 147-D-107 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 13000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 13000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 13000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 13000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Hori) 147-D-108 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Hori.) in Sump 147-D-109 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 16440 | 16060 | 380 | 16440 | 100% |  |  |  |  | 1644000% | 0 | 0 | -16440
|  | Chipping & Padding | % | 100 | 100 | 0 | 100 | 100% |  |  |  |  | 10000% | 0 | 0 | -100
|  | Installation | Kg | 16440 | 0 | 16440 | 16440 | 100% |  |  |  |  | 0% | -16440 | 0 | -16440
|  | Alignment | Kg | 16440 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Drum (Hori) on St. 147-D-110 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 35205 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 35205 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 35205 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 35205 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LP FLARE K.O. DRUM 147-D-111 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 5300 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 5300 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 5300 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 5300 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Electric Heater 147-DH-107 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 124 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 124 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 124 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 124 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Electric Heater 147-DH-108 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 235 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 235 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 235 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 235 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Electric Heater 147-DH-109 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 195 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 195 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 195 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 195 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Electric Heater 147-DH-110 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 244 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LPG TANK FLARE 147-X-101 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 25000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 25000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 25000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 25000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | LOW PRESSURE PROPANE CHILLER 147-E-101 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 9890 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 9890 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 9890 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 9890 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | MEDUIM PRESSURE PROPANE CHILLER 147-E-102 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 20700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 20700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 20700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 20700 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | HIGH PRESSURE PROPANE CHILLER 147-E-103 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 13600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 13600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 13600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 13600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | PROPANE BOIL OFF GAS CONDENSER 147-E-104 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 7000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 7000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 7000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 7000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Rotary Equipment | [11 empty] | 0 |  | 0
|  | Compressor 147-K-101A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 132600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 132600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 132600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 132600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Compressor 147-K-101B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 132600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 132600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 132600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 132600 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Compressor 147-K-102A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 48000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 48000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 48000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 48000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Compressor 147-K-102B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 48000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 48000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 48000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 48000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-101A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-101B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-101C | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1800 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-102 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-103A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-103B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-103C | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-104 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-106 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1120 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1120 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1120 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1120 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-107 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1046 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1046 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1046 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1046 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-108 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 955 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 955 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 955 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 955 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-109A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 930 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 930 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 930 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 930 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 147-P-109B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 930 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 930 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 930 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 930 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 148-P-101A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 148-P-101B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 148-P-101C | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 1000 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 148-P-102 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 148-P-103A | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 148-P-103B | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 148-P-103C | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Pump 148-P-104 | [11 empty] | 0 |  | 0
|  | Material Handling | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Chipping & Padding | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Alignment | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Grouting | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | External Installation | Kg | 500 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
|  | Final Inspection | % | 100 | 0 | 0 | 0 | 0% |  |  |  |  | 0% | 0 | 0 | 0
[14 empty] | 0 |  | 0
232049999999.9999
9825103953.4884
1761398233.3764
120317904475.3876
40837741910.0229
59307851427.7247

## Planning 1 (hidden)
South Pars Gas Field Development Phases 14
|  | Date : | 2013-08-31
Description |  |  | Unit | Quantity |  |  |  | Work Performed | Remain | W.F | Up To Now
|  |  |  | Estimate | Up To Last |  | This Month |  |  |  | % Actual |  | 58
|  | Package NO.2 | [7 empty] | 100% | 27.84% |  | 2.6
|  | Procurement | per |  |  | 76.06% |  |  |  | 15% | 76.07% |  | 6826
|  | fire proof | per | [6 empty] | 0.1987% | 0% |  | 29
|  | PO Placement | m2 | 200 | [5 empty] | 0.04968% | 0% |  | 35
|  | Fabrication & Test | m2 | 200 | [5 empty] | 0.1192% | 0% |  | 2275
|  | Delivery | m2 | 200 | [5 empty] | 0.02981% | 0% |  | 103
|  | Rebar | per | [6 empty] | 4.373% | 100% | 308693 | 28
|  | PO Placement | Kg | 308693 |  |  |  | 308693 |  | 1.093% | 100% |  | 100
|  | Fabrication & Test | Kg | 308693 |  |  |  | 308693 |  | 2.624% | 100% |  | 150
|  | Delivery | Kg | 308693 |  |  |  | 308693 |  | 0.6559% | 100% |  | 1000
|  | Piping Support | per | [6 empty] | 0.934% | 85% |  | 100
|  | PO Placement | Kg | 72000 |  |  |  | 72000 |  | 0.2335% | 100%
|  | Fabrication & Test | Kg | 72000 |  |  |  | 72000 |  | 0.5604% | 100%
|  | Delivery | Kg | 72000 | [5 empty] | 0.1401% | 0%
|  | Cold Insulating | per | [6 empty] | 0.7797% | 0% |  | 0
|  | PO Placement | m2 | 5862 | [5 empty] | 0.1949% | 0%
|  | Fabrication & Test | m2 | 5862 | [5 empty] | 0.4678% | 0%
|  | Delivery | m2 | 5862 | [5 empty] | 0.117% | 0%
|  | Warm Insulating | per | [6 empty] | 0.5209% | 0% |  | 0
|  | PO Placement | m2 | 2937 | [5 empty] | 0.1302% | 0%
|  | Fabrication & Test | m2 | 2937 | [5 empty] | 0.3125% | 0%
|  | Delivery | m2 | 2937 | [5 empty] | 0.07813% | 0%
|  | Paint | per | [6 empty] | 5.56% | 80.58% | 13900 | 13900
|  | PO Placement | Kg | 57000 |  |  |  | 57000 |  | 4.17% | 100%
|  | Delivery | Kg | 57000 |  |  |  | 12730 |  | 1.39% | 22.33%
|  | Electrode | per | [6 empty] | 2.634% | 66.96% | 18080 | 18080
|  | PO Placement | Kg | 27000 |  |  |  | 18080 |  | 0.6584% | 66.96%
|  | Fabrication & Test | Kg | 27000 |  |  |  | 18080 |  | 1.58% | 66.96%
|  | Delivery | Kg | 27000 |  |  |  | 18080 |  | 0.3951% | 66.96%
|  | Plant Construction |  |  |  | 18.89% |  |  |  | 85% | 19.33% |  | 0
|  | General |  |  |  | 47.49% |  |  |  | 3.599% | 49.66% |  | 0
|  | mobolization | [7 empty] | 3.249% | 55% |  | 0
|  | primary mobilozation | % | 100 | 100 | 100% | 0 | 100 |  | 1.3% | 100% | 100 | 0
|  | countiuse mobilization | % | 100 | 21 | 21% | 4 | 25 |  | 1.95% | 25% | 27 | 2
|  | Demobilizaton |  |  |  |  | 0 |  |  | 0.3496% | 0% |  | 0
|  | Demobilizaton | % | 100 | 0 | 0% | 0 | 0 |  | 0.3496% | 0% |  | 0
|  | Gate House | civ |  |  | 20% | 0 |  |  | 0.6452% | 25% |  | 0
|  | civil | civ |  |  | 80% | 0 |  |  | 0.1613% | 100% |  | 0
| ` | Foundation | % | 100 | 100 | 100% | 0 | 100 |  | 0.04839% | 100% | 100 | 0
|  | columns | % | 100 | 100 | 100% | 0 | 100 |  | 0.04839% | 100% | 100 | 0
|  | Wall | % | 100 | 0 | 0% | 100 | 100 |  | 0.01613% | 100% |  | -100
|  | Floor | % | 100 | 0 | 0% | 100 | 100 |  | 0.01613% | 100% |  | -100
|  | Roof | % | 100 | 100 | 100% | 0 | 100 |  | 0.03226% | 100% | 95 | -5
|  | Mechanical | civ |  |  | 0% | 0 |  |  | 0.06452% | 0% |  | 0
|  | Piping | % | 100 | 0 | 0% | 0 | 0 |  | 0.04516% | 0% |  | 0
|  | Installation | % | 100 | 0 | 0% | 0 | 0 |  | 0.01936% | 0% |  | 0
|  | electrical | civ |  |  | 0% | 0 |  |  | 0.06452% | 0% |  | 0
|  | Cabling | % | 100 | 0 | 0% | 0 | 0 |  | 0.04516% | 0% |  | 0
|  | Installation | % | 100 | 0 | 0% | 0 | 0 |  | 0.01936% | 0% |  | 0
|  | telecom | civ |  |  | 0% | 0 |  |  | 0.129% | 0% |  | 0
|  | telecom | % | 100 | 0 | 0% | 0 | 0 |  | 0.129% | 0% |  | 0
|  | architect | civ |  |  | 0% | 0 |  |  | 0.1936% | 0% |  | 0
|  | architect | % | 100 | 0 | 0% | 0 | 0 |  | 0.1936% | 0% |  | 0
|  | final works | civ |  |  | 0% | 0 |  |  | 0.03226% | 0% |  | 0
|  | final works | % | 100 | 0 | 0% | 0 | 0 |  | 0.03226% | 0% |  | 0
|  | Unit 140 |  |  |  | 27.04% | 0 |  |  | 43.74% | 28.31% |  | 0
|  | Welding & NDT Procedures | pip |  |  | 30.2% | 0 |  |  | 2.527% | 62% |  | 0
|  | Prepare and qualify welding procedures (welding procedures qualfication tests (WPQT) including lab. Tests) for structural and pipe welding | % | 100 | 100 | 100% | 0 | 100 |  | 0.01263% | 100% | 100 | 0
|  | Qualification of welders including lab testing for structural and pipe welding | % | 100 | 100 | 100% | 0 | 100 |  | 0.01263% | 100% | 100 | 0
|  | Qualification of welding equipment | % | 100 | 100 | 100% | 0 | 100 |  | 0.01263% | 100% | 100 | 0
|  | Maintaining welder qualification records | % | 100 | 100 | 100% | 0 | 100 |  | 0.01263% | 100% | 100 | 0
|  | Monitoring welder performance | % | 100 | 100 | 100% | 0 | 100 |  | 0.01263% | 100% | 100 | 0
|  | Prepare and NDT Procedures and obtain certification | % | 100 | 50 | 50% | 5 | 55 |  | 0.7581% | 100% |  | -55
|  | Qualification of NDT equipment and dimensional control (UT, RT, MT,...) | % | 100 | 20 | 20% | 5 | 25 |  | 0.01263% | 100% |  | -25
|  | Qualification of equipment operators for NDT and dimensional control | % | 100 | 20 | 20% | 5 | 25 |  | 0.01263% | 100% |  | -25
|  | Perform NDT as per the procedures | % | 100 | 20 | 20% | 5 | 25 |  | 0.2022% | 100% |  | -25
|  | Supply of associated Elec. Power, consumables, Materials construction equipments | % | 100 | 100 | 100% | 0 | 100 |  | 0.2022% | 100% | 100 | 0
|  | Prepare PWHT procedure and obtain certification | % | 100 | 0 | 0% | 0 | 0 |  | 0.6317% | 0% |  | 0
|  | Perform PWHT testing | % | 100 | 0 | 0% | 0 | 0 |  | 0.3285% | 0% |  | 0
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 20% | 5 | 25 |  | 0.3032% | 100% |  | -25
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100 | 100% | 0 | 100 |  | 0.01263% | 100% | 100 | 0
|  | Civil | civ |  |  | 48.39% |  |  |  | 5.511% | 35.29% |  | 0
|  | Plat Form |  |  |  | 81.47% |  |  |  | 2.567% | 60.61% |  | 0
|  | West HP |  |  |  | 88.9% |  |  |  | 1.097% | 58.52% |  | 0
|  | excavation | m3 | 1983 | 1983 | 100% | 218 | 1765 | 539 | 0.08773% | 89.01% | 1385 | -380
|  | level&compact | m2 | 851 | 851 | 100% | 146 | 705 | 269 | 0.02193% | 82.84% | 588 | -117
|  | lean | m3 | 36.57 | 36.57 | 100% | 4.57 | 32 | 9 | 0.01097% | 87.5% | 40 | 8
|  | footing rebar | Kg | 33778 | 33778 | 100% | 30910 | 2868 | 7829.5 | 0.1535% | 8.491% | 25188 | 22320
|  | footing form | m2 | 309 | 309 | 100% | 132 | 177 | 132 | 0.1151% | 57.28% | 195 | 18
|  | foting concrete | m3 | 448 | 448 | 100% | 90 | 358 | 90 | 0.2303% | 79.91% | 343 | -15
|  | ped rebar | Kg | 22520 | 22520 | 100% | 3355.5 | 19164.5 | 3355.5 | 0.0658% | 85.1% | 11666 | -7498.5
|  | ped form | m2 | 376 | 376 | 100% | 132 | 244 | 132 | 0.04935% | 64.89% | 225 | -19
|  | anchor | NO. | 418 | 418 | 100% | 166 | 252 | 166 | 0.05483% | 60.29% | 98 | -154
|  | ped concrete | m3 | 146 | 138.7584 | 95.04% | 26 | 120 | 26 | 0.09869% | 82.19% | 12 | -108
|  | curing | % | 100 | 85 | 85% | 80 | 20 | 80 | 0.01097% | 20% | 75 | 55
|  | coating | m2 | 1174 | 997.9 | 85% | 391 | 783 | 391 | 0.0329% | 85% | 400 | -383
|  | back fill | m3 | 1402 | 280.4 | 20% | 265 | 1137 | 265 | 0.1097% | 20% | 0 | -1137
|  | Final Certificate | % | 100 | 59 | 59% | 66 | 34 | 66 | 0.05483% | 34% | 50 | 16
|  | East HP |  |  |  | 86.36% | 0 |  |  | 1.078% | 74.18% |  | 0
|  | excavation | m3 | 1983 | 1983 | 100% | 0 | 1444 | 539 | 0.08621% | 72.82% | 1358 | -86
|  | level&compact | m2 | 845 | 845 | 100% | 0 | 583 | 262 | 0.02155% | 68.99% | 575 | -8
|  | lean | m3 | 36 | 36 | 100% | 0 | 27 | 9 | 0.01078% | 75% | 39 | 12
|  | footing rebar | Kg | 33471 | 33471 | 100% | 0 | 25641 | 7830 | 0.1509% | 76.61% | 26445 | 804
|  | footing form | m2 | 298 | 298 | 100% | 0 | 177 | 121 | 0.1132% | 59.4% | 200 | 23
|  | foting concrete | m3 | 444 | 444 | 100% | 0 | 359 | 85 | 0.2263% | 80.86% | 358 | -1
|  | ped rebar | Kg | 21315 | 21315 | 100% | 0 | 17959 | 3356 | 0.06466% | 84.26% | 12103 | -5856
|  | ped form | m2 | 389 | 389 | 100% | 0 | 244 | 145 | 0.04849% | 62.72% | 235 | -9
|  | anchor | NO. | 420 | 420 | 100% | 0 | 252 | 168 | 0.05388% | 60% | 132 | -120
|  | ped concrete | m3 | 146 | 103.4118 | 70.83% | 0 | 117 | 29 | 0.09699% | 80.14% | 60 | -57
|  | curing | % | 100 | 85 | 85% | 0 | 20 | 80 | 0.01078% | 20% | 60 | 40
|  | coating | m2 | 1173 | 821.1 | 70% | 0 | 792 | 381 | 0.03233% | 67.52% | 500 | -292
|  | back fill | m3 | 1406 | 313.8192 | 22.32% | 0 | 980 | 426 | 0.1078% | 69.7% | 0 | -980
|  | Final Certificate | % | 100 | 56 | 56% | 0 | 100 |  | 0.05388% | 100% | 52 | -48
|  | West LP |  |  |  | 96.5% | 0 |  |  | 0.1705% | 53.39% |  | 0
|  | excavation | m3 | 397 | 397 | 100% | 0 | 206 | 191 | 0.01364% | 51.89% | 145 | -61
|  | level&compact | m2 | 218 | 218 | 100% | 0 | 112 | 106 | 0.003411% | 51.38% | 99 | -13
|  | lean | m3 | 7 | 7 | 100% | 0 | 3.7 | 3.3 | 0.001705% | 52.86% | 5 | 1.3
|  | footing rebar | Kg | 7260 | 7260 | 100% | 0 | 3344.9 | 3915.1 | 0.02387% | 46.07% | 6702 | 3357.1
|  | footing form | m2 | 100 | 100 | 100% | 0 | 49 | 51 | 0.01791% | 49% | 71 | 22
|  | foting concrete | m3 | 65 | 65 | 100% | 0 | 34.75 | 30.25 | 0.03581% | 53.46% | 18 | -16.75
|  | ped rebar | Kg | 4840 | 4840 | 100% | 0 | 3162.1 | 1677.9 | 0.01023% | 65.33% | 2300 | -862.1
|  | ped form | m2 | 107 | 107 | 100% | 0 | 56 | 51 | 0.007674% | 52.34% | 41 | -15
|  | anchor | NO. | 120 | 120 | 100% | 0 | 56 | 64 | 0.008526% | 46.67% | 29 | -27
|  | ped concrete | m3 | 35 | 31.5 | 90% | 0 | 25.5 | 9.5 | 0.01535% | 72.86% | 21 | -4.5
|  | curing | % | 100 | 65 | 65% | 0 | 20 | 80 | 0.001705% | 20% | 40 | 20
|  | coating | m2 | 384 | 249.6 | 65% | 0 | 230 | 154 | 0.005116% | 59.9% | 0 | -230
|  | back fill | m3 | 296 | 266.4 | 90% | 0 | 145 | 151 | 0.01705% | 48.99% | 0 | -145
|  | Final Certificate | % | 100 | 55 | 55% | 0 | 56 | 53 | 0.008526% | 56% | 39 | -17
|  | East LP |  |  |  | 10.5% | 0 |  |  | 0.2226% | 10.75% |  | 0
|  | excavation | m3 | 397 | 397 | 100% | 0 | 397 | 0 | 0.01781% | 100% | 214 | -183
|  | level&compact | m2 | 218 | 218 | 100% | 0 | 218 |  | 0.004453% | 100% | 138 | -80
|  | lean | m3 | 7 | 0 |  | 0 | 0 |  | 0.002226% | 0% |  | 0
|  | footing rebar | Kg | 7260 | 0 |  | 0 | 0 |  | 0.03117% | 0% |  | 0
|  | footing form | m2 | 102 | 0 |  | 0 | 0 |  | 0.02338% | 0% |  | 0
|  | foting concrete | m3 | 65 | 0 |  | 0 | 0 |  | 0.04675% | 0% |  | 0
|  | ped rebar | Kg | 4840 | 0 |  | 0 | 0 |  | 0.01336% | 0% |  | 0
|  | ped form | m2 | 107 | 0 |  | 0 | 0 |  | 0.01002% | 0% |  | 0
|  | anchor | NO. | 120 | 0 |  | 0 | 0 |  | 0.01113% | 0% |  | 0
|  | ped concrete | m3 | 35 | 0 |  | 0 | 0 |  | 0.02004% | 0% |  | 0
|  | curing | % | 100 | 0 |  | 0 | 0 |  | 0.002226% | 0% |  | 0
|  | coating | m2 | 384 | 0 |  | 0 | 0 |  | 0.006679% | 0% |  | 0
|  | back fill | m3 | 296 | 0 |  | 0 | 0 |  | 0.02226% | 0% |  | 0
|  | Final Certificate | % | 100 | 10 | 10% | 5 | 15 |  | 0.01113% | 15% | 10 | -5
|  | Retaining wall |  |  |  | 20.19% | 0 |  |  | 2.849% | 13.65% |  | 0
|  | Retaining wall 7 |  |  |  | 4% | 0 |  |  | 1.902% | 4.2% |  | 0
|  | excavation | m3 | 2750 | 1375 | 50% | 375 | 1750 | 1000 | 0.1522% | 50% |  | -1750
|  | level&compact | m2 | 275 | 0 |  | 0 | 0 | 275 | 0.03805% | 0% |  | 0
|  | lean | m3 | 46 | 0 |  | 0 | 0 | 46 | 0.01902% | 0% |  | 0
|  | footing rebar | Kg | 54855 | 0 |  | 0 | 0 | 54855 | 0.2663% | 0% |  | 0
|  | footing form | m2 | 200 | 0 |  | 0 | 0 | 200 | 0.1997% | 0% |  | 0
|  | foting concrete | m3 | 400 | 0 |  | 0 | 0 | 400 | 0.3995% | 0% |  | 0
|  | Wall rebar | Kg | 18285 | 0 |  | 0 | 0 | 18285 | 0.1141% | 0% |  | 0
|  | Wall form | m2 | 760 | 0 |  | 0 | 0 | 760 | 0.08561% | 0% |  | 0
|  | Wall concrete | m3 | 370 | 0 |  | 0 | 0 | 370 | 0.2663% | 0% |  | 0
|  | curing | % | 100 | 0 |  | 0 | 0 | 100 | 0.01902% | 0% |  | 0
|  | coating | m2 | 1206 | 0 |  | 0 | 0 | 1206 | 0.05707% | 0% |  | 0
|  | back fill | m3 | 4000 | 0 |  | 0 | 0 | 4000 | 0.1902% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 4 | 4 | 100 | 0.09512% | 4% |  | -4
|  | Retaining wall 9 |  |  |  | 86% | 0 |  |  | 0.2292% | 88.45% |  | 0
|  | excavation | m3 | 316 | 316 | 100% | 0 | 316 | 0 | 0.01834% | 100% | 316 | 0
|  | level&compact | m2 | 128 | 128 | 100% | 0 | 128 | 0 | 0.004584% | 100% | 128 | 0
|  | lean | m3 | 4 | 4 | 100% | 0 | 4 | 0 | 0.002292% | 100% | 4 | 0
|  | footing rebar | Kg | 10025 | 10025 | 100% | 0 | 10025 | 0 | 0.03209% | 100% | 10025 | 0
|  | footing form | m2 | 45 | 45 | 100% | 0 | 45 | 0 | 0.02407% | 100% | 45 | 0
|  | foting concrete | m3 | 58 | 58 | 100% | 0 | 58 | 0 | 0.04813% | 100% |  | -58
|  | Wall rebar | Kg | 10100 | 10100 | 100% | 0 | 10100 | 0 | 0.01375% | 100% |  | -10100
|  | Wall form | m2 | 195 | 195 | 100% | 0 | 195 | 0 | 0.01031% | 100% |  | -195
|  | Wall concrete | m3 | 56 | 56 | 100% | 0 | 56 | 0 | 0.03209% | 100% |  | -56
|  | curing | % | 100 | 65 | 65% | 35 | 100 | 0 | 0.002292% | 65% |  | -100
|  | coating | m2 | 145 | 87 | 60% | 58 | 145 | 0 | 0.006876% | 60% |  | -145
|  | back fill | m3 | 166 | 0 | 0% | 166 | 166 | 0 | 0.02292% | 0% |  | -166
|  | Final Certificate | % | 100 | 51 | 51% | 49 | 100 | 0 | 0.01146% | 100% | 20 | -80
|  | Retaining wall 11 |  |  |  | 0% | 0 |  |  | 0.2292% | 6.535% |  | 0
|  | excavation | m3 | 850 | 0 | 0% | 650 | 650 | 200 | 0.01834% | 76.47% |  | -650
|  | level&compact | m2 | 55 | 0 | 0% | 0 | 0 | 55 | 0.004584% | 0% |  | 0
|  | lean | m3 | 3.4 | 0 | 0% | 0.4 | 0.4 | 3 | 0.002292% | 11.76% |  | -0.4
|  | footing rebar | Kg | 8400 | 0 | 0% | 0 | 0 | 8400 | 0.03209% | 0% |  | 0
|  | footing form | m2 | 50 | 0 | 0% | 0 | 0 | 50 | 0.02407% | 0% |  | 0
|  | foting concrete | m3 | 73 | 0 | 0% | 0 | 0 | 73 | 0.04813% | 0% |  | 0
|  | Wall rebar | Kg | 2800 | 0 | 0% | 0 | 0 | 2800 | 0.01375% | 0% |  | 0
|  | Wall form | m2 | 159 | 0 | 0% | 0 | 0 | 159 | 0.01031% | 0% |  | 0
|  | Wall concrete | m3 | 76 | 0 | 0% | 0 | 0 | 76 | 0.03209% | 0% |  | 0
|  | curing | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.002292% | 0% |  | 0
|  | coating | m2 | 251 | 0 | 0% | 0 | 0 | 251 | 0.006876% | 0% |  | 0
|  | back fill | m3 | 1500 | 0 | 0% | 0 | 0 | 1500 | 0.02292% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0% | 6 | 6 | 94 | 0.01146% | 6% |  | -6
|  | Retaining wall 12 |  |  |  | 87.8% | 0 |  |  | 0.3438% | 0% |  | 0
|  | excavation | m3 | 316 | 316 | 100% | 0 | 0 | 316 | 0 | 0% | 316 | 316
|  | level&compact | m2 | 128 | 128 | 100% | 0 | 0 | 128 | 0 | 0% | 128 | 128
|  | lean | m3 | 5 | 5 | 100% | 0 | 0 | 5 | 0 | 0% |  | 0
|  | footing rebar | Kg | 10025 | 10025 | 100% | 0 | 0 | 10025 | 0 | 0% |  | 0
|  | footing form | m2 | 45 | 45 | 100% | 0 | 0 | 45 | 0 | 0% |  | 0
|  | foting concrete | m3 | 50 | 50 | 100% | 0 | 0 | 50 | 0 | 0% |  | 0
|  | Wall rebar | Kg | 10100 | 10100 | 100% | 0 | 0 | 10100 | 0 | 0% |  | 0
|  | Wall form | m2 | 195 | 195 | 100% | 0 | 0 | 195 | 0 | 0% |  | 0
|  | Wall concrete | m3 | 64 | 64 | 100% | 0 | 0 | 64 | 0 | 0% |  | 0
|  | curing | % | 100 | 100 | 100% | 0 | 0 | 100 | 0 | 100% |  | 0
|  | coating | m2 | 145 | 145 | 100% | 0 | 0 | 145 | 0 | 100% |  | 0
|  | back fill | m3 | 166 | 0 | 0% | 166 | 166 | 0 | 0 | 100% |  | -166
|  | Final Certificate | % | 100 | 56 | 56% | 0 | 44 | 56 | 0 | 44% | 8 | -36
|  | Retaining wall 13 |  |  |  | 0% | 0 |  |  | 0.1444% | 63.15% |  | 0
|  | excavation | m3 | 600 | 0 |  | 600 | 600 | 0 | 0.01155% | 100% |  | -600
|  | level&compact | m2 | 58 | 0 |  | 58 | 58 | 0 | 0.002888% | 100% |  | -58
|  | lean | m3 | 2.6 | 0 |  | 2.6 | 2.6 | 0 | 0.001444% | 100% |  | -2.6
|  | footing rebar | Kg | 6826 | 0 |  | 6826 | 6826 | 0 | 0.02022% | 100% |  | -6826
|  | footing form | m2 | 29 | 0 |  | 29 | 29 | 0 | 0.01516% | 100% |  | -29
|  | foting concrete | m3 | 35 | 0 |  | 35 | 35 | 0 | 0.03032% | 100% |  | -35
|  | Wall rebar | Kg | 2275 | 0 |  | 1000 | 1000 | 1275 | 0.008664% | 43.96% |  | -1000
|  | Wall form | m2 | 103 | 0 |  | 53 | 53 | 50 | 0.006498% | 51.46% |  | -53
|  | Wall concrete | m3 | 28 | 0 |  | 0 | 0 | 28 | 0.02022% | 0% |  | 0
|  | curing | % | 100 | 0 |  | 0 | 0 | 100 | 0.001444% | 0% |  | 0
|  | coating | m2 | 150 | 0 |  | 0 | 0 | 150 | 0.004332% | 0% |  | 0
|  | back fill | m3 | 1000 | 0 |  | 0 | 0 | 1000 | 0.01444% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 34 | 34 | 66 | 0.00722% | 34% |  | -34
|  | Base |  |  | 0 | 0% | 0 |  |  | 0.095% | 0% |  | 0
|  | Base | m3 | 560 | 0 | 0% | 0 | 0 |  | 0.095% | 0% |  | 0
|  | Piping | pip |  | 0 | 11.33% | 0 |  |  | 19.52% | 12.84% |  | 0
|  | AG Piping |  |  | 0 | 11.45% | 0 |  |  | 19.32% | 12.72% |  | 0
|  | Shop |  |  | 0 | 4.93% | 0 |  |  | 6.763% | 4.996% |  | 0
|  | Carbon Steel |  |  | 0 | 6.74% | 0 |  |  | 3.489% | 6.743% |  | 0
|  | Material Handling From Lay down To Shop | ID | 42944 | 14708.32 | 34.25% | 10889.68 | 25598 |  | 0.1744% | 34.25% | 3390 | -22208
|  | Cutting & Bevelling & Fit Up | ID | 12883 | 523.0498 | 4.06% | 6409.9502 | 6933 |  | 1.221% | 4.06% |  | -6933
|  | Welding | ID | 12883 | 224.1642 | 1.74% | 5632.8358 | 5857 |  | 1.221% | 1.74% |  | -5857
|  | NDT | ID | 12883 | 0 | 0% | 0 | 0 |  | 0.1744% | 0% |  | 0
|  | PWHT | ID | 12883 | 0 | 0% | 0 | 0 |  | 0.1744% | 0% |  | 0
|  | Final Certificate | % | 100 | 20 | 20% | 0 | 20 |  | 0.5233% | 20% | 20 | 0
|  | Low Temperature CS |  |  | 0 | 3% | 0 |  |  | 1.993% | 3.224% |  | 0
|  | Material Handling From Lay down To Shop | ID | 27889 | 0 |  | 1248 | 1248 |  | 0.09967% | 4.475% |  | -1248
|  | Cutting & Bevelling & Fit Up | ID | 8367 | 0 |  | 0 | 0 |  | 0.6977% | 0% |  | 0
|  | Welding | ID | 8367 | 0 |  | 0 | 0 |  | 0.6977% | 0% |  | 0
|  | NDT | ID | 8367 | 0 |  | 0 | 0 |  | 0.09967% | 0% |  | 0
|  | PWHT | ID | 1 | 0 |  | 0 | 0 |  | 0.09967% | 0% |  | 0
|  | Final Certificate | % | 100 | 20 | 20% | 0 | 20 |  | 0.299% | 20% | 20 | 0
|  | Stainless Steel |  |  | 0 | 3% | 0 |  |  | 1.167% | 3% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 |  | 0 | 0 |  | 0.05833% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 |  | 0 | 0 |  | 0.4083% | 0% |  | 0
|  | Welding | ID | 1 | 0 |  | 0 | 0 |  | 0.4083% | 0% |  | 0
|  | NDT | ID | 1 | 0 |  | 0 | 0 |  | 0.05833% | 0% |  | 0
|  | PWHT | ID | 1 | 0 |  | 0 | 0 |  | 0.05833% | 0% |  | 0
|  | Final Certificate | % | 100 | 20 | 20% | 0 | 20 |  | 0.175% | 20% | 20 | 0
|  | Galva |  |  | 0 | 3% | 0 |  |  | 0.115% | 3% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 |  | 0 | 0 |  | 0.00575% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 |  | 0 | 0 |  | 0.04025% | 0% |  | 0
|  | Welding | ID | 1 | 0 |  | 0 | 0 |  | 0.04025% | 0% |  | 0
|  | NDT | ID | 1 | 0 |  | 0 | 0 |  | 0.00575% | 0% |  | 0
|  | PWHT | ID | 1 | 0 |  | 0 | 0 |  | 0.00575% | 0% |  | 0
|  | Final Certificate | % | 100 | 20 | 20% | 0 | 20 |  | 0.01725% | 20% | 20 | 0
|  | Field |  |  | 0 | 14.96% | 0 |  |  | 12.56% | 16.88% |  | 0
|  | Carbon Steel |  |  | 0 | 17.25% | 0 |  |  | 6.478% | 17.25% |  | 0
|  | Material Handling From Shop To Field | ID | 42944 | 3409.7536 | 7.94% | 2597.2464 | 6007 |  | 0.3239% | 7.94% | 452 | -5555
|  | Scaffolding | m2 | 8000 | 6646.4 | 83.08% | 702.6 | 7349 |  | 0.8422% | 83.08% | 2350 | -4999
|  | Erection & Fit Up | ID | 30060 | 1605.204 | 5.34% | 2013.796 | 3619 |  | 1.231% | 5.34% | 452 | -3167
|  | Valve Installation | ID | 280 | 0 | 0% | 0 | 0 |  | 0.3239% | 0% |  | 0
|  | Welding | ID | 30060 | 949.896 | 3.16% | 2481.104 | 3431 |  | 2.138% | 3.16% | 408 | -3023
|  | NDT | ID | 30060 | 0 |  | 0 | 0 |  | 0.162% | 0% |  | 0
|  | PWHT | ID | 30060 | 0 |  | 0 | 0 |  | 0.1944% | 0% |  | 0
|  | Hydro test | ID | 30060 | 0 |  | 0 | 0 |  | 0.6155% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.6478% | 40% | 40 | 0
|  | Low Temperature CS |  |  | 0 | 12.52% | 0 |  |  | 3.702% | 16.81% |  | 0
|  | Material Handling From Shop To Field | ID | 27889 | 0 | 0% | 496 | 496 |  | 0.1851% | 1.778% |  | -496
|  | Scaffolding | m2 | 8000 | 5244.8 | 65.56% | 2104.2 | 7349 |  | 0.4813% | 91.86% | 2350 | -4999
|  | Erection & Fit Up | ID | 19522 | 0 | 0% | 384 | 384 |  | 0.7034% | 1.967% |  | -384
|  | Valve Installation | ID | 280 | 0 |  | 0 | 0 |  | 0.1851% | 0% |  | 0
|  | Welding | ID | 19522 | 0 |  | 240 | 240 |  | 1.222% | 1.229% |  | -240
|  | NDT | ID | 19522 | 0 |  | 0 | 0 |  | 0.09255% | 0% |  | 0
|  | PWHT | ID | 19522 | 0 |  | 0 | 0 |  | 0.1111% | 0% |  | 0
|  | Hydro test | ID | 19522 | 0 |  | 0 | 0 |  | 0.3517% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.3702% | 40% | 40 | 0
|  | Stainless Steel |  |  | 0 | 12.52% | 0 |  |  | 2.166% | 15.94% |  | 0
|  | Material Handling From Shop To Field | ID | 13845 | 0 | 0% | 0 | 0 |  | 0.1083% | 0% |  | 0
|  | Scaffolding | m2 | 8000 | 5200 | 65% | 2149 | 7349 |  | 0.2816% | 91.86% | 2350 | -4999
|  | Erection & Fit Up | ID | 9692 | 0 |  | 0 | 0 |  | 0.4116% | 0% |  | 0
|  | Valve Installation | ID | 280 | 0 |  | 0 | 0 |  | 0.1083% | 0% |  | 0
|  | Welding | ID | 9692 | 0 |  | 0 | 0 |  | 0.7149% | 0% |  | 0
|  | NDT | ID | 9692 | 0 |  | 0 | 0 |  | 0.05416% | 0% |  | 0
|  | PWHT | ID | 9692 | 0 |  | 0 | 0 |  | 0.06499% | 0% |  | 0
|  | Hydro test | ID | 9692 | 0 |  | 0 | 0 |  | 0.2058% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.2166% | 40% | 40 | 0
|  | Galva |  |  | 0 | 12.52% | 0 |  |  | 0.2136% | 15.94% |  | 0
|  | Material Handling From Shop To Field | ID | 2645 | 0 | 0% | 0 | 0 |  | 0.01068% | 0% |  | 0
|  | Scaffolding | m2 | 8000 | 5244.8 | 65.56% | 2104.2 | 7349 |  | 0.02776% | 91.86% | 2350 | -4999
|  | Erection & Fit Up | ID | 1852 | 0 |  | 0 | 0 |  | 0.04058% | 0% |  | 0
|  | Valve Installation | ID | 280 | 0 |  | 0 | 0 |  | 0.01068% | 0% |  | 0
|  | Welding | ID | 1852 | 0 |  | 0 | 0 |  | 0.07048% | 0% |  | 0
|  | NDT | ID | 1852 | 0 |  | 0 | 0 |  | 0.005339% | 0% |  | 0
|  | PWHT | ID | 1852 | 0 |  | 0 | 0 |  | 0.006407% | 0% |  | 0
|  | Hydro test | ID | 1852 | 0 |  | 0 | 0 |  | 0.02029% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.02136% | 40% | 40 | 0
|  | Pipe Support |  |  | 0 | 0% | 0 |  |  | 0.1995% | 24.55% |  | 0
|  | Shop |  |  | 0 | 0% | 0 |  |  | 0.06982% | 66.13% |  | 0
|  | Handling | Kg | 43200 | 0 |  | 43200 | 43200 |  | 0.007681% | 100% |  | -43200
|  | shop drawing | Kg | 43200 | 0 |  | 100 | 100 |  | 0.01117% | 0.2315% |  | -100
|  | Cutting & assembling | Kg | 43200 | 0 |  | 35000 | 35000 |  | 0.01536% | 81.02% |  | -35000
|  | Welding | Kg | 43200 | 0 |  | 35000 | 35000 |  | 0.03212% | 81.02% |  | -35000
|  | Final Certificate | % | 100 | 0 |  | 0 | 0 |  | 0.003491% | 0% |  | 0
|  | Field |  |  | 0 | 0% | 0 |  |  | 0.1297% | 2.164% |  | 0
|  | Material Handling From Shop To Field | Kg | 43200 | 0 |  | 8500 | 8500 |  | 0.01426% | 19.68% |  | -8500
|  | Erection | Kg | 43200 | 0 |  | 0 | 0 |  | 0.02723% | 0% |  | 0
|  | Welding | Kg | 43200 | 0 |  | 0 | 0 |  | 0.06743% | 0% |  | 0
|  | NDT | Kg | 43200 | 0 |  | 0 | 0 |  | 0.01426% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 0 | 0 |  | 0.006484% | 0% |  | 0
|  | Painting & Sandblasting | pan |  | 0 | 3.24% | 0 |  |  | 2.557% | 3.266% |  | 0
|  | Pipe |  |  | 0 | 3.3% | 0 |  |  | 2.531% | 3.3% |  | 0
|  | Sand Blast | m2 | 39250 | 8635 | 22% | 5916 | 14551 |  | 0.3797% | 22% | 1886 | -12665
|  | Primer | m2 | 39250 | 0 |  | 14551 | 14551 |  | 0.5062% | 0% | 1886 | -12665
|  | Middle Paint | m2 | 39250 | 0 |  | 0 | 0 |  | 0.8859% | 0% |  | 0
|  | Final Paint | m2 | 39250 | 0 |  | 0 | 0 |  | 0.5062% | 0% |  | 0
|  | Touch Up & Punch | m2 | 39250 | 0 |  | 0 | 0 |  | 0.1266% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 0 | 0 |  | 0.1266% | 0% |  | 0
|  | Support |  |  | 0 | 0% | 0 |  |  | 0.02613% | 0% |  | 0
|  | Sand Blast | m2 | 1 | 0 |  | 0 | 0 |  | 0.00392% | 0% |  | 0
|  | Primer | m2 | 1 | 0 |  | 0 | 0 |  | 0.005226% | 0% |  | 0
|  | Middle Paint | m2 | 1 | 0 |  | 0 | 0 |  | 0.009146% | 0% |  | 0
|  | Final Paint | m2 | 1 | 0 |  | 0 | 0 |  | 0.005226% | 0% |  | 0
|  | Touch Up & Punch | m2 | 1 | 0 |  | 0 | 0 |  | 0.001307% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 0 | 0 |  | 0.001307% | 0% |  | 0
|  | Steel Structure | str |  | 0 | 80.2% | 0 |  |  | 7.466% | 84.12% |  | 0
|  | Installation Steel Structure |  |  | 0 | 80.93% | 0 |  |  | 7.399% | 84.88% |  | 0
|  | 140-IM-A1 |  |  | 0 | 95.05% | 0 |  |  | 0.2474% | 99.25% |  | 0
|  | Handling | Kg | 94004 | 94004 | 100% | 0 | 94004 |  | 0.02474% | 100% | 94004 | 0
|  | Chip&Padding | NO | 14 | 14 | 100% | 0 | 14 |  | 0.01237% | 100% | 14 | 0
|  | Erection | Kg | 94004 | 94004 | 100% | 0 | 94004 |  | 0.09894% | 100% | 94004 | 0
|  | Alignment | Kg | 94004 | 94004 | 100% | 0 | 94004 |  | 0.02968% | 100% | 94004 | 0
|  | Bolt Tightening & Test | Kg | 94004 | 94004 | 100% | 0 | 94004 |  | 0.01979% | 100% | 94004 | 0
|  | Grouting | NO | 14 | 14 | 100% | 0 | 14 |  | 0.02474% | 100% | 14 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.0371% | 95% | 62 | -33
|  | 140-IM-A2 |  |  | 0 | 95.05% | 0 |  |  | 0.3595% | 99.25% |  | 0
|  | Handling | Kg | 136607 | 136607 | 100% | 0 | 136607 |  | 0.03595% | 100% | 136607 | 0
|  | Chip&Padding | NO | 16 | 16 | 100% | 0 | 16 |  | 0.01797% | 100% | 16 | 0
|  | Erection | Kg | 136607 | 136607 | 100% | 0 | 136607 |  | 0.1438% | 100% | 136607 | 0
|  | Alignment | Kg | 136607 | 136607 | 100% | 0 | 136607 |  | 0.04313% | 100% | 136607 | 0
|  | Bolt Tightening & Test | Kg | 136607 | 136607 | 100% | 0 | 136607 |  | 0.02876% | 100% | 136607 | 0
|  | Grouting | NO | 16 | 16 | 100% | 0 | 16 |  | 0.03595% | 100% | 16 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.05392% | 95% | 63 | -32
|  | 140-IM-A3 |  |  | 0 | 95.05% | 0 |  |  | 0.2126% | 99.25% |  | 0
|  | Handling | Kg | 80800 | 80800 | 100% | 0 | 80800 |  | 0.02126% | 100% | 80800 | 0
|  | Chip&Padding | NO | 16 | 16 | 100% | 0 | 16 |  | 0.01063% | 100% | 16 | 0
|  | Erection | Kg | 80800 | 80800 | 100% | 0 | 80800 |  | 0.08504% | 100% | 80800 | 0
|  | Alignment | Kg | 80800 | 80800 | 100% | 0 | 80800 |  | 0.02551% | 100% | 80800 | 0
|  | Bolt Tightening & Test | Kg | 80800 | 80800 | 100% | 0 | 80800 |  | 0.01701% | 100% | 80800 | 0
|  | Grouting | NO | 16 | 16 | 100% | 0 | 16 |  | 0.02126% | 100% | 16 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.03189% | 95% | 63 | -32
|  | 140-IM-A4 |  |  | 0 | 95.05% | 0 |  |  | 0.1649% | 99.25% |  | 0
|  | Handling | Kg | 62652 | 62652 | 100% | 0 | 62652 |  | 0.01649% | 100% | 62652 | 0
|  | Chip&Padding | NO | 14 | 14 | 100% | 0 | 14 |  | 0.008243% | 100% | 14 | 0
|  | Erection | Kg | 62652 | 62652 | 100% | 0 | 62652 |  | 0.06594% | 100% | 62652 | 0
|  | Alignment | Kg | 62652 | 62652 | 100% | 0 | 62652 |  | 0.01978% | 100% | 62652 | 0
|  | Bolt Tightening & Test | Kg | 62652 | 62652 | 100% | 0 | 62652 |  | 0.01319% | 100% | 62652 | 0
|  | Grouting | NO | 14 | 14 | 100% | 0 | 14 |  | 0.01649% | 100% | 14 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.02473% | 95% | 62 | -33
|  | 140-IM-A5 |  |  | 0 | 95.05% | 0 |  |  | 0.4729% | 99.25% |  | 0
|  | Handling | Kg | 179726 | 179726 | 100% | 0 | 179726 |  | 0.04729% | 100% | 179726 | 0
|  | Chip&Padding | NO | 32 | 32 | 100% | 0 | 32 |  | 0.02365% | 100% | 32 | 0
|  | Erection | Kg | 179726 | 179726 | 100% | 0 | 179726 |  | 0.1892% | 100% | 179726 | 0
|  | Alignment | Kg | 179726 | 179726 | 100% | 0 | 179726 |  | 0.05675% | 100% | 179726 | 0
|  | Bolt Tightening & Test | Kg | 179726 | 179726 | 100% | 0 | 179726 |  | 0.03783% | 100% | 179726 | 0
|  | Grouting | NO | 32 | 32 | 100% | 0 | 32 |  | 0.04729% | 100% | 32 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.07094% | 95% | 64 | -31
|  | 140-IM-A6 |  |  | 0 | 94.86% | 0 |  |  | 0.3567% | 98.91% |  | 0
|  | Handling | Kg | 135576 | 135196.3872 | 99.72% | 3.6128 | 135200 |  | 0.03567% | 99.72% | 135200 | 0
|  | Chip&Padding | NO | 33 | 33 | 100% | 0 | 33 |  | 0.01784% | 100% | 33 | 0
|  | Erection | Kg | 135576 | 135196.3872 | 99.72% | 3.6128 | 135200 |  | 0.1427% | 99.72% | 135199 | -1
|  | Alignment | Kg | 135576 | 135196.3872 | 99.72% | 3.6128 | 135200 |  | 0.04281% | 99.72% | 135199 | -1
|  | Bolt Tightening & Test | Kg | 135576 | 135196.3872 | 99.72% | 3.6128 | 135200 |  | 0.02854% | 99.72% | 135199 | -1
|  | Grouting | NO | 33 | 33 | 100% | 0 | 33 |  | 0.03567% | 100% | 33 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 27 | 94 |  | 0.05351% | 94% | 64 | -30
|  | 140-IM-A7 |  |  | 0 | 14% | 0 |  |  | 0.1538% | 14.6% |  | 0
|  | Handling | Kg | 58446 | 58446 | 100% | 0 | 58446 |  | 0.01538% | 100% | 58446 | 0
|  | Chip&Padding | NO | 16 | 8 | 50% | 0 | 8 |  | 0.007689% | 50% | 8 | 0
|  | Erection | Kg | 58446 | 0 |  | 0 | 0 |  | 0.06152% | 0% | 0 | 0
|  | Alignment | Kg | 58446 | 0 |  | 0 | 0 |  | 0.01845% | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 58446 | 0 |  | 0 | 0 |  | 0.0123% | 0% | 0 | 0
|  | Grouting | NO | 16 | 0 |  | 0 | 0 |  | 0.01538% | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 10 | 10% | 4 | 14 |  | 0.02307% | 14% | 10 | -4
|  | 140-IM-B1 |  |  | 0 | 9.6% | 0 |  |  | 0.1758% | 10.95% |  | 0
|  | Handling | Kg | 66800 | 64128 | 96% | 3 | 64131 |  | 0.01758% | 96% | 64131 | 0
|  | Chip&Padding | NO | 10 | 0 |  | 0 | 0 |  | 0.008789% | 0% | 0 | 0
|  | Erection | Kg | 66800 | 0 |  | 0 | 0 |  | 0.07031% | 0% | 0 | 0
|  | Alignment | Kg | 66800 | 0 |  | 0 | 0 |  | 0.02109% | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 66800 | 0 |  | 0 | 0 |  | 0.01406% | 0% | 0 | 0
|  | Grouting | NO | 10 | 0 |  | 0 | 0 |  | 0.01758% | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 0 |  | 9 | 9 |  | 0.02637% | 9% | 7 | -2
|  | 140-IM-B2 |  |  | 0 | 9.94% | 0 |  |  | 0.4518% | 11.44% |  | 0
|  | Handling | Kg | 171694 | 170732.5136 | 99.44% | 8.4864 | 170741 |  | 0.04518% | 99.44% | 170741 | 0
|  | Chip&Padding | NO | 12 | 0 | 0% | 0 | 0 |  | 0.02259% | 0% | 0 | 0
|  | Erection | Kg | 171694 | 0 |  | 0 | 0 |  | 0.1807% | 0% | 0 | 0
|  | Alignment | Kg | 171694 | 0 |  | 0 | 0 |  | 0.05421% | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 171694 | 0 |  | 0 | 0 |  | 0.03614% | 0% | 0 | 0
|  | Grouting | NO | 12 | 0 |  | 0 | 0 |  | 0.04518% | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 0 |  | 10 | 10 |  | 0.06777% | 10% | 7 | -3
|  | 140-IM-B3 |  |  | 0 | 93.7% | 0 |  |  | 0.4453% | 98.95% |  | 0
|  | Handling | Kg | 169239 | 169239 | 100% | 0 | 169239 |  | 0.04453% | 100% | 167795 | -1444
|  | Chip&Padding | NO | 28 | 28 | 100% | 0 | 28 |  | 0.02227% | 100% | 28 | 0
|  | Erection | Kg | 169239 | 169239 | 100% | 0 | 169238.6 |  | 0.1781% | 100% | 167795 | -1443.6
|  | Alignment | Kg | 169239 | 169239 | 100% | 0 | 169239 |  | 0.05344% | 100% | 167795 | -1444
|  | Bolt Tightening & Test | Kg | 169239 | 169239 | 100% | 0 | 169239 |  | 0.03563% | 100% | 0 | -169239
|  | Grouting | NO | 28 | 28 | 100% | 0 | 28 |  | 0.04453% | 100% | 0 | -28
|  | Final test & Documents | % | 100 | 58 | 58% | 35 | 93 |  | 0.0668% | 93% | 48 | -45
|  | 140-IM-B4 |  |  | 0 | 94.39% | 0 |  |  | 0.3028% | 99.04% |  | 0
|  | Handling | Kg | 115066 | 115066 | 100% | 0 | 115066 |  | 0.03028% | 100% | 115066 | 0
|  | Chip&Padding | NO | 20 | 20 | 100% | 0 | 20 |  | 0.01514% | 100% | 20 | 0
|  | Erection | Kg | 115066 | 114950.934 | 99.9% | 0 | 114950.6 |  | 0.1211% | 99.9% | 113646 | -1304.6
|  | Alignment | Kg | 115066 | 114950.934 | 99.9% | 0.066 | 114951 |  | 0.03633% | 99.9% | 113646 | -1305
|  | Bolt Tightening & Test | Kg | 115066 | 114950.934 | 99.9% | 0.066 | 114951 |  | 0.02422% | 99.9% | 113646 | -1305
|  | Grouting | NO | 20 | 20 | 100% | 0 | 20 |  | 0.03028% | 100% | 20 | 0
|  | Final test & Documents | % | 100 | 63 | 63% | 31 | 94 |  | 0.04542% | 94% | 62 | -32
|  | 140-IM-B5 |  |  | 0 | 94.12% | 0 |  |  | 0.1895% | 98.77% |  | 0
|  | Handling | Kg | 72807 | 72807 | 100% | 0 | 72807 |  | 0.01895% | 100% | 72293 | -514
|  | Chip&Padding | NO | 10 | 10 | 100% | 0 | 10 |  | 0.009473% | 100% | 10 | 0
|  | Erection | Kg | 72807 | 72406.5615 | 99.45% | 0.4385 | 72407 |  | 0.07579% | 99.45% | 72293 | -114
|  | Alignment | Kg | 72807 | 72406.5615 | 99.45% | 0.4385 | 72407 |  | 0.02274% | 99.45% | 72293 | -114
|  | Bolt Tightening & Test | Kg | 72807 | 72406.5615 | 99.45% | 0.4385 | 72407 |  | 0.01516% | 99.45% | 72293 | -114
|  | Grouting | NO | 10 | 10 | 100% | 0 | 10 |  | 0.01895% | 100% | 10 | 0
|  | Final test & Documents | % | 100 | 63 | 63% | 31 | 94 |  | 0.02842% | 94% | 62 | -32
|  | 140-IM-B6 |  |  | 0 | 94.37% | 0 |  |  | 0.4257% | 99.02% |  | 0
|  | Handling | Kg | 161771 | 161771 | 100% | 0 | 161771 |  | 0.04257% | 100% | 161544 | -227
|  | Chip&Padding | NO | 26 | 26 | 100% | 0 | 26 |  | 0.02128% | 100% | 26 | 0
|  | Erection | Kg | 161771 | 161544.5206 | 99.86% | 0 | 161544.3 |  | 0.1703% | 99.86% | 161544 | -0.3
|  | Alignment | Kg | 161771 | 161544.5206 | 99.86% | 0 | 161544 |  | 0.05108% | 99.86% | 161544 | 0
|  | Bolt Tightening & Test | Kg | 161771 | 161544.5206 | 99.86% | 0 | 161544 |  | 0.03405% | 99.86% | 161544 | 0
|  | Grouting | NO | 26 | 26 | 100% | 0 | 26 |  | 0.04257% | 100% | 26 | 0
|  | Final test & Documents | % | 100 | 63 | 63% | 31 | 94 |  | 0.06385% | 94% | 62 | -32
|  | 140-IM-B7 |  |  | 0 | 94.38% | 0 |  |  | 0.2262% | 99.03% |  | 0
|  | Handling | Kg | 85977 | 85977 | 100% | 0 | 85977 |  | 0.02262% | 100% | 85857 | -120
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 |  | 0.01131% | 100% | 12 | 0
|  | Erection | Kg | 85977 | 85873.8276 | 99.88% | 2.8724 | 85876.7 |  | 0.09049% | 99.88% | 83375 | -2501.7
|  | Alignment | Kg | 85977 | 85873.8276 | 99.88% | 3.1724 | 85877 |  | 0.02715% | 99.88% | 83375 | -2502
|  | Bolt Tightening & Test | Kg | 85977 | 85873.8276 | 99.88% | 3.1724 | 85877 |  | 0.0181% | 99.88% | 83375 | -2502
|  | Grouting | NO | 12 | 12 | 100% | 0 | 12 |  | 0.02262% | 100% | 12 | 0
|  | Final test & Documents | % | 100 | 63 | 63% | 31 | 94 |  | 0.03393% | 94% | 61 | -33
|  | 140-IM-B8 |  |  | 0 | 94.57% | 0 |  |  | 0.2579% | 98.92% |  | 0
|  | Handling | Kg | 98013 | 98013 | 100% | 0 | 98013 |  | 0.02579% | 100% | 97681 | -332
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 |  | 0.0129% | 100% | 12 | 0
|  | Erection | Kg | 98013 | 97709.1597 | 99.69% | 4.8403 | 97714 |  | 0.1032% | 99.69% | 97320 | -394
|  | Alignment | Kg | 98013 | 97709.1597 | 99.69% | 4.8403 | 97714 |  | 0.03095% | 99.69% | 97320 | -394
|  | Bolt Tightening & Test | Kg | 98013 | 97709.1597 | 99.69% | 4.8403 | 97714 |  | 0.02063% | 99.69% | 97320 | -394
|  | Grouting | NO | 12 | 12 | 100% | 0 | 12 |  | 0.02579% | 100% | 12 | 0
|  | Final test & Documents | % | 100 | 65 | 65% | 29 | 94 |  | 0.03869% | 94% | 62 | -32
|  | 140-IM-B9 |  |  | 0 | 94.45% | 0 |  |  | 0.1566% | 99.1% |  | 0
|  | Handling | Kg | 59500 | 59500 | 100% | 0 | 59500 |  | 0.01566% | 100% | 59500 | 0
|  | Chip&Padding | NO | 8 | 8 | 100% | 0 | 8 |  | 0.007828% | 100% | 8 | 0
|  | Erection | Kg | 59500 | 59500 | 100% | 0 | 59500 |  | 0.06262% | 100% | 59500 | 0
|  | Alignment | Kg | 59500 | 59500 | 100% | 0 | 59500 |  | 0.01879% | 100% | 59500 | 0
|  | Bolt Tightening & Test | Kg | 59500 | 59500 | 100% | 0 | 59500 |  | 0.01252% | 100% | 59500 | 0
|  | Grouting | NO | 8 | 8 | 100% | 0 | 8 |  | 0.01566% | 100% | 8 | 0
|  | Final test & Documents | % | 100 | 63 | 63% | 31 | 94 |  | 0.02348% | 94% | 62 | -32
|  | 140-IM-B10 |  |  | 0 | 73.89% | 0 |  |  | 0.2676% | 77.94% |  | 0
|  | Handling | Kg | 101700 | 101700 | 100% | 0 | 101700 |  | 0.02676% | 100% | 101700 | 0
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 |  | 0.01338% | 100% | 12 | 0
|  | Erection | Kg | 101700 | 80404.02 | 79.06% | 0 | 80400 |  | 0.107% | 79.06% | 80400 | 0
|  | Alignment | Kg | 101700 | 80404.02 | 79.06% | 0 | 80400 |  | 0.03211% | 79.06% | 80400 | 0
|  | Bolt Tightening & Test | Kg | 101700 | 64193.04 | 63.12% | 0 | 64193 |  | 0.02141% | 63.12% | 0 | -64193
|  | Grouting | NO | 12 | 6.9996 | 58.33% | 0.0004 | 7 |  | 0.02676% | 58.33% | 0 | -7
|  | Final test & Documents | % | 100 | 46 | 46% | 27 | 73 |  | 0.04014% | 73% | 42 | -31
|  | 140-IM-B11 |  |  | 0 | 94.45% | 0 |  |  | 0.3757% | 99.1% |  | 0
|  | Handling | Kg | 142783 | 142783 | 100% | 0 | 142783 |  | 0.03757% | 100% | 142783 | 0
|  | Chip&Padding | NO | 24 | 24 | 100% | 0 | 24 |  | 0.01879% | 100% | 24 | 0
|  | Erection | Kg | 142783 | 142783 | 100% | 0 | 142783 |  | 0.1503% | 100% | 142783 | 0
|  | Alignment | Kg | 142783 | 142783 | 100% | 0 | 142783 |  | 0.04508% | 100% | 142783 | 0
|  | Bolt Tightening & Test | Kg | 142783 | 142783 | 100% | 0 | 142783 |  | 0.03006% | 100% | 142783 | 0
|  | Grouting | NO | 24 | 24 | 100% | 0 | 24 |  | 0.03757% | 100% | 24 | 0
|  | Final test & Documents | % | 100 | 63 | 63% | 31 | 94 |  | 0.05636% | 94% | 57 | -37
|  | 140-IM-B12 |  |  | 0 | 61.15% | 0 |  |  | 0.2155% | 64.15% |  | 0
|  | Handling | Kg | 81227 | 81227 | 100% | 0 | 81227 |  | 0.02155% | 100% | 81169 | -58
|  | Chip&Padding | NO | 6 | 6 | 100% | 0 | 6 |  | 0.01078% | 100% | 6 | 0
|  | Erection | Kg | 81227 | 81227 | 100% | 0 | 81227 |  | 0.0862% | 100% | 81000 | -227
|  | Alignment | Kg | 81227 | 0 | 0% | 0 | 0 |  | 0.02586% | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 81227 | 0 | 0% | 0 | 0 |  | 0.01724% | 0% | 0 | 0
|  | Grouting | NO | 6 | 0 | 0% | 0 | 0 |  | 0.02155% | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 41 | 41% | 20 | 61 |  | 0.03233% | 61% | 41 | -20
|  | 140-IM-B13 |  |  | 0 | 46.01% | 0 |  |  | 0.3027% | 48.26% |  | 0
|  | Handling | Kg | 115037 | 115037 | 100% | 0 | 115037 |  | 0.03027% | 100% | 114739 | -298
|  | Chip&Padding | NO | 14 | 14 | 100% | 0 | 14 |  | 0.01513% | 100% | 14 | 0
|  | Erection | Kg | 115037 | 74774.05 | 65% | 1033.95 | 75808 |  | 0.1211% | 65.9% | 75656 | -152
|  | Alignment | Kg | 115037 | 0 | 0% | 0 | 0 |  | 0.03632% | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 115037 | 0 | 0% | 0 | 0 |  | 0.02422% | 0% | 0 | 0
|  | Grouting | NO | 14 | 0 | 0% | 0 | 0 |  | 0.03027% | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 31 | 31% | 15 | 46 |  | 0.0454% | 46% | 31 | -15
|  | 140-IM-C1 |  |  | 0 | 93.4% | 0 |  |  | 0.08789% | 98.95% |  | 0
|  | Handling | Kg | 33400 | 33400 | 100% | 0 | 33400 |  | 0.008789% | 100% | 33400 | 0
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 |  | 0.004394% | 100% | 12 | 0
|  | Erection | Kg | 33400 | 33400 | 100% | 0 | 33399.6 |  | 0.03515% | 100% | 33400 | 0.4
|  | Alignment | Kg | 33400 | 33400 | 100% | 0 | 33400 |  | 0.01055% | 100% | 0 | -33400
|  | Bolt Tightening & Test | Kg | 33400 | 33400 | 100% | 0 | 33400 |  | 0.007031% | 100% | 0 | -33400
|  | Grouting | NO | 12 | 12 | 100% | 0 | 12 |  | 0.008789% | 100% | 0 | -12
|  | Final test & Documents | % | 100 | 56 | 56% | 37 | 93 |  | 0.01318% | 93% | 41 | -52
|  | 140-IM-C2 |  |  | 0 | 94.45% | 0 |  |  | 0.1658% | 99.1% |  | 0
|  | Handling | Kg | 63000 | 63000 | 100% | 0 | 63000 |  | 0.01658% | 100% | 63000 | 0
|  | Chip&Padding | NO | 22 | 22 | 100% | 0 | 22 |  | 0.008289% | 100% | 22 | 0
|  | Erection | Kg | 63000 | 63000 | 100% | 0 | 63000 |  | 0.06631% | 100% | 61847 | -1153
|  | Alignment | Kg | 63000 | 63000 | 100% | 0 | 63000 |  | 0.01989% | 100% | 0 | -63000
|  | Bolt Tightening & Test | Kg | 63000 | 63000 | 100% | 0 | 63000 |  | 0.01326% | 100% | 0 | -63000
|  | Grouting | NO | 22 | 22 | 100% | 0 | 22 |  | 0.01658% | 100% | 0 | -22
|  | Final test & Documents | % | 100 | 63 | 63% | 31 | 94 |  | 0.02487% | 94% | 41 | -53
|  | 140-IM-C3 |  |  | 0 | 94.45% | 0 |  |  | 0.08368% | 99.1% |  | 0
|  | Handling | Kg | 31800 | 31800 | 100% | 0 | 31800 |  | 0.008368% | 100% | 31800 | 0
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 |  | 0.004184% | 100% | 12 | 0
|  | Erection | Kg | 31800 | 31800 | 100% | 0 | 31800 |  | 0.03347% | 100% | 31800 | 0
|  | Alignment | Kg | 31800 | 31800 | 100% | 0 | 31800 |  | 0.01004% | 100% | 0 | -31800
|  | Bolt Tightening & Test | Kg | 31800 | 31800 | 100% | 0 | 31800 |  | 0.006694% | 100% | 0 | -31800
|  | Grouting | NO | 12 | 12 | 100% | 0 | 12 |  | 0.008368% | 100% | 0 | -12
|  | Final test & Documents | % | 100 | 63 | 63% | 31 | 94 |  | 0.01255% | 94% | 41 | -53
|  | 140-IM-D1 |  |  | 0 | 95.05% | 0 |  |  | 0.1514% | 99.25% |  | 0
|  | Handling | Kg | 57553 | 57553 | 100% | 0 | 57553 |  | 0.01514% | 100% | 57553 | 0
|  | Chip&Padding | NO | 18 | 18 | 100% | 0 | 18 |  | 0.007572% | 100% | 18 | 0
|  | Erection | Kg | 57553 | 57553 | 100% | 0 | 57553 |  | 0.06058% | 100% | 57553 | 0
|  | Alignment | Kg | 57553 | 57553 | 100% | 0 | 57553 |  | 0.01817% | 100% | 57553 | 0
|  | Bolt Tightening & Test | Kg | 57553 | 57553 | 100% | 0 | 57553 |  | 0.01212% | 100% | 57533 | -20
|  | Grouting | NO | 18 | 18 | 100% | 0 | 18 |  | 0.01514% | 100% | 18 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.02272% | 95% | 61 | -34
|  | 140-IM-D2 |  |  | 0 | 95.05% | 0 |  |  | 0.1342% | 99.25% |  | 0
|  | Handling | Kg | 51015 | 51015 | 100% | 0 | 51015 |  | 0.01342% | 100% | 50938 | -77
|  | Chip&Padding | NO | 16 | 16 | 100% | 0 | 16 |  | 0.006712% | 100% | 16 | 0
|  | Erection | Kg | 51015 | 51015 | 100% | 0 | 51015 |  | 0.05369% | 100% | 50588 | -427
|  | Alignment | Kg | 51015 | 51015 | 100% | 0 | 51015 |  | 0.01611% | 100% | 50588 | -427
|  | Bolt Tightening & Test | Kg | 51015 | 51015 | 100% | 0 | 51015 |  | 0.01074% | 100% | 50588 | -427
|  | Grouting | NO | 16 | 16 | 100% | 0 | 16 |  | 0.01342% | 100% | 16 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.02014% | 95% | 62 | -33
|  | 140-IM-D3 |  |  | 0 | 95.05% | 0 |  |  | 0.178% | 99.25% |  | 0
|  | Handling | Kg | 67658 | 67658 | 100% | 0 | 67658 |  | 0.0178% | 100% | 67658 | 0
|  | Chip&Padding | NO | 26 | 26 | 100% | 0 | 26 |  | 0.008901% | 100% | 26 | 0
|  | Erection | Kg | 67658 | 67658 | 100% | 0 | 67658 |  | 0.07121% | 100% | 67658 | 0
|  | Alignment | Kg | 67658 | 67658 | 100% | 0 | 67658 |  | 0.02136% | 100% | 67658 | 0
|  | Bolt Tightening & Test | Kg | 67658 | 67658 | 100% | 0 | 67658 |  | 0.01424% | 100% | 67658 | 0
|  | Grouting | NO | 26 | 26 | 100% | 0 | 26 |  | 0.0178% | 100% | 26 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.0267% | 95% | 61 | -34
|  | 140-IM-D4 |  |  | 0 | 93.04% | 0 |  |  | 0.1544% | 98.95% |  | 0
|  | Handling | Kg | 58695 | 58695 | 100% | 0 | 58695 |  | 0.01544% | 100% | 58695 | 0
|  | Chip&Padding | NO | 18 | 18 | 100% | 0 | 18 |  | 0.007722% | 100% | 18 | 0
|  | Erection | Kg | 58695 | 0 | 0% | 58695 | 58695 |  | 0.06178% | 100% | 58695 | 0
|  | Alignment | Kg | 58695 | 58695 | 100% | 0 | 58695 |  | 0.01853% | 100% | 0 | -58695
|  | Bolt Tightening & Test | Kg | 58695 | 58695 | 100% | 0 | 58695 |  | 0.01236% | 100% | 0 | -58695
|  | Grouting | NO | 18 | 18 | 100% | 0 | 18 |  | 0.01544% | 100% | 0 | -18
|  | Final test & Documents | % | 100 | 56 | 56% | 37 | 93 |  | 0.02317% | 93% | 41 | -52
|  | 140-IM-E1 |  |  | 0 | 72.12% | 0 |  |  | 0.1329% | 75.72% |  | 0
|  | Handling | Kg | 50500 | 50500 | 100% | 0 | 50500 |  | 0.01329% | 100% | 50500 | 0
|  | Chip&Padding | NO | 20 | 20 | 100% | 0 | 20 |  | 0.006644% | 100% | 20 | 0
|  | Erection | Kg | 50500 | 40450.5 | 80.1% | 0.5 | 40451 |  | 0.05315% | 80.1% | 35264 | -5187
|  | Alignment | Kg | 50500 | 30002.05 | 59.41% | 0 | 30000 |  | 0.01595% | 59.41% | 0 | -30000
|  | Bolt Tightening & Test | Kg | 50500 | 30002.05 | 59.41% | 0 | 30000 |  | 0.01063% | 59.41% | 0 | -30000
|  | Grouting | NO | 20 | 12 | 60% | 0 | 12 |  | 0.01329% | 60% | 0 | -12
|  | Final test & Documents | % | 100 | 48 | 48% | 24 | 72 |  | 0.01993% | 72% | 40 | -32
|  | 140-IM-E2 |  |  | 0 | 95.05% | 0 |  |  | 0.1702% | 99.25% |  | 0
|  | Handling | Kg | 64679 | 64679 | 100% | 0 | 64679 |  | 0.01702% | 100% | 64431 | -248
|  | Chip&Padding | NO | 26 | 26 | 100% | 0 | 26 |  | 0.008509% | 100% | 26 | 0
|  | Erection | Kg | 64679 | 64679 | 100% | 0 | 64679 |  | 0.06808% | 100% | 63845 | -834
|  | Alignment | Kg | 64679 | 64679 | 100% | 0 | 64679 |  | 0.02042% | 100% | 63845 | -834
|  | Bolt Tightening & Test | Kg | 64679 | 64679 | 100% | 0 | 64679 |  | 0.01362% | 100% | 63845 | -834
|  | Grouting | NO | 26 | 26 | 100% | 0 | 26 |  | 0.01702% | 100% | 26 | 0
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.02553% | 95% | 62 | -33
|  | 140-IM-E3 |  |  | 0 | 79.18% | 0 |  |  | 0.1053% | 83.23% |  | 0
|  | Handling | Kg | 40000 | 40000 | 100% | 0 | 40000 |  | 0.01053% | 100% | 38834 | -1166 | 75.87% | 50.83%
|  | Chip&Padding | NO | 16 | 16 | 100% | 0 | 16 |  | 0.005263% | 100% | 16 | 0 | 82.85% | 55.51%
|  | Erection | Kg | 40000 | 39524 | 98.81% | 1 | 39525 |  | 0.0421% | 98.81% | 37088 | -2437 | 87.36% | 58.53%
|  | Alignment | Kg | 40000 | 39524 | 98.81% | 1 | 39525 |  | 0.01263% | 98.81% | 37088 | -2437 | 83.84% | 56.17%
|  | Bolt Tightening & Test | Kg | 40000 | 25000 | 62.5% | 0 | 25000 |  | 0.00842% | 62.5% | 37088 | 12088 | 82.2% | 55.07%
|  | Grouting | NO | 16 | 0 | 0% | 0 | 0 |  | 0.01053% | 0% | 0 | 0 | 10.5% | 7.035%
|  | Final test & Documents | % | 100 | 52 | 52% | 27 | 79 |  | 0.01579% | 79% | 52 | -27 | 95.05% | 63.68%
|  | 140-IM-E4 |  |  | 0 | 83.03% | 0 |  |  | 0.03736% | 87.38% |  | 0 | 95% | 63.65%
|  | Handling | Kg | 14200 | 14164.5 | 99.75% | 0.5 | 14165 |  | 0.003736% | 99.75% | 14200 | 35 | 95% | 63.65%
|  | Chip&Padding | NO | 6 | 6 | 100% | 0 | 6 |  | 0.001868% | 100% | 6 | 0 | 95% | 63.65%
|  | Erection | Kg | 14200 | 14200 | 100% | 0.4 | 14200.4 |  | 0.01495% | 100% | 14200 | -0.4 | 95% | 63.65%
|  | Alignment | Kg | 14200 | 14164.5 | 99.75% | 0.5 | 14165 |  | 0.004484% | 99.75% | 14200 | 35 | 95% | 63.65%
|  | Bolt Tightening & Test | Kg | 14200 | 14164.5 | 99.75% | 0.5 | 14165 |  | 0.002989% | 99.75% | 14200 | 35 | 14% | 9.38%
|  | Grouting | NO | 6 | 0 | 0% | 0 | 0 |  | 0.003736% | 0% | 0 | 0 | 11% | 7.37%
|  | Final test & Documents | % | 100 | 54 | 54% | 29 | 83 |  | 0.005605% | 83% | 54 | -29 | 11% | 7.37%
|  | 140-IM-F1 |  |  | 0 | 62.2% | 0 |  |  | 0.0942% | 64.3% |  | 0 | 95% | 63.65%
|  | Handling | Kg | 35800 | 35800 | 100% | 0 | 35800 |  | 0.00942% | 100% | 35800 | 0 | 95% | 63.65%
|  | Chip&Padding | NO | 20 | 20 | 100% | 0 | 20 |  | 0.00471% | 100% | 20 | 0 | 95% | 63.65%
|  | Erection | Kg | 35800 | 35800 | 100% | 0.2 | 35800.2 |  | 0.03768% | 100% | 34945 | -855.2 | 95% | 63.65%
|  | Alignment | Kg | 35800 | 0 | 0% | 0 | 0 |  | 0.0113% | 0% | 0 | 0 | 95% | 63.65%
|  | Bolt Tightening & Test | Kg | 35800 | 0 | 0% | 0 | 0 |  | 0.007536% | 0% | 0 | 0 | 95% | 63.65%
|  | Grouting | NO | 20 | 0 | 0% | 0 | 0 |  | 0.00942% | 0% | 0 | 0 | 95% | 63.65%
|  | Final test & Documents | % | 100 | 48 | 48% | 14 | 62 |  | 0.01413% | 62% | 48 | -14 | 79% | 52.93%
|  | 140-IM-F2 |  |  | 0 | 95.05% | 0 |  |  | 0.1429% | 99.25% |  | 0 | 95% | 63.65%
|  | Handling | Kg | 54300 | 5430 | 10% | 48870 | 54300 |  | 0.01429% | 100% | 54300 | 0 | 68% | 45.56%
|  | Chip&Padding | NO | 22 | 22 | 100% | 0 | 22 |  | 0.007144% | 100% | 22 | 0 | 50% | 33.5%
|  | Erection | Kg | 54300 | 54300 | 100% | 0 | 54300 |  | 0.05715% | 100% | 54300 | 0 | 93% | 62.31%
|  | Alignment | Kg | 54300 | 54300 | 100% | 0 | 54300 |  | 0.01715% | 100% | 0 | -54300 | 95% | 63.65%
|  | Bolt Tightening & Test | Kg | 54300 | 54300 | 100% | 0 | 54300 |  | 0.01143% | 100% | 0 | -54300 | 95% | 63.65%
|  | Grouting | NO | 22 | 22 | 100% | 0 | 22 |  | 0.01429% | 100% | 0 | -22 | 95% | 63.65%
|  | Final test & Documents | % | 100 | 67 | 67% | 28 | 95 |  | 0.02143% | 95% | 55 | -40 | 95% | 63.65%
|  | Fireproofing |  |  | 0 | 0% | 0 |  |  | 0.06706% | 0% |  | 0 | 95% | 63.65%
|  | Fireproofing | m2 | 200 | 0 | 0% | 0 | 0 |  | 0.06706% | 0% |  | 0 | 94% | 62.98%
|  | Insulation | ins |  | 0 | 0% | 0 |  |  | 0.212% | 0% |  | 0 | 82% | 54.94%
|  | Cold Insulation | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.106% | 0% |  | 0 | 95% | 63.65%
|  | Hot Insulation | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.106% | 0% |  | 0 | 80% | 53.6%
|  | Equipment Packages | equ |  | 0 | 0% | 0 |  |  | 5.941% | 0% |  | 0 | 83% | 55.61%
|  | Static Equipment |  |  | 0 | 0% | 0 |  |  | 3.268% | 0% |  | 0 | 83% | 55.61%
|  | HP FLARE 140-X-101 |  |  | 0 | 0% | 0 |  |  | 0.7275% | 0% |  | 0 | 95% | 63.65%
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.2546% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.1091% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.1091% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.1455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | HP FLARE 140-X-201 |  |  | 0 |  | 0 |  |  | 0.7275% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.2546% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.1091% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.1091% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.1455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | LP FLARE 140-X-102 |  |  | 0 |  | 0 |  |  | 0.08424% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.004212% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.004212% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.02948% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.01264% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.01264% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.01685% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.004212% | 0% |  | 0
|  | LP FLARE 140-X-202 |  |  | 0 |  | 0 |  |  | 0.08424% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.004212% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.004212% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.02948% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.01264% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.01264% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.01685% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.004212% | 0% |  | 0
|  | MP FLARE 140-X-103 |  |  | 0 |  | 0 |  |  | 0.7275% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.2546% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.1091% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.1091% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.1455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | MP FLARE 140-X-203 |  |  | 0 |  | 0 |  |  | 0.7275% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.2546% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.1091% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.1091% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.1455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.03638% | 0% |  | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-101 |  |  | 0 |  | 0 |  |  | 0.0009343% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.000327% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001401% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.0001401% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001869% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-103 |  |  | 0 |  | 0 |  |  | 0.0009343% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.000327% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001401% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.0001401% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001869% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | HP Cold Flare K.O. Drum Heater 140-DH-104 |  |  | 0 |  | 0 |  |  | 0.0009534% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 4.767e-05% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 4.767e-05% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.0003337% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.000143% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.000143% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001907% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 4.767e-05% | 0% |  | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-201 |  |  | 0 |  | 0 |  |  | 0.0009343% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.000327% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001401% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.0001401% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001869% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | MP Flare K.O. Drum Heater 140-DH-203 |  |  | 0 |  | 0 |  |  | 0.0009343% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.000327% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001401% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.0001401% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001869% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 4.671e-05% | 0% |  | 0
|  | HP Cold Flare K.O. Drum Heater 140-DH-204 |  |  | 0 |  | 0 |  |  | 0.0009534% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 4.767e-05% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 4.767e-05% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.0003337% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.000143% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.000143% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.0001907% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 4.767e-05% | 0% |  | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-105 |  |  | 0 |  | 0 |  |  | 0.04595% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.01608% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.006892% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.006892% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.00919% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-106 |  |  | 0 |  | 0 |  |  | 0.04595% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.01608% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.006892% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.006892% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.00919% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-205 |  |  | 0 |  | 0 |  |  | 0.04595% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.01608% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.006892% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.006892% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.00919% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-206 |  |  | 0 |  | 0 |  |  | 0.04595% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.01608% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.006892% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.006892% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.00919% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.002297% | 0% |  | 0
|  | Rotary Equipment |  |  | 0 |  | 0 |  |  | 2.673% | 0% |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-104A |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-104B |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | LP FLARE STACKS PUMPS, 140-P-105A |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | LP FLARE STACKS PUMPS, 140-P-105B |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | MP FLARE STACKS PUMPS, 140-P-106A |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | MP FLARE STACKS PUMPS, 140-P-106B |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-204A |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-204B |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | LP FLARE STACKS PUMPS, 140-P-205A |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | LP FLARE STACKS PUMPS, 140-P-205B |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | MP FLARE STACKS PUMPS, 140-P-206A |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | MP FLARE STACKS PUMPS, 140-P-206B |  |  | 0 |  | 0 |  |  | 0.2227% | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.07796% | 0% |  | 0
|  | Alignment | Kg | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | Grouting | % | 1 | 0 |  | 0 | 0 |  | 0.03341% | 0% |  | 0
|  | External Installation | Kg | 1 | 0 |  | 0 | 0 |  | 0.04455% | 0% |  | 0
|  | Final Inspection | % | 1 | 0 |  | 0 | 0 |  | 0.01114% | 0% |  | 0
|  | Unit 143 |  |  | 0 | 8.3% | 0 |  |  | 15.14% | 7.439% |  | 0
|  | Welding & NDT Procedures | pip |  | 0 | 45.2% | 0 |  |  | 1.15% | 23.8% |  | 0
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100 | 100 | 100% | 0 | 100 |  | 0.00575% | 100% | 100 | 0
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100 | 100 | 100% | 0 | 100 |  | 0.00575% | 100% | 100 | 0
|  | Qualification of Welding Equipments | % | 100 | 100 | 100% | 0 | 100 |  | 0.00575% | 100% | 100 | 0
|  | Maintaining Welder Qualification Records | % | 100 | 100 | 100% | 0 | 100 |  | 0.00575% | 100% | 100 | 0
|  | Monitoring Welder Performance | % | 100 | 100 | 100% | 0 | 100 |  | 0.00575% | 100% | 100 | 0
|  | Prepare NDT Procedures & Obtain Certification | % | 100 | 100 | 100% | 0 | 50 |  | 0.345% | 50% |  | -50
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100 | 20 | 20% | 0 | 20 |  | 0.00575% | 20% |  | -20
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100 | 20 | 20% | 0 | 20 |  | 0.00575% | 20% |  | -20
|  | Perform NDT as per the Procedures | % | 100 | 20 | 20% | 0 | 20 |  | 0.092% | 20% |  | -20
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100 | 100 | 100% | 0 | 100 |  | 0.092% | 20% | 100 | 0
|  | Prepare PWHT Procedures & Obtain Certification | % | 100 | 0 | 0% | 0 | 0 |  | 0.2875% | 0% |  | 0
|  | Perform PWHT Testing | % | 100 | 0 | 0% | 0 | 0 |  | 0.1495% | 0% |  | 0
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 20% | 0 | 20 |  | 0.138% | 20% |  | -20
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100 | 100% | 0 | 100 |  | 0.00575% | 100% | 100 | 0
|  | Piping | pip |  | 0 | 6.43% | 0 |  |  | 8.885% | 7.674% |  | 0
|  | AG Piping |  |  | 0 | 6.43% | 0 |  |  | 8.794% | 7.753% |  | 0
|  | Shop |  |  | 0 | 10.43% | 0 |  |  | 3.078% | 10.43% |  | 0
|  | Carbon Steel |  |  | 0 | 13.63% | 0 |  |  | 2.083% | 13.63% |  | 0
|  | Material Handling From Lay down To Shop | ID | 26984 | 5220 | 24.24% | 8776 | 13996 |  | 0.1041% | 24.24% | 2000 | -11996
|  | Cutting & Bevelling & Fit Up | ID | 8095 | 1172 | 12.94% | 2899 | 4071 |  | 0.7289% | 12.94% |  | -4071
|  | Welding | ID | 8095 | 900 | 11.82% | 2636 | 3536 |  | 0.7289% | 11.82% |  | -3536
|  | NDT | ID | 8095 | 0 | 0% | 0 | 0 |  | 0.1041% | 0% |  | 0
|  | PWHT | ID | 8095 | 0 | 0% | 0 | 0 |  | 0.1041% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 0.3124% | 25% | 25 | 0
|  | Low Temperature CS |  |  | 0 | 3.75% | 0 |  |  | 0.3407% | 3.75% |  | 0
|  | Material Handling From Lay down To Shop | ID | 93 | 0 | 0% | 0 | 0 |  | 0.01704% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 28 | 0 | 0% | 0 | 0 |  | 0.1193% | 0% |  | 0
|  | Welding | ID | 28 | 0 | 0% | 0 | 0 |  | 0.1193% | 0% |  | 0
|  | NDT | ID | 28 | 0 | 0% | 0 | 0 |  | 0.01704% | 0% |  | 0
|  | PWHT | ID | 28 | 0 | 0% | 0 | 0 |  | 0.01704% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 0.05111% | 25% | 25 | 0
|  | Stainless Steel |  |  | 0 | 3.75% | 0 |  |  | 0.0001235% | 3.75% |  | 0
|  | Material Handling From Lay down To Shop | ID | 41 | 0 | 0% | 0 | 0 |  | 6.173e-06% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 12 | 0 | 0% | 0 | 0 |  | 4.321e-05% | 0% |  | 0
|  | Welding | ID | 12 | 0 | 0% | 0 | 0 |  | 4.321e-05% | 0% |  | 0
|  | NDT | ID | 12 | 0 | 0% | 0 | 0 |  | 6.173e-06% | 0% |  | 0
|  | PWHT | ID | 12 | 0 | 0% | 0 | 0 |  | 6.173e-06% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 1.852e-05% | 25% | 25 | 0
|  | Galva |  |  | 0 | 3.75% | 0 |  |  | 0.1825% | 3.75% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1971 | 0 | 0% | 0 | 0 |  | 0.009123% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 591 | 0 | 0% | 0 | 0 |  | 0.06386% | 0% |  | 0
|  | Welding | ID | 591 | 0 | 0% | 0 | 0 |  | 0.06386% | 0% |  | 0
|  | NDT | ID | 591 | 0 | 0% | 0 | 0 |  | 0.009123% | 0% |  | 0
|  | PWHT | ID | 591 | 0 | 0% | 0 | 0 |  | 0.009123% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 0.02737% | 25% | 25 | 0
|  | CU-NI |  |  | 0 | 3.75% | 0 |  |  | 0.472% | 3.75% |  | 0
|  | Material Handling From Lay down To Shop | ID | 5256 | 0 | 0% | 0 | 0 |  | 0.0236% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1577 | 0 | 0% | 0 | 0 |  | 0.1652% | 0% |  | 0
|  | Welding | ID | 1577 | 0 | 0% | 0 | 0 |  | 0.1652% | 0% |  | 0
|  | NDT | ID | 1577 | 0 | 0% | 0 | 0 |  | 0.0236% | 0% |  | 0
|  | PWHT | ID | 1577 | 0 | 0% | 0 | 0 |  | 0.0236% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 0.07081% | 25% | 25 | 0
|  | Field |  |  | 0 | 4.28% | 0 |  |  | 5.716% | 6.31% |  | 0
|  | Carbon Steel |  |  | 0 | 5.13% | 0 |  |  | 3.868% | 8.131% |  | 0
|  | Material Handling From Shop To Field | ID | 26984 | 1488 | 5.89% | 1400 | 2888 |  | 0.1934% | 10.7% | 1072 | -1816
|  | Scaffolding | M2 | 1 | 0 | 0% | 0 | 0 |  | 0.5028% | 0% |  | 0
|  | Erection & Fit Up | ID | 18889 | 966 | 6.06% | 861 | 1827 |  | 0.7348% | 9.672% | 756 | -1071
|  | Valve Installation | ID | 380 | 0 | 0% | 0 | 0 |  | 0.1934% | 0% |  | 0
|  | Welding | ID | 18889 | 706 | 3.41% | 1118 | 1824 |  | 1.276% | 9.656% | 756 | -1068
|  | NDT | ID | 18889 | 540 | 2.46% | 0 | 540 |  | 0.09669% | 2.859% |  | -540
|  | PWHT | ID | 18889 | 0 | 0% | 0 | 0 |  | 0.116% | 0% |  | 0
|  | Hydro test | ID | 18889 | 0 | 0% | 0 | 0 |  | 0.3674% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 0.3868% | 25% | 25 | 0
|  | Low Temperature CS |  |  | 0 | 2.5% | 0 |  |  | 0.6328% | 2.5% |  | 0
|  | Material Handling From Shop To Field | ID | 93 | 0 | 0% | 0 | 0 |  | 0.03164% | 0% |  | 0
|  | Scaffolding | M2 | 1 | 0 | 0% | 0 | 0 |  | 0.08226% | 0% |  | 0
|  | Erection & Fit Up | ID | 65 | 0 | 0% | 0 | 0 |  | 0.1202% | 0% |  | 0
|  | Valve Installation | ID | 380 | 0 | 0% | 0 | 0 |  | 0.03164% | 0% |  | 0
|  | Welding | ID | 65 | 0 | 0% | 0 | 0 |  | 0.2088% | 0% |  | 0
|  | NDT | ID | 65 | 0 | 0% | 0 | 0 |  | 0.01582% | 0% |  | 0
|  | PWHT | ID | 65 | 0 | 0% | 0 | 0 |  | 0.01898% | 0% |  | 0
|  | Hydro test | ID | 65 | 0 | 0% | 0 | 0 |  | 0.06012% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 0.06328% | 25% | 25 | 0
|  | Stainless Steel |  |  | 0 | 2.5% | 0 |  |  | 0.0002293% | 2.5% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0% | 0 | 0 |  | 1.146e-05% | 0% |  | 0
|  | Scaffolding | M2 | 1 | 0 | 0% | 0 | 0 |  | 2.981e-05% | 0% |  | 0
|  | Erection & Fit Up | ID | 1 | 0 | 0% | 0 | 0 |  | 4.356e-05% | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0% | 0 | 0 |  | 1.146e-05% | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0% | 0 | 0 |  | 7.566e-05% | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0% | 0 | 0 |  | 5.732e-06% | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0% | 0 | 0 |  | 6.878e-06% | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0% | 0 | 0 |  | 2.178e-05% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 2.293e-05% | 25% | 25 | 0
|  | Galva |  |  | 0 | 2.5% | 0 |  |  | 0.3389% | 2.5% |  | 0
|  | Material Handling From Shop To Field | ID | 41 | 0 | 0% | 0 | 0 |  | 0.01694% | 0% |  | 0
|  | Scaffolding | M2 | 1 | 0 | 0% | 0 | 0 |  | 0.04405% | 0% |  | 0
|  | Erection & Fit Up | ID | 29 | 0 | 0% | 0 | 0 |  | 0.06439% | 0% |  | 0
|  | Valve Installation | ID | 380 | 0 | 0% | 0 | 0 |  | 0.01694% | 0% |  | 0
|  | Welding | ID | 29 | 0 | 0% | 0 | 0 |  | 0.1118% | 0% |  | 0
|  | NDT | ID | 29 | 0 | 0% | 0 | 0 |  | 0.008472% | 0% |  | 0
|  | PWHT | ID | 29 | 0 | 0% | 0 | 0 |  | 0.01017% | 0% |  | 0
|  | Hydro test | ID | 29 | 0 | 0% | 0 | 0 |  | 0.03219% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 0.03389% | 25% | 25 | 0
|  | CU-NI |  |  | 0 | 2.5% | 0 |  |  | 0.8766% | 2.5% |  | 0
|  | Material Handling From Shop To Field | ID | 1971 | 0 | 0% | 0 | 0 |  | 0.04383% | 0% |  | 0
|  | Scaffolding | M2 | 1 | 0 | 0% | 0 | 0 |  | 0.114% | 0% |  | 0
|  | Erection & Fit Up | ID | 1380 | 0 | 0% | 0 | 0 |  | 0.1666% | 0% |  | 0
|  | Valve Installation | ID | 381 | 0 | 0% | 0 | 0 |  | 0.04383% | 0% |  | 0
|  | Welding | ID | 1380 | 0 | 0% | 0 | 0 |  | 0.2893% | 0% |  | 0
|  | NDT | ID | 1380 | 0 | 0% | 0 | 0 |  | 0.02192% | 0% |  | 0
|  | PWHT | ID | 1380 | 0 | 0% | 0 | 0 |  | 0.0263% | 0% |  | 0
|  | Hydro test | ID | 1380 | 0 | 0% | 0 | 0 |  | 0.08328% | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 |  | 0.08766% | 25% | 25 | 0
|  | Pipe Support |  |  | 0 | 0% | 0 |  |  | 0.09079% | 0% |  | 0
|  | Shop |  |  | 0 | 0% | 0 |  |  | 0.03178% | 0% |  | 0
|  | Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.003495% | 0% |  | 0
|  | shop drawing | Kg | 1 | 0 |  | 0 | 0 |  | 0.005084% | 0% |  | 0
|  | Cutting & assembling | Kg | 1 | 0 |  | 0 | 0 |  | 0.006991% | 0% |  | 0
|  | Welding | Kg | 1 | 0 |  | 0 | 0 |  | 0.01462% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 0 | 0 |  | 0.001589% | 0% |  | 0
|  | Field |  |  | 0 | 0% | 0 |  |  | 0.05901% | 0% |  | 0
|  | Material Handling From Shop To Field | Kg | 1 | 0 |  | 0 | 0 |  | 0.006491% | 0% |  | 0
|  | Erection | Kg | 1 | 0 |  | 0 | 0 |  | 0.01239% | 0% |  | 0
|  | Welding | Kg | 1 | 0 |  | 0 | 0 |  | 0.03069% | 0% |  | 0
|  | NDT | Kg | 1 | 0 |  | 0 | 0 |  | 0.006491% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 0 | 0 |  | 0.002951% | 0% |  | 0
|  | Painting & Sandblasting | pan |  | 0 | 14.69% | 0 |  |  | 1.164% | 14.69% |  | 0
|  | Pipe |  |  | 0 | 14.84% | 0 |  |  | 1.152% | 14.84% |  | 0
|  | Sand Blast | m2 | 11000 | 4664 | 42.4% | 0 | 4663.99 |  | 0.1728% | 42.4% | 3480 | -1183.99
|  | Primer | m2 | 11000 | 4664 | 42.4% | 0 | 4663.99 |  | 0.2304% | 42.4% | 3480 | -1183.99
|  | Middle Paint | m2 | 11000 | 0 | 0% | 0 | 0 |  | 0.4032% | 0% |  | 0
|  | Final Paint | m2 | 11000 | 0 | 0% | 0 | 0 |  | 0.2304% | 0% |  | 0
|  | Touch Up & Punch | m2 | 11000 | 0 | 0% | 0 | 0 |  | 0.05759% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0% | 0 | 0 |  | 0.05759% | 0% |  | 0
|  | Support |  |  | 0 | 0% | 0 |  |  | 0.01189% | 0% |  | 0
|  | Sand Blast | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.001784% | 0% |  | 0
|  | Primer | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.002378% | 0% |  | 0
|  | Middle Paint | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.004162% | 0% |  | 0
|  | Final Paint | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.002378% | 0% |  | 0
|  | Touch Up & Punch | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.0005946% | 0% |  | 0
|  | Final Certificate | % | 1 | 0 | 0% | 0 | 0 |  | 0.0005946% | 0% |  | 0
|  | Insulation | ins |  | 0 | 0% | 0 |  |  | 0.09649% | 0% |  | 0
|  | Cold Insulation | M2 | 1 | 0 | 0% | 0 | 0 |  | 0.04825% | 0% |  | 0
|  | Hot Insulation | M2 | 1 | 0 | 0% | 0 | 0 |  | 0.04825% | 0% |  | 0
|  | Equipment Packages | equ |  | 0 | 0% | 0 |  |  | 3.848% | 0% |  | 0
|  | Static Equipment |  |  | 0 | 0% | 0 |  |  | 0.2516% | 0% |  | 0
|  | Sump Drum 143-D-101 |  |  | 0 | 0% | 0 |  |  | 0.1962% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.009808% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.009808% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.06866% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.02942% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.02942% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.03923% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.009808% | 0% |  | 0
|  | Degassing Boot 143-D-102 |  |  | 0 | 0% | 0 |  |  | 0.05541% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.00277% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.00277% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01939% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.008311% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.008311% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01108% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.00277% | 0% |  | 0
|  | Rotary Equipment |  |  | 0 |  | 0 |  |  | 3.597% | 0% |  | 0
|  | Pump 143-P-101 |  |  | 0 |  | 0 |  |  | 0.5136% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.02568% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.02568% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1798% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.07705% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.07705% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1027% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.02568% | 0% |  | 0
|  | Pump 143-P-102 |  |  | 0 |  | 0 |  |  | 0.9399% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.329% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.141% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.141% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.188% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.047% | 0% |  | 0
|  | Pump 143-P-103 A |  |  | 0 |  | 0 |  |  | 0.6093% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.2133% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.0914% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.0914% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1219% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Pump 143-P-103 B |  |  | 0 |  | 0 |  |  | 0.6093% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.2133% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.0914% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.0914% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1219% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Pump 143-P-103 C |  |  | 0 |  | 0 |  |  | 0.6093% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.2133% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.0914% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.0914% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1219% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.03047% | 0% |  | 0
|  | Pump 143-P-104 |  |  | 0 |  | 0 |  |  | 0.3151% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.01575% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.01575% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1103% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.04726% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.04726% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.06301% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.01575% | 0% |  | 0
|  | Unit 147/148 |  |  | 0 | 5.21% | 0 |  |  | 21.87% | 4.455% |  | 0
|  | Welding & NDT Procedures | pip |  | 0 | 45.2% | 0 |  |  | 1.323% | 30.2% |  | 0
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100 | 100 | 100% | 0 | 100 |  | 0.006615% | 100% | 100 | 0
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100 | 100 | 100% | 0 | 100 |  | 0.006615% | 100% | 100 | 0
|  | Qualification of Welding Equipments | % | 100 | 100 | 100% | 0 | 100 |  | 0.006615% | 100% | 100 | 0
|  | Maintaining Welder Qualification Records | % | 100 | 100 | 100% | 0 | 100 |  | 0.006615% | 100% | 100 | 0
|  | Monitoring Welder Performance | % | 100 | 100 | 100% | 0 | 100 |  | 0.006615% | 100% | 100 | 0
|  | Prepare NDT Procedures & Obtain Certification | % | 100 | 100 | 100% | 0 | 50 |  | 0.3969% | 50% |  | -50
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100 | 20 | 20% | 0 | 20 |  | 0.006615% | 20% |  | -20
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100 | 20 | 20% | 0 | 20 |  | 0.006615% | 20% |  | -20
|  | Perform NDT as per the Procedures | % | 100 | 20 | 20% | 0 | 20 |  | 0.1058% | 20% |  | -20
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100 | 100 | 100% | 0 | 100 |  | 0.1058% | 100% | 100 | 0
|  | Prepare PWHT Procedures & Obtain Certification | % | 100 | 0 | 0% | 0 | 0 |  | 0.3307% | 0% |  | 0
|  | Perform PWHT Testing | % | 100 | 0 | 0% | 0 | 0 |  | 0.172% | 0% |  | 0
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 20% | 0 | 20 |  | 0.1588% | 20% |  | -20
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100 | 100% | 0 | 100.0001 |  | 0.006615% | 100% | 100 | -6.615e-05
|  | Piping | pip |  | 0 | 4.89% | 0 |  |  | 10.22% | 5.227% |  | 0
|  | AG Piping |  |  | 0 | 4.94% | 0 |  |  | 10.12% | 5.281% |  | 0
|  | Shop |  |  | 0 | 6.69% | 0 |  |  | 3.541% | 7.661% |  | 0
|  | Carbon Steel |  |  | 0 | 12.28% | 0 |  |  | 0.3889% | 21.12% |  | 0
|  | Material Handling From Lay down To Shop | ID | 4934 | 1136.3002 | 23.03% | 296.6998 | 1433 |  | 0.01944% | 23.03% | 600 | -833
|  | Cutting & Bevelling & Fit Up | ID | 1480 | 216.82 | 14.65% | 350.18 | 567 |  | 0.1361% | 14.65% |  | -567
|  | Welding | ID | 1480 | 0 | 0% | 374 | 374 |  | 0.1361% | 25.27% |  | -374
|  | NDT | ID | 1480 | 0 | 0% | 0 | 0 |  | 0.01944% | 0% |  | 0
|  | PWHT | ID | 1480 | 0 | 0% | 0 | 0 |  | 0.01944% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.05833% | 40% | 40 | 0
|  | Low Temperature CS |  |  | 0 | 6% | 0 |  |  | 2.875% | 6% |  | 0
|  | Material Handling From Lay down To Shop | ID | 36676 | 0 | 0% | 0 | 0 |  | 0.1438% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 11003 | 0 | 0% | 0 | 0 |  | 1.006% | 0% |  | 0
|  | Welding | ID | 11003 | 0 | 0% | 0 | 0 |  | 1.006% | 0% |  | 0
|  | NDT | ID | 11003 | 0 | 0% | 0 | 0 |  | 0.1438% | 0% |  | 0
|  | PWHT | ID | 11003 | 0 | 0% | 0 | 0 |  | 0.1438% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.4313% | 40% | 40 | 0
|  | Galva |  |  | 0 | 6% | 0 |  |  | 0.04255% | 6% |  | 0
|  | Material Handling From Lay down To Shop | ID | 544 | 0 | 0% | 0 | 0 |  | 0.002127% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 163 | 0 | 0% | 0 | 0 |  | 0.01489% | 0% |  | 0
|  | Welding | ID | 163 | 0 | 0% | 0 | 0 |  | 0.01489% | 0% |  | 0
|  | NDT | ID | 163 | 0 | 0% | 0 | 0 |  | 0.002127% | 0% |  | 0
|  | PWHT | ID | 163 | 0 | 0% | 0 | 0 |  | 0.002127% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.006382% | 40% | 40 | 0
|  | Copper Alloys |  |  | 0 | 6% | 0 |  |  | 0.2344% | 6% |  | 0
|  | Material Handling From Lay down To Shop | ID | 578 | 0 | 0% | 0 | 0 |  | 0.01172% | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 173 | 0 | 0% | 0 | 0 |  | 0.08205% | 0% |  | 0
|  | Welding | ID | 173 | 0 | 0% | 0 | 0 |  | 0.08205% | 0% |  | 0
|  | NDT | ID | 173 | 0 | 0% | 0 | 0 |  | 0.01172% | 0% |  | 0
|  | PWHT | ID | 173 | 0 | 0% | 0 | 0 |  | 0.01172% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.03516% | 40% | 40 | 0
|  | Field |  |  | 0 | 4% | 0 |  |  | 6.576% | 4% |  | 0
|  | Carbon Steel |  |  | 0 | 4% | 0 |  |  | 0.7134% | 4% |  | 0
|  | Material Handling From Shop To Field | ID | 6223 | 0 | 0% | 0 | 0 |  | 0.03567% | 0% |  | 0
|  | Scaffolding | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.09275% | 0% |  | 0
|  | Erection & Fit Up | ID | 4045 | 0 | 0% | 0 | 0 |  | 0.1356% | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0% | 0 | 0 |  | 0.03567% | 0% |  | 0
|  | Welding | ID | 4045 | 0 | 0% | 0 | 0 |  | 0.2354% | 0% |  | 0
|  | NDT | ID | 4045 | 0 | 0% | 0 | 0 |  | 0.01784% | 0% |  | 0
|  | PWHT | ID | 4045 | 0 | 0% | 0 | 0 |  | 0.0214% | 0% |  | 0
|  | Hydro test | ID | 4045 | 0 | 0% | 0 | 0 |  | 0.06778% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.07134% | 40% | 40 | 0
|  | Low Temperature CS |  |  | 0 | 4% | 0 |  |  | 5.276% | 4% |  | 0
|  | Material Handling From Shop To Field | ID | 36676 | 0 | 0% | 0 | 0 |  | 0.2638% | 0% |  | 0
|  | Scaffolding | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.6858% | 0% |  | 0
|  | Erection & Fit Up | ID | 25673 | 0 | 0% | 0 | 0 |  | 1.002% | 0% |  | 0
|  | Valve Installation | ID | 611 | 0 | 0% | 0 | 0 |  | 0.2638% | 0% |  | 0
|  | Welding | ID | 25673 | 0 | 0% | 0 | 0 |  | 1.741% | 0% |  | 0
|  | NDT | ID | 25673 | 0 | 0% | 0 | 0 |  | 0.1319% | 0% |  | 0
|  | PWHT | ID | 25673 | 0 | 0% | 0 | 0 |  | 0.1583% | 0% |  | 0
|  | Hydro test | ID | 25673 | 0 | 0% | 0 | 0 |  | 0.5012% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.5276% | 40% | 40 | 0
|  | Galva |  |  | 0 | 4% | 0 |  |  | 0.07807% | 4% |  | 0
|  | Material Handling From Shop To Field | ID | 544 | 0 | 0% | 0 | 0 |  | 0.003904% | 0% |  | 0
|  | Scaffolding | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.01015% | 0% |  | 0
|  | Erection & Fit Up | ID | 381 | 0 | 0% | 0 | 0 |  | 0.01483% | 0% |  | 0
|  | Valve Installation | ID | 611 | 0 | 0% | 0 | 0 |  | 0.003904% | 0% |  | 0
|  | Welding | ID | 381 | 0 | 0% | 0 | 0 |  | 0.02576% | 0% |  | 0
|  | NDT | ID | 381 | 0 | 0% | 0 | 0 |  | 0.001952% | 0% |  | 0
|  | PWHT | ID | 381 | 0 | 0% | 0 | 0 |  | 0.002342% | 0% |  | 0
|  | Hydro test | ID | 381 | 0 | 0% | 0 | 0 |  | 0.007417% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.007807% | 40% | 40 | 0
|  | GRE |  |  | 0 | 4% | 0 |  |  | 0.07876% | 4% |  | 0
|  | Scoffolding | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.01024% | 0% |  | 0
|  | Material Handling To Field | ID | 386 | 0 | 0% | 0 | 0 |  | 0.004726% | 0% |  | 0
|  | Erection & Fittup | ID | 270 | 0 | 0% | 0 | 0 |  | 0.01496% | 0% |  | 0
|  | Bonding | ID | 270 | 0 | 0% | 0 | 0 |  | 0.0315% | 0% |  | 0
|  | Hydro test | ID | 270 | 0 | 0% | 0 | 0 |  | 0.009451% | 0% |  | 0
|  | Final Certificate | % | 100 | 4 | 4% | 36 | 40 |  | 0.007876% | 40% | 40 | 0
|  | Copper Alloys |  |  | 0 | 4% | 0 |  |  | 0.4302% | 4% |  | 0
|  | Material Handling From Shop To Field | ID | 192 | 0 | 0% | 0 | 0 |  | 0.02151% | 0% |  | 0
|  | Scaffolding | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.05592% | 0% |  | 0
|  | Erection & Fit Up | ID | 134 | 0 | 0% | 0 | 0 |  | 0.08173% | 0% |  | 0
|  | Valve Installation | ID | 611 | 0 | 0% | 0 | 0 |  | 0.02151% | 0% |  | 0
|  | Welding | ID | 134 | 0 | 0% | 0 | 0 |  | 0.142% | 0% |  | 0
|  | NDT | ID | 134 | 0 | 0% | 0 | 0 |  | 0.01075% | 0% |  | 0
|  | PWHT | ID | 134 | 0 | 0% | 0 | 0 |  | 0.0129% | 0% |  | 0
|  | Hydro test | ID | 134 | 0 | 0% | 0 | 0 |  | 0.04086% | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 |  | 0.04302% | 40% | 40 | 0
|  | Pipe Support |  |  | 0 | 0% | 0 |  |  | 0.1044% | 0% |  | 0
|  | Shop |  |  | 0 | 0% | 0 |  |  | 0.03656% | 0% |  | 0
|  | Handling | Kg | 1 | 0 |  | 0 | 0 |  | 0.004021% | 0% |  | 0
|  | shop drawing | Kg | 1 | 0 |  | 0 | 0 |  | 0.005849% | 0% |  | 0
|  | Cutting & assembling | Kg | 1 | 0 |  | 0 | 0 |  | 0.008042% | 0% |  | 0
|  | Welding | Kg | 1 | 0 |  | 0 | 0 |  | 0.01682% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 0 | 0 |  | 0.001828% | 0% |  | 0
|  | Field |  |  | 0 | 0% | 0 |  |  | 0.06789% | 0% |  | 0
|  | Material Handling From Shop To Field | Kg | 1 | 0 |  | 0 | 0 |  | 0.01086% | 0% |  | 0
|  | Erection | Kg | 1 | 0 |  | 0 | 0 |  | 0.01426% | 0% |  | 0
|  | Welding | Kg | 1 | 0 |  | 0 | 0 |  | 0.02851% | 0% |  | 0
|  | NDT | Kg | 1 | 0 |  | 0 | 0 |  | 0.01086% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 |  | 0 | 0 |  | 0.003394% | 0% |  | 0
|  | Painting & Sandblasting | pan |  | 0 | 2.86% | 0 |  |  | 1.339% | 2.858% |  | 0
|  | Pipe |  |  | 0 | 2.89% | 0 |  |  | 1.325% | 2.887% |  | 0
|  | Sand Blast | m2 | 5200 | 429 | 8.25% | 0 | 429 |  | 0.1988% | 8.25% | 415 | -14
|  | Primer | m2 | 5201 | 429.0825 | 8.25% | 0 | 429 |  | 0.265% | 8.248% | 415 | -14
|  | Middle Paint | m2 | 5202 | 0 | 0% | 0 | 0 |  | 0.4638% | 0% |  | 0
|  | Final Paint | m2 | 5203 | 0 | 0% | 0 | 0 |  | 0.265% | 0% |  | 0
|  | Touch Up & Punch | m2 | 5204 | 0 | 0% | 0 | 0 |  | 0.06626% | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0% | 0 | 0 |  | 0.06626% | 0% |  | 0
|  | Support |  |  | 0 | 0% | 0 |  |  | 0.01368% | 0% |  | 0
|  | Sand Blast | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.002052% | 0% |  | 0
|  | Primer | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.002736% | 0% |  | 0
|  | Middle Paint | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.004788% | 0% |  | 0
|  | Final Paint | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.002736% | 0% |  | 0
|  | Touch Up & Punch | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.000684% | 0% |  | 0
|  | Final Certificate | % | 1 | 0 | 0% | 0 | 0 |  | 0.000684% | 0% |  | 0
|  | Insulation | ins |  | 0 | 0% | 0 |  |  | 0.111% | 0% |  | 0
|  | Cold Insulation | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.0555% | 0% |  | 0
|  | Hot Insulation | m2 | 1 | 0 | 0% | 0 | 0 |  | 0.0555% | 0% |  | 0
|  | Equipment Packages | equ |  | 0 | 0.03% | 0 |  |  | 8.88% | 0.0274% |  | 0
|  | Static Equipment |  |  | 0 | 0.2% | 0 |  |  | 1.217% | 0.2% |  | 0
|  | Air cooler 147-A-101 |  |  | 0 | 0% | 0 |  |  | 0.7488% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.03744% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.03744% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.2621% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.1123% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.1123% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1498% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.03744% | 0% |  | 0
|  | Drum (Vert.) 147-D-101 A |  |  | 0 |  | 0 |  |  | 0.03062% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001531% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001531% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01072% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.004594% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.004594% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.006125% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001531% | 0% |  | 0
|  | Drum (Vert.) 147-D-101 B |  |  | 0 |  | 0 |  |  | 0.03062% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001531% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001531% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01072% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.004594% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.004594% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.006125% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001531% | 0% |  | 0
|  | Drum (Vert.) 147-D-102 A |  |  | 0 |  | 0 |  |  | 0.0161% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0008049% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0008049% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.005635% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.002415% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.002415% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.00322% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0008049% | 0% |  | 0
|  | Drum (Vert.) 147-D-102 B |  |  | 0 |  | 0 |  |  | 0.0161% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0008049% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0008049% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.005635% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.002415% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.002415% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.00322% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0008049% | 0% |  | 0
|  | Drum (Vert.) 147-D-103 A |  |  | 0 |  | 0 |  |  | 0.01662% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0008311% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0008311% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.005818% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.002493% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.002493% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003325% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0008311% | 0% |  | 0
|  | Drum (Vert.) 147-D-103 B |  |  | 0 |  | 0 |  |  | 0.01662% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0008311% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0008311% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.005818% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.002493% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.002493% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003325% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0008311% | 0% |  | 0
|  | Drum (Hori) 147-D-104 |  |  | 0 |  | 0 |  |  | 0.0912% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.00456% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.00456% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.03192% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.01368% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.01368% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01824% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.00456% | 0% |  | 0
|  | Drum (Vert.) 147-D-105 |  |  | 0 |  | 0 |  |  | 0.01977% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0009884% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0009884% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.006919% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.002965% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.002965% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003954% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0009884% | 0% |  | 0
|  | Drum (Hori) 147-D-106 |  |  | 0 |  | 0 |  |  | 0.01018% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005092% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005092% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003564% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001527% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001527% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002037% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005092% | 0% |  | 0
|  | Drum (Hori) 147-D-107 |  |  | 0 |  | 0 |  |  | 0.01947% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0009734% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0009734% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.006814% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.00292% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.00292% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003894% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0009734% | 0% |  | 0
|  | Drum (Hori) 147-D-108 |  |  | 0 |  | 0 |  |  | 0.0001498% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 7.488e-06% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 7.488e-06% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 5.241e-05% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 2.246e-05% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 2.246e-05% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 2.995e-05% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 7.488e-06% | 0% |  | 0
|  | Drum (Hori.) in Sump 147-D-109 |  |  | 0 |  | 0 |  |  | 0.02462% | 9.884% |  | 0
|  | Material Handling | Kg | 16440 | 0 |  | 16060 | 16060 |  | 0.001231% | 97.69% |  | -16060
|  | Chipping & Padding | % | 100 | 0 |  | 100 | 100 |  | 0.001231% | 100% |  | -100
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.008617% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.003693% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.003693% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.004924% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001231% | 0% |  | 0
|  | Drum (Hori) on St. 147-D-110 |  |  | 0 |  | 0 |  |  | 0.05272% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.002636% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.002636% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01845% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.007908% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.007908% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01054% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.002636% | 0% |  | 0
|  | LP FLARE K.O. DRUM 147-D-111 |  |  | 0 |  | 0 |  |  | 0.007937% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0003968% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0003968% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002778% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001191% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001191% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.001587% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0003968% | 0% |  | 0
|  | Electric Heater 147-DH-107 |  |  | 0 |  | 0 |  |  | 0.0001857% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 9.285e-06% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 9.285e-06% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 6.499e-05% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 2.785e-05% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 2.785e-05% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 3.714e-05% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 9.285e-06% | 0% |  | 0
|  | Electric Heater 147-DH-108 |  |  | 0 |  | 0 |  |  | 0.0003519% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 1.76e-05% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 1.76e-05% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.0001232% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 5.279e-05% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 5.279e-05% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 7.038e-05% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 1.76e-05% | 0% |  | 0
|  | Electric Heater 147-DH-109 |  |  | 0 |  | 0 |  |  | 0.000292% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 1.46e-05% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 1.46e-05% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.0001022% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 4.38e-05% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 4.38e-05% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 5.84e-05% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 1.46e-05% | 0% |  | 0
|  | Electric Heater 147-DH-110 |  |  | 0 |  | 0 |  |  | 0.0003654% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 1.827e-05% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 1.827e-05% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.0001279% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 5.481e-05% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 5.481e-05% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 7.308e-05% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 1.827e-05% | 0% |  | 0
|  | LPG TANK FLARE 147-X-101 |  |  | 0 |  | 0 |  |  | 0.03744% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001872% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001872% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.0131% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.005616% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.005616% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007488% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001872% | 0% |  | 0
|  | LOW PRESSURE PROPANE CHILLER 147-E-101 |  |  | 0 |  | 0 |  |  | 0.01481% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0007405% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0007405% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.005184% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.002222% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.002222% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002962% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0007405% | 0% |  | 0
|  | MEDUIM PRESSURE PROPANE CHILLER 147-E-102 |  |  | 0 |  | 0 |  |  | 0.031% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.00155% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.00155% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01085% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.00465% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.00465% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.0062% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.00155% | 0% |  | 0
|  | HIGH PRESSURE PROPANE CHILLER 147-E-103 |  |  | 0 |  | 0 |  |  | 0.02037% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001018% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001018% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007128% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.003055% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.003055% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.004073% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001018% | 0% |  | 0
|  | PROPANE BOIL OFF GAS CONDENSER 147-E-104 |  |  | 0 |  | 0 |  |  | 0.01048% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005241% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005241% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003669% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001572% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001572% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002097% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005241% | 0% |  | 0
|  | Rotary Equipment |  |  | 0 |  | 0 |  |  | 7.663% | 0% |  | 0
|  | Compressor 147-K-101A |  |  | 0 | 0% | 0 |  |  | 2.677% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.1339% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.1339% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.937% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.4016% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.4016% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.5354% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.1339% | 0% |  | 0
|  | Compressor 147-K-101B |  |  | 0 | 0% | 0 |  |  | 2.677% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.1339% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.1339% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.937% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.4016% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.4016% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.5354% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.1339% | 0% |  | 0
|  | Compressor 147-K-102A |  |  | 0 | 0% | 0 |  |  | 0.9691% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.04845% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.04845% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.3392% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.1454% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.1454% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1938% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.04845% | 0% |  | 0
|  | Compressor 147-K-101B |  |  | 0 | 0% | 0 |  |  | 0.9691% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.04845% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.04845% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.3392% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.1454% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.1454% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.1938% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.04845% | 0% |  | 0
|  | Pump 147-P-101A |  |  | 0 | 0% | 0 |  |  | 0.03634% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01272% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.005451% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.005451% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007268% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Pump 147-P-101B |  |  | 0 | 0% | 0 |  |  | 0.03634% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01272% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.005451% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.005451% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007268% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Pump 147-P-101C |  |  | 0 | 0% | 0 |  |  | 0.03634% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.01272% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.005451% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.005451% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007268% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001817% | 0% |  | 0
|  | Pump 147-P-102 |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 147-P-103A |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 147-P-103B |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 147-P-103C |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 147-P-104 |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 147-P-106 |  |  | 0 | 0% | 0 |  |  | 0.02261% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001131% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001131% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007914% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.003392% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.003392% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.004522% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001131% | 0% |  | 0
|  | Pump 147-P-107 |  |  | 0 | 0% | 0 |  |  | 0.02112% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001056% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001056% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007391% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.003168% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.003168% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.004224% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001056% | 0% |  | 0
|  | Pump 147-P-108 |  |  | 0 | 0% | 0 |  |  | 0.01928% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.000964% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.000964% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.006748% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.002892% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.002892% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003856% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.000964% | 0% |  | 0
|  | Pump 147-P-109A |  |  | 0 | 9.88% | 0 |  |  | 0.01878% | 0% |  | 0
|  | Material Handling |  | 1 | 0.9769 | 97.69% | 0 | 0 |  | 0.0009388% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 1 | 100% | 0 | 0 |  | 0.0009388% | 0% |  | 0
|  | Installation |  | 1 | 0 | 0% | 0 | 0 |  | 0.006571% | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 |  | 0.002816% | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 |  | 0.002816% | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 |  | 0.003755% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 |  | 0.0009388% | 0% |  | 0
|  | Pump 147-P-109B |  |  | 0 | 0% | 0 |  |  | 0.01878% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0009388% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0009388% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.006571% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.002816% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.002816% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003755% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0009388% | 0% |  | 0
|  | Pump 148-P-101A |  |  | 0 | 0% | 0 |  |  | 0.02019% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007066% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.003028% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.003028% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.004038% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Pump 148-P-101B |  |  | 0 | 0% | 0 |  |  | 0.02019% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007066% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.003028% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.003028% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.004038% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Pump 148-P-101C |  |  | 0 | 0% | 0 |  |  | 0.02019% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.007066% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.003028% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.003028% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.004038% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.001009% | 0% |  | 0
|  | Pump 148-P-102 |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 148-P-103A |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 148-P-103B |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 148-P-103C |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Pump 148-P-104 |  |  | 0 | 0% | 0 |  |  | 0.01009% | 0% |  | 0
|  | Material Handling |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
|  | Installation |  | 1 | 0 |  | 0 | 0 |  | 0.003533% | 0% |  | 0
|  | Alignment |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | Grouting |  | 1 | 0 |  | 0 | 0 |  | 0.001514% | 0% |  | 0
|  | External Installation |  | 1 | 0 |  | 0 | 0 |  | 0.002019% | 0% |  | 0
|  | Final Inspection |  | 1 | 0 |  | 0 | 0 |  | 0.0005047% | 0% |  | 0
0
0

## Planning 3 (hidden)
South Pars Gas Field Development Phases 14
|  | Date : | 2014-05-01
Description |  |  | Unit | Quantity |  |  |  | Work Performed | Remain | W.F | Up To Now |  |  |  |  | Up To Now
|  |  |  | Estimate | Up To Last | Up To Last % Actual | This Month |  |  |  | % Actual |  | 58 |  |  | % Actual | last | پیمانکار | تاییدی | اختلاف
|  | Package NO.2 |  |  |  | 34.37% |  |  |  | 100% | 34.86% |  | 2.6 |  |  | 33.36% | 27.47% |  |  |  | Material Hndling | fit up | welding
|  | Procurement | per | 0 | 0 | 90% | 0 | 0 | 0 | 15% | 93.48% |  | 6826 | 14.02% |  | 90% | 76.07% | 76.07% | 76.07% | 0% | 58655 | 22531 | 15546.375
|  | fire proof | per | 0 | 0 | 0% | 0 | 0 | 0 | 0.1987% | 0% |  | 29 |  |  | 0% | 0% | 0% | 0% | 0%
|  | PO Placement | m2 | 200 | 0 | 0% | 0 | 0 | 200 | 0.04968% | 0% |  | 35 |  |  | 0% | 0% | 0% | 0% | 0%
|  | Fabrication & Test | m2 | 200 | 0 | 0% | 0 | 0 | 200 | 0.1192% | 0% |  | 2275 |  |  | 0% | 0% | 0% | 0% | 0%
|  | Delivery | m2 | 200 | 0 | 0% | 0 | 0 | 200 | 0.02981% | 0% |  | 103 |  |  | 0% | 0% | 0% | 0% | 0%
|  | Rebar | per | 0 | 0 | 100% | 0 | 0 | 0 | 4.373% | 100% | 308693 | 28 |  |  | 100% | 100% | 100% | 100% | 0%
|  | PO Placement | Kg | 308693 | 308693 | 100% | 0 | 308693 | 0 | 1.093% | 100% |  | 100 |  |  | 100% | 100% | 100% | 100% | 0%
|  | Fabrication & Test | Kg | 308693 | 308693 | 100% | 0 | 308693 | 0 | 2.624% | 100% |  | 150 |  |  | 100% | 100% | 100% | 100% | 0%
|  | Delivery | Kg | 308693 | 308693 | 100% | 0 | 308693 | 0 | 0.6559% | 100% |  | 1000 |  |  | 100% | 100% | 100% | 100% | 0%
|  | Piping Support | per | 0 | 0 | 100% | 0 | 0 | 0 | 0.934% | 100% |  | 100 |  |  | 100% | 85% | 85% | 85% | 0%
|  | PO Placement | Kg | 80000 | 80000 | 100% | 0 | 80000 | 0 | 0.2335% | 100% |  |  |  |  | 100% | 100% | 100% | 100% | 0%
|  | Fabrication & Test | Kg | 80000 | 80000 | 100% | 0 | 80000 | 0 | 0.5604% | 100% |  |  |  |  | 100% | 100% | 100% | 100% | 0%
|  | Delivery | Kg | 80000 | 80000 | 100% | 0 | 80000 | 0 | 0.1401% | 100% |  |  |  |  | 100% | 0% | 0% | 0% | 0%
|  | Cold Insulating | per | 0 | 0 | 0% | 0 | 0 | 0 | 0.7797% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0%
|  | PO Placement | m2 | 5862 | 0 | 0% | 0 | 0 | 5862 | 0.1949% | 0% |  |  |  |  | 0% | 0% | 0% | 0% | 0%
|  | Fabrication & Test | m2 | 5862 | 0 | 0% | 0 | 0 | 5862 | 0.4678% | 0% |  |  |  |  | 0% | 0% | 0% | 0% | 0%
|  | Delivery | m2 | 5862 | 0 | 0% | 0 | 0 | 5862 | 0.117% | 0% |  |  |  |  | 0% | 0% | 0% | 0% | 0%
|  | Warm Insulating | per | 0 | 0 | 0% | 0 | 0 | 0 | 0.5209% | 100% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0%
|  | PO Placement | m2 | 2937 | 0 | 0% | 2937 | 2937 | 0 | 0.1302% | 100% |  |  |  |  | 0% | 0% | 0% | 0% | 0%
|  | Fabrication & Test | m2 | 2937 | 0 | 0% | 2937 | 2937 | 0 | 0.3125% | 100% |  |  |  |  | 0% | 0% | 0% | 0% | 0%
|  | Delivery | m2 | 2937 | 0 | 0% | 2937 | 2937 | 0 | 0.07813% | 100% |  |  |  |  | 0% | 0% | 0% | 0% | 0%
|  | Paint | per | 0 | 0 | 100% | 0 | 0 | 0 | 5.56% | 100% | 13900 | 13900 |  |  | 100% | 80.58% | 80.58% | 80.58% | 0%
|  | PO Placement | Kg | 57000 | 57000 | 100% | 0 | 57000 | 0 | 4.17% | 100% |  |  |  |  | 100% | 100% | 100% | 100% | 0%
|  | Delivery | Kg | 57000 | 57000 | 100% | 0 | 57000 | 0 | 1.39% | 100% |  |  |  |  | 100% | 22.33% | 22.33% | 22.33% | 0%
|  | Electrode | per | 0 | 0 | 100% | 0 | 0 | 0 | 2.634% | 100% | 18080 | 18080 |  |  | 100% | 66.96% | 66.96% | 66.96% | 0%
|  | PO Placement | Kg | 27000 | 27000 | 100% | 0 | 27000 | 0 | 0.6584% | 100% |  |  |  |  | 100% | 66.96% | 66.96% | 66.96% | 0%
|  | Fabrication & Test | Kg | 27000 | 27000 | 100% | 0 | 27000 | 0 | 1.58% | 100% |  |  |  |  | 100% | 66.96% | 66.96% | 66.96% | 0%
|  | Delivery | Kg | 27000 | 27000 | 100% | 0 | 27000 | 0 | 0.3951% | 100% |  |  |  |  | 100% | 66.96% | 66.96% | 66.96% | 0%
|  | Plant Construction |  | 0 | 0 | 23.32% | 0 | 0 | 0 | 85% | 24.51% |  | 0 |  |  | 23.36% | 18.89% | 20.74% | 20.74% | 0% | 24.55% | 0%
|  | General |  | 0 | 0 | 48.85% | 0 | 0 | 0 | 3.599% | 59.93% |  | 0 | 2.157% |  | 47.49% | 47.49% | 49.66% | 49.66% | 0% | 0.49658 | 0%
|  | mobolization |  | 0 | 0 | 54.1% | 0 | 0 | 0 | 3.249% | 61% |  | 0 |  |  | 52.6% | 52.6% | 55% | 55% | 0% | 55% | 0%
|  | primary mobilozation | % | 100 | 100 | 100% | 0 | 100 | 0 | 1.3% | 100% | 100 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | countiuse mobilization | % | 100 | 35 | 23.5% | 0 | 35 | 65 | 1.95% | 35% | 27 | -8 |  |  | 21% | 21% | 25% | 21% | 4% | 25% | 0%
|  | Demobilizaton |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.3496% | 50% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Demobilizaton | % | 100 | 0 | 0% | 50 | 50 | 50 | 0.3496% | 50% |  | -50 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Gate House | civ | 0 | 0 | 25% | 0 | 0 | 0 | 0.6452% | 25% |  | 0 | 0.1613% |  | 25% | 20% | 25% | 25% | 0% | 25% | 0%
|  | civil | civ | 0 | 0 | 100% | 0 | 0 | 0 | 0.1613% | 100% |  | 0 |  |  | 100% | 80% | 100% | 100% | 0% | 100% | 0%
| ` | Foundation | % | 100 | 100 | 100% | 0 | 100 | 0 | 0.04839% | 100% | 100 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | columns | % | 100 | 100 | 100% | 0 | 100 | 0 | 0.04839% | 100% | 100 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Wall | % | 100 | 100 | 100% | 0 | 100 | 0 | 0.01613% | 100% |  | -100 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | Floor | % | 100 | 100 | 100% | 0 | 100 | 0 | 0.01613% | 100% |  | -100 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | Roof | % | 100 | 100 | 100% | 0 | 100 | 0 | 0.03226% | 100% | 95 | -5 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Mechanical | civ | 0 | 0 | 0% | 0 | 0 | 0 | 0.06452% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Piping | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.04516% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.01936% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | electrical | civ | 0 | 0 | 0% | 0 | 0 | 0 | 0.06452% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cabling | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.04516% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.01936% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | telecom | civ | 0 | 0 | 0% | 0 | 0 | 0 | 0.129% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | telecom | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.129% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | architect | civ | 0 | 0 | 0% | 0 | 0 | 0 | 0.1936% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | architect | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.1936% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | final works | civ | 0 | 0 | 0% | 0 | 0 | 0 | 0.03226% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | final works | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.03226% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Unit 140 |  | 0 | 0 | 33.16% | 0 | 0 | 0 | 43.74% | 34.61% |  | 0 | 15.14% |  | 33.21% | 27.04% | 30.87% | 30.87% | 0% | 33.38% | 0%
|  | Welding & NDT Procedures | pip | 0 | 0 | 31.04% | 0% | 0 | 0 | 2.527% | 30.4% |  | 0 |  |  | 30.2% | 30.2% | 33.8% | 33.8% | 0% | 39.21% | 0%
|  | Prepare and qualify welding procedures (welding procedures qualfication tests (WPQT) including lab. Tests) for structural and pipe welding | % | 100% | 100% | 100% | -72% | 28% | 72% | 0.01263% | 28% | 100 | 99.72 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Qualification of welders including lab testing for structural and pipe welding | % | 100% | 100% | 100% | -72% | 28% | 72% | 0.01263% | 28% | 100 | 99.72 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Qualification of welding equipment | % | 100% | 100% | 100% | -72% | 28% | 72% | 0.01263% | 28% | 100 | 99.72 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Maintaining welder qualification records | % | 100% | 100% | 100% | -72% | 28% | 72% | 0.01263% | 28% | 100 | 99.72 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Monitoring welder performance | % | 100% | 100% | 100% | -72% | 28% | 72% | 0.01263% | 28% | 100 | 99.72 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Prepare and NDT Procedures and obtain certification | % | 100% | 50% | 50% | -14% | 36% | 64% | 0.7581% | 36% |  | -0.36 |  |  | 50% | 50% | 55% | 50% | 5% | 50% | 0%
|  | Qualification of NDT equipment and dimensional control (UT, RT, MT,...) | % | 100% | 24% | 24% | 4% | 28% | 72% | 0.01263% | 28% |  | -0.28 |  |  | 20% | 20% | 30% | 20% | 10% | 25% | 0%
|  | Qualification of equipment operators for NDT and dimensional control | % | 100% | 24% | 24% | 4% | 28% | 72% | 0.01263% | 28% |  | -0.28 |  |  | 20% | 20% | 30% | 20% | 10% | 25% | 0%
|  | Perform NDT as per the procedures | % | 100% | 24% | 24% | 4% | 28% | 72% | 0.2022% | 28% |  | -0.28 |  |  | 20% | 20% | 30% | 20% | 10% | 25% | 0%
|  | Supply of associated Elec. Power, consumables, Materials construction equipments | % | 100% | 100% | 100% | -72% | 28% | 72% | 0.2022% | 28% | 100 | 99.72 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Prepare PWHT procedure and obtain certification | % | 100% | 0% | 0% | 28% | 28% | 72% | 0.6317% | 28% |  | -0.28 |  |  | 0% | 0% | 0% | 0% | 0% | 20% | 0%
|  | Perform PWHT testing | % | 100% | 0% | 0% | 28% | 28% | 72% | 0.3285% | 28% |  | -0.28 |  |  | 0% | 0% | 0% | 0% | 0% | 20% | 0%
|  | Provide and maintain secure storage for radioactive sources | % | 100% | 24% | 24% | 4% | 28% | 72% | 0.3032% | 28% |  | -0.28 |  |  | 20% | 20% | 30% | 20% | 10% | 28% | 0%
|  | Implement specific safety procedures relating to radioactive sources | % | 100% | 100% | 100% | -72% | 28% | 72% | 0.01263% | 28% | 100 | 99.72 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Civil | civ | 0 | 0 | 50.94% | 0 | 0 | 0 | 5.511% | 52.78% |  | 0 |  |  | 44.85% | 48.39% | 40.67% | 40.67% | 0% | 51.85% | 0%
|  | Plat Form |  | 0 | 0 | 75.85% | 0 | 0 | 0 | 2.567% | 78.97% |  | 0 |  |  | 68.14% | 81.47% | 68.17% | 68.17% | 0% | 77.77% | 0%
|  | West HP |  | 0 | 0 | 82.64% | 0 | 0 | 0 | 1.097% | 85.68% |  | 0 |  |  | 73.25% | 88.9% | 73.25% | 73.25% | 0% | 84.38% | 0%
|  | excavation | m3 | 1983 | 1765 | 89.01% | 0 | 1765 | 218 | 0.08773% | 89.01% | 1385 | -380 |  |  | 89.01% | 100% | 89.01% | 89.01% | 0% | 0.89007 | 0%
|  | level&compact | m2 | 851 | 705 | 82.84% | 0 | 705 | 146 | 0.02193% | 82.84% | 588 | -117 |  |  | 82.84% | 100% | 82.84% | 82.84% | 0% | 0.82844 | 0%
|  | lean | m3 | 36.57 | 32 | 87.5% | 0 | 32 | 4.57 | 0.01097% | 87.5% | 40 | 8 |  |  | 87.5% | 100% | 87.5% | 87.5% | 0% | 0.87503 | 0%
|  | footing rebar | Kg | 33778 | 29400 | 75% | 0 | 29400 | 4378 | 0.1535% | 87.04% | 25188 | -4212 |  |  | 8.491% | 100% | 8.491% | 8.491% | 0% | 0.87039 | 0%
|  | footing form | m2 | 309 | 246 | 79.61% | 0 | 246 | 63 | 0.1151% | 79.61% | 195 | -51 |  |  | 79.61% | 100% | 79.61% | 79.61% | 0% | 0.79612 | 0%
|  | foting concrete | m3 | 448 | 390 | 87.05% | 0 | 390 | 58 | 0.2303% | 87.05% | 343 | -47 |  |  | 87.05% | 100% | 87.05% | 87.05% | 0% | 0.87054 | 0%
|  | ped rebar | Kg | 22520 | 20892 | 92.77% | 0 | 20892 | 1628 | 0.0658% | 92.77% | 11666 | -9226 |  |  | 92.77% | 100% | 92.77% | 92.77% | 0% | 0.92771 | 0%
|  | ped form | m2 | 376 | 306 | 81.38% | 0 | 306 | 70 | 0.04935% | 81.38% | 225 | -81 |  |  | 81.38% | 100% | 81.38% | 81.38% | 0% | 0.81383 | 0%
|  | anchor | NO. | 418 | 335 | 79% | 0 | 335 | 83 | 0.05483% | 80.14% | 98 | -237 |  |  | 77.51% | 100% | 77.51% | 77.51% | 0% | 0.80144 | 0%
|  | ped concrete | m3 | 146 | 130 | 89.04% | 0 | 130 | 16 | 0.09869% | 89.04% | 12 | -118 |  |  | 89.04% | 95.04% | 89.04% | 89.04% | 0% | 0.89041 | 0%
|  | curing | % | 100 | 60 | 60% | 0 | 60 | 40 | 0.01097% | 60% | 75 | 15 |  |  | 60% | 85% | 60% | 60% | 0% | 0.6 | 0%
|  | coating | m2 | 1174 | 864 | 73.59% | 0 | 864 | 310 | 0.0329% | 73.59% | 400 | -464 |  |  | 73.59% | 85% | 73.59% | 73.59% | 0% | 0.73595 | 0%
|  | back fill | m3 | 1402 | 1240 | 88.45% | 0 | 1240 | 162 | 0.1097% | 88.45% | 0 | -1240 |  |  | 88.45% | 20% | 88.45% | 88.45% | 0% | 0.88445 | 0%
|  | Final Certificate | % | 100 | 60 | 60% | 26 | 86 | 14 | 0.05483% | 86% | 50 | -36 |  |  | 60% | 59% | 60% | 60% | 0% | 0.6 | 0%
|  | East HP |  | 0 | 0 | 82.72% | 0 | 0 | 0 | 1.078% | 86.93% |  | 0 |  |  | 73.91% | 86.36% | 73.91% | 73.91% | 0% | 85.53% | 0%
|  | excavation | m3 | 1983 | 1765 | 89.01% | 0 | 1765 | 218 | 0.08621% | 89.01% | 1358 | -407 |  |  | 89.01% | 100% | 89.01% | 89.01% | 0% | 89.01% | 0%
|  | level&compact | m2 | 845 | 705 | 83.43% | 0 | 705 | 140 | 0.02155% | 83.43% | 575 | -130 |  |  | 83.43% | 100% | 83.43% | 83.43% | 0% | 83.43% | 0%
|  | lean | m3 | 36 | 32 | 88.89% | 0 | 32 | 4 | 0.01078% | 88.89% | 39 | 7 |  |  | 88.89% | 100% | 88.89% | 88.89% | 0% | 88.89% | 0%
|  | footing rebar | Kg | 33471 | 29750 | 69% | 0 | 29750 | 3721 | 0.1509% | 88.88% | 26445 | -3305 |  |  | 8.569% | 100% | 8.569% | 8.569% | 0% | 88.88% | 0%
|  | footing form | m2 | 298 | 246 | 82.55% | 0 | 246 | 52 | 0.1132% | 82.55% | 200 | -46 |  |  | 82.55% | 100% | 82.55% | 82.55% | 0% | 82.55% | 0%
|  | foting concrete | m3 | 444 | 390 | 87.84% | 0 | 390 | 54 | 0.2263% | 87.84% | 358 | -32 |  |  | 87.84% | 100% | 87.84% | 87.84% | 0% | 87.84% | 0%
|  | ped rebar | Kg | 21315 | 20892 | 98.02% | 0 | 20892 | 423 | 0.06466% | 98.02% | 12103 | -8789 |  |  | 98.02% | 100% | 98.02% | 98.02% | 0% | 98.02% | 0%
|  | ped form | m2 | 389 | 306 | 78.66% | 0 | 306 | 83 | 0.04849% | 78.66% | 235 | -71 |  |  | 78.66% | 100% | 78.66% | 78.66% | 0% | 78.66% | 0%
|  | anchor | NO. | 420 | 324 | 77.14% | 0 | 324 | 96 | 0.05388% | 77.14% | 132 | -192 |  |  | 77.14% | 100% | 77.14% | 77.14% | 0% | 77.14% | 0%
|  | ped concrete | m3 | 146 | 130 | 89.04% | 0 | 130 | 16 | 0.09699% | 89.04% | 60 | -70 |  |  | 89.04% | 70.83% | 89.04% | 89.04% | 0% | 89.04% | 0%
|  | curing | % | 100 | 80 | 79% | 0 | 80 | 20 | 0.01078% | 80% | 60 | -20 |  |  | 60% | 85% | 60% | 60% | 0% | 80% | 0%
|  | coating | m2 | 1173 | 932 | 79% | 0 | 932 | 241 | 0.03233% | 79.45% | 500 | -432 |  |  | 73.66% | 70% | 73.66% | 73.66% | 0% | 79.45% | 0%
|  | back fill | m3 | 1406 | 1240 | 88.19% | 0 | 1240 | 166 | 0.1078% | 88.19% | 0 | -1240 |  |  | 88.19% | 22.32% | 88.19% | 88.19% | 0% | 88.19% | 0%
|  | Final Certificate | % | 100 | 60 | 60% | 28 | 88 | 12 | 0.05388% | 88% | 52 | -36 |  |  | 60% | 56% | 60% | 60% | 0% | 60% | 0%
|  | West LP |  | 0 | 0 | 73.72% | 0 | 0 | 0 | 0.1705% | 74.77% |  | 0 |  |  | 73.72% | 95.5% | 74.22% | 74.22% | 0% | 73.72% | 0%
|  | excavation | m3 | 397 | 325 | 81.86% | 0 | 325 | 72 | 0.01364% | 81.86% | 145 | -180 |  |  | 81.86% | 100% | 81.86% | 81.86% | 0% | 81.86% | 0%
|  | level&compact | m2 | 218 | 175 | 80.28% | 0 | 175 | 43 | 0.003411% | 80.28% | 99 | -76 |  |  | 80.28% | 100% | 80.28% | 80.28% | 0% | 80.28% | 0%
|  | lean | m3 | 7 | 5 | 71.43% | 0 | 5 | 2 | 0.001705% | 71.43% | 5 | 0 |  |  | 71.43% | 100% | 71.43% | 71.43% | 0% | 71.43% | 0%
|  | footing rebar | Kg | 7260 | 6154 | 84.77% | 0 | 6154 | 1106 | 0.02387% | 84.77% | 6702 | 548 |  |  | 84.77% | 100% | 84.77% | 84.77% | 0% | 84.77% | 0%
|  | footing form | m2 | 100 | 65 | 65% | 0 | 65 | 35 | 0.01791% | 65% | 71 | 6 |  |  | 65% | 100% | 65% | 65% | 0% | 65% | 0%
|  | foting concrete | m3 | 65 | 45 | 69.23% | 0 | 45 | 20 | 0.03581% | 69.23% | 18 | -27 |  |  | 69.23% | 100% | 69.23% | 69.23% | 0% | 69.23% | 0%
|  | ped rebar | Kg | 4840 | 3389 | 70.02% | 0 | 3389 | 1451 | 0.01023% | 70.02% | 2300 | -1089 |  |  | 70.02% | 100% | 70.02% | 70.02% | 0% | 70.02% | 0%
|  | ped form | m2 | 107 | 85 | 79.44% | 0 | 85 | 22 | 0.007674% | 79.44% | 41 | -44 |  |  | 79.44% | 100% | 79.44% | 79.44% | 0% | 79.44% | 0%
|  | anchor | NO. | 120 | 95 | 79.17% | 0 | 95 | 25 | 0.008526% | 79.17% | 29 | -66 |  |  | 79.17% | 100% | 79.17% | 79.17% | 0% | 79.17% | 0%
|  | ped concrete | m3 | 35 | 28 | 80% | 0 | 28 | 7 | 0.01535% | 80% | 21 | -7 |  |  | 80% | 90% | 80% | 80% | 0% | 80% | 0%
|  | curing | % | 100 | 60 | 60% | 0 | 60 | 40 | 0.001705% | 60% | 40 | -20 |  |  | 60% | 65% | 60% | 60% | 0% | 60% | 0%
|  | coating | m2 | 384 | 287 | 74.74% | 0 | 287 | 97 | 0.005116% | 74.74% | 0 | -287 |  |  | 74.74% | 100% | 74.74% | 74.74% | 0% | 74.74% | 0%
|  | back fill | m3 | 296 | 210 | 70.95% | 0 | 210 | 86 | 0.01705% | 70.95% | 0 | -210 |  |  | 70.95% | 90% | 70.95% | 70.95% | 0% | 70.95% | 0%
|  | Final Certificate | % | 100 | 55 | 55% | 21 | 76 | 24 | 0.008526% | 76% | 39 | -37 |  |  | 55% | 55% | 65% | 55% | 10% | 55% | 0%
|  | East LP |  | 0 | 0 | 10.75% | 0 | 0 | 0 | 0.2226% | 10.6% |  | 0 |  |  | 10.75% | 10.5% | 10.75% | 10.75% | 0% | 10.75% | 0%
|  | excavation | m3 | 397 | 397 | 100% | 0 | 397 | 0 | 0.01781% | 100% | 214 | -183 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | level&compact | m2 | 218 | 218 | 100% | 0 | 218 | 0 | 0.004453% | 100% | 138 | -80 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | lean | m3 | 7 | 0 | 0% | 0 | 0 | 7 | 0.002226% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | footing rebar | Kg | 7260 | 0 | 0% | 0 | 0 | 7260 | 0.03117% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | footing form | m2 | 102 | 0 | 0% | 0 | 0 | 102 | 0.02338% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | foting concrete | m3 | 65 | 0 | 0% | 0 | 0 | 65 | 0.04675% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | ped rebar | Kg | 4840 | 0 | 0% | 0 | 0 | 4840 | 0.01336% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | ped form | m2 | 107 | 0 | 0% | 0 | 0 | 107 | 0.01002% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | anchor | NO. | 120 | 0 | 0% | 0 | 0 | 120 | 0.01113% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | ped concrete | m3 | 35 | 0 | 0% | 0 | 0 | 35 | 0.02004% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | curing | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.002226% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | coating | m2 | 384 | 0 | 0% | 0 | 0 | 384 | 0.006679% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | back fill | m3 | 296 | 0 | 0% | 0 | 0 | 296 | 0.02226% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 15 | 15% | -3 | 12 | 88 | 0.01113% | 12% | 10 | -2 |  |  | 15% | 10% | 15% | 15% | 0% | 15% | 0%
|  | Retaining wall |  | 0 | 0 | 30.18% | 0 | 0 | 0 | 2.849% | 30.94% |  | 0 |  |  | 25.35% | 20.19% | 17.24% | 17.24% | 0% | 30.22% | 0%
|  | Retaining wall 7 |  | 0 | 0 | 10.2% | 0 | 0 | 0 | 1.902% | 10.6% |  | 0 |  |  | 4.2% | 4% | 8.2% | 8.2% | 0% | 10.2% | 0%
|  | excavation | m3 | 2750 | 2750 | 100% | 0 | 2750 | 0 | 0.1522% | 100% |  | -2750 |  |  | 50% | 50% | 100% | 50% | 50% | 100% | 0%
|  | level&compact | m2 | 275 | 275 | 100% | 0 | 275 | 0 | 0.03805% | 100% |  | -275 |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | lean | m3 | 46 | 0 | 0% | 0 | 0 | 46 | 0.01902% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | footing rebar | Kg | 54855 | 0 | 0% | 0 | 0 | 54855 | 0.2663% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | footing form | m2 | 200 | 0 | 0% | 0 | 0 | 200 | 0.1997% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | foting concrete | m3 | 400 | 0 | 0% | 0 | 0 | 400 | 0.3995% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Wall rebar | Kg | 18285 | 0 | 0% | 0 | 0 | 18285 | 0.1141% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Wall form | m2 | 760 | 0 | 0% | 0 | 0 | 760 | 0.08561% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Wall concrete | m3 | 370 | 0 | 0% | 0 | 0 | 370 | 0.2663% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | curing | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.01902% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | coating | m2 | 1206 | 0 | 0% | 0 | 0 | 1206 | 0.05707% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | back fill | m3 | 4000 | 0 | 0% | 0 | 0 | 4000 | 0.1902% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 4 | 4% | 8 | 12 | 88 | 0.09512% | 12% |  | -12 |  |  | 4% | 0% | 4% | 4% | 0% | 4% | 0%
|  | Retaining wall 9 |  | 0 | 0 | 93.25% | 0 | 0 | 0 | 0.2292% | 94.75% |  | 0 |  |  | 91.45% | 86% | 100% | 100% | 0% | 93.25% | 0%
|  | excavation | m3 | 316 | 316 | 100% | 0 | 316 | 0 | 0.01834% | 100% | 316 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | level&compact | m2 | 128 | 128 | 100% | 0 | 128 | 0 | 0.004584% | 100% | 128 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | lean | m3 | 4 | 4 | 100% | 0 | 4 | 0 | 0.002292% | 100% | 4 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | footing rebar | Kg | 10025 | 10025 | 100% | 0 | 10025 | 0 | 0.03209% | 100% | 10025 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | footing form | m2 | 45 | 45 | 100% | 0 | 45 | 0 | 0.02407% | 100% | 45 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | foting concrete | m3 | 58 | 58 | 100% | 0 | 58 | 0 | 0.04813% | 100% |  | -58 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Wall rebar | Kg | 10100 | 10100 | 100% | 0 | 10100 | 0 | 0.01375% | 100% |  | -10100 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Wall form | m2 | 195 | 195 | 100% | 0 | 195 | 0 | 0.01031% | 100% |  | -195 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Wall concrete | m3 | 56 | 56 | 100% | 0 | 56 | 0 | 0.03209% | 100% |  | -56 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | curing | % | 100 | 100 | 100% | 0 | 100 | 0 | 0.002292% | 100% |  | -100 |  |  | 65% | 65% | 100% | 65% | 35% | 100% | 0%
|  | coating | m2 | 145 | 145 | 100% | 0 | 145 | 0 | 0.006876% | 100% |  | -145 |  |  | 60% | 60% | 100% | 60% | 40% | 100% | 0%
|  | back fill | m3 | 166 | 83 | 50% | 0 | 83 | 83 | 0.02292% | 50% |  | -83 |  |  | 50% | 0% | 100% | 50% | 50% | 50% | 0%
|  | Final Certificate | % | 100 | 65 | 65% | 30 | 95 | 5 | 0.01146% | 95% | 20 | -75 |  |  | 60% | 51% | 100% | 60% | 40% | 65% | 0%
|  | Retaining wall 11 |  | 0 | 0 | 10.3% | 0 | 0 | 0 | 0.2292% | 10.6% |  | 0 |  |  | 3.5% | 0% | 6.418% | 6.418% | 0% | 10.3% | 0%
|  | excavation | m3 | 850 | 850 | 100% | 0 | 850 | 0 | 0.01834% | 100% |  | -850 |  |  | 40% | 0% | 76.47% | 40% | 36.47% | 100% | 0%
|  | level&compact | m2 | 55 | 55 | 100% | 0 | 55 | 0 | 0.004584% | 100% |  | -55 |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | lean | m3 | 3.4 | 0 | 0% | 0 | 0 | 3.4 | 0.002292% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | footing rebar | Kg | 8400 | 0 | 0% | 0 | 0 | 8400 | 0.03209% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | footing form | m2 | 50 | 0 | 0% | 0 | 0 | 50 | 0.02407% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | foting concrete | m3 | 73 | 0 | 0% | 0 | 0 | 73 | 0.04813% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Wall rebar | Kg | 2800 | 0 | 0% | 0 | 0 | 2800 | 0.01375% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Wall form | m2 | 159 | 0 | 0% | 0 | 0 | 159 | 0.01031% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Wall concrete | m3 | 76 | 0 | 0% | 0 | 0 | 76 | 0.03209% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | curing | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.002292% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | coating | m2 | 251 | 0 | 0% | 0 | 0 | 251 | 0.006876% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | back fill | m3 | 1500 | 0 | 0% | 0 | 0 | 1500 | 0.02292% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 6 | 6% | 6 | 12 | 88 | 0.01146% | 12% |  | -12 |  |  | 6% | 0% | 6% | 6% | 0% | 6% | 0%
|  | Retaining wall 12 |  | 0 | 0 | 98.25% | 0 | 0 | 0 | 0.3438% | 100% |  | 0 |  |  | 97.8% | 87.8% | 0% | 0% | 0% | 98.3% | 0%
|  | excavation | m3 | 316 | 316 | 100% | 0 | 316 | 0 | 0.0275% | 100% | 316 | 0 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | level&compact | m2 | 128 | 128 | 100% | 0 | 128 | 0 | 0.006876% | 100% | 128 | 0 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | lean | m3 | 5 | 5 | 100% | 0 | 5 | 0 | 0.003438% | 100% |  | -5 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | footing rebar | Kg | 10025 | 10025 | 100% | 0 | 10025 | 0 | 0.04813% | 100% |  | -10025 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | footing form | m2 | 45 | 45 | 100% | 0 | 45 | 0 | 0.0361% | 100% |  | -45 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | foting concrete | m3 | 50 | 50 | 100% | 0 | 50 | 0 | 0.0722% | 100% |  | -50 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | Wall rebar | Kg | 10100 | 10100 | 100% | 0 | 10100 | 0 | 0.02063% | 100% |  | -10100 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | Wall form | m2 | 195 | 195 | 100% | 0 | 195 | 0 | 0.01547% | 100% |  | -195 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | Wall concrete | m3 | 64 | 64 | 100% | 0 | 64 | 0 | 0.04813% | 100% |  | -64 |  |  | 100% | 100% | 0% | 100% | -100% | 100% | 0%
|  | curing | % | 100 | 100 | 100% | 0 | 100 | 0 | 0.003438% | 100% |  | -100 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | coating | m2 | 145 | 145 | 100% | 0 | 145 | 0 | 0.01031% | 100% |  | -145 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | back fill | m3 | 166 | 166 | 100% | 0 | 166 | 0 | 0.03438% | 100% |  | -166 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | Final Certificate | % | 100 | 66 | 65% | 34 | 100 | 0 | 0.01719% | 100% | 8 | -92 |  |  | 56% | 56% | 44% | 56% | -12% | 66% | 0%
|  | Retaining wall 13 |  | 0 | 0 | 62.86% | 0 | 0 | 0 | 0.1444% | 65.42% |  | 0 |  |  | 61.35% | 0% | 63.15% | 63.15% | 0% | 63.47% | 0%
|  | excavation | m3 | 600 | 600 | 100% | 0 | 600 | 0 | 0.01155% | 100% |  | -600 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | level&compact | m2 | 58 | 58 | 100% | 0 | 58 | 0 | 0.002888% | 100% |  | -58 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | lean | m3 | 2.6 | 2.6 | 100% | 0 | 2.6 | 0 | 0.001444% | 100% |  | -2.6 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | footing rebar | Kg | 6826 | 6826 | 100% | 0 | 6826 | 0 | 0.02022% | 100% |  | -6826 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | footing form | m2 | 29 | 29 | 100% | 0 | 29 | 0 | 0.01516% | 100% |  | -29 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | foting concrete | m3 | 35 | 35 | 100% | 0 | 35 | 0 | 0.03032% | 100% |  | -35 |  |  | 100% | 0% | 100% | 100% | 0% | 100% | 0%
|  | Wall rebar | Kg | 2275 | 1100 | 40% | 0 | 1100 | 1175 | 0.008664% | 48.35% |  | -1100 |  |  | 30% | 0% | 43.96% | 30% | 13.96% | 48.35% | 0%
|  | Wall form | m2 | 103 | 52 | 49% | 0 | 52 | 51 | 0.006498% | 50.49% |  | -52 |  |  | 30% | 0% | 51.46% | 30% | 21.46% | 50.49% | 0%
|  | Wall concrete | m3 | 28 | 0 | 0% | 0 | 0 | 28 | 0.02022% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | curing | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.001444% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | coating | m2 | 150 | 0 | 0% | 0 | 0 | 150 | 0.004332% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | back fill | m3 | 1000 | 0 | 0% | 0 | 0 | 1000 | 0.01444% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 36 | 35% | 39 | 75 | 25 | 0.00722% | 75% |  | -75 |  |  | 34% | 0% | 34% | 34% | 0% | 36% | 0%
|  | Base |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.095% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Base | m3 | 560 | 0 | 0% | 0 | 0 | 560 | 0.095% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Piping | pip | 0 | 0 | 23.17% | 0 | 0 | 0 | 19.52% | 23.03% |  | 0 |  |  | 18.14% | 11.33% | 20.72% | 20.72% | 0% | 21.68% | 0%
|  | AG Piping |  | 0 | 0 | 23.17% | 0 | 0 | 0 | 19.32% | 22.97% |  | 0 |  |  | 18.27% | 11.45% | 20.68% | 20.68% | 0% | 21.76% | 0%
|  | Shop |  | 0 | 0 | 26.86% | 0 | 0 | 0 | 6.763% | 23.83% |  | 0 |  |  | 17.51% | 4.93% | 22.53% | 22.53% | 0% | 23.41% | 0%
|  | Carbon Steel |  | 0 | 0 | 44.74% | 0 | 0 | 0 | 3.489% | 41.33% |  | 0 |  |  | 31.01% | 6.743% | 40.73% | 40.73% | 0% | 41.33% | 0%
|  | Material Handling From Lay down To Shop | ID | 42944 | 25598 | 59.61% | 0 | 25598 | 17346 | 0.1744% | 59.61% | 3390 | -22208 |  |  | 59.61% | 34.25% | 59.61% | 59.61% | 0% | 0.59608 | 0%
|  | Cutting & Bevelling & Fit Up | ID | 12883 | 6933 | 53.82% | 0 | 6933 | 5950 | 1.221% | 53.82% |  | -6933 |  |  | 53.82% | 4.06% | 53.82% | 53.82% | 0% | 53.82% | 0%
|  | Welding | ID | 12883 | 5800 | 56.91% | 0 | 5800 | 7083 | 1.221% | 45.02% |  | -5800 |  |  | 17.7% | 1.74% | 45.46% | 17.7% | 27.77% | 45.02% | 0%
|  | NDT | ID | 2576.6 | 17 | 0.1139% | -13.6 | 3.4 | 2573.2 | 0.1744% | 0.132% |  | -3.4 |  |  | 0% | 0% | 0% | 0% | 0% | 0.132% | 0%
|  | PWHT | ID | 12883 | 0 | 0% | 0 | 0 | 12883 | 0.1744% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 20% | 0 | 25 | 75 | 0.5233% | 25% | 20 | -5 |  |  | 20% | 20% | 20% | 20% | 0% | 25% | 0%
|  | Low Temperature CS |  | 0 | 0 | 10.92% | 0 | 0 | 0 | 1.993% | 5.165% |  | 0 |  |  | 3.224% | 3% | 3.224% | 3.224% | 0% | 5.165% | 0%
|  | Material Handling From Lay down To Shop | ID | 27889 | 1248 | 5.211% | 0 | 1248 | 26641 | 0.09967% | 4.475% |  | -1248 |  |  | 4.475% | 0% | 4.475% | 4.475% | 0% | 4.475% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 8367 | 232 | 11.31% | 0 | 232 | 8135 | 0.6977% | 2.773% |  | -232 |  |  | 0% | 0% | 0% | 0% | 0% | 2.773% | 0%
|  | Welding | ID | 8367 | 232 | 10.59% | 0 | 232 | 8135 | 0.6977% | 2.773% |  | -232 |  |  | 0% | 0% | 0% | 0% | 0% | 2.773% | 0%
|  | NDT | ID | 8367 | 0 | 0% | 0 | 0 | 8367 | 0.09967% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 1 | 0 | 0% | 0 | 0 | 1 | 0.09967% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 20 | 20% | 0 | 20 | 80 | 0.299% | 20% | 20 | 0 |  |  | 20% | 20% | 20% | 20% | 0% | 20% | 0%
|  | Stainless Steel |  | 0 | 0 | 3% | 0 | 0 | 0 | 1.167% | 3% |  | 0 |  |  | 3% | 3% | 3% | 3% | 0% | 3% | 0%
|  | Material Handling From Lay down To Shop | ID | 13845 | 0 | 0% | 0 | 0 | 13845 | 0.05833% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 4154 | 0 | 0% | 0 | 0 | 4154 | 0.4083% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 4154 | 0 | 0% | 0 | 0 | 4154 | 0.4083% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 4154 | 0 | 0% | 0 | 0 | 4154 | 0.05833% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 4154 | 0 | 0% | 0 | 0 | 4154 | 0.05833% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 20 | 20% | 0 | 20 | 80 | 0.175% | 20% | 20 | 0 |  |  | 20% | 20% | 20% | 20% | 0% | 20% | 0%
|  | Galva |  | 0 | 0 | 3% | 0 | 0 | 0 | 0.115% | 27.83% |  | 0 |  |  | 3% | 3% | 3% | 3% | 0% | 3% | 0%
|  | Material Handling From Lay down To Shop | ID | 2645 | 2645 | 0% | 0 | 2645 | 0 | 0.00575% | 100% |  | -2645 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 794 | 794 | 0% | -612.0417 | 181.9583 | 612.0417 | 0.04025% | 22.92% |  | -181.9583 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 794 | 794 | 0% | -612.0417 | 181.9583 | 612.0417 | 0.04025% | 22.92% |  | -181.9583 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 794 | 794 | 0% | -612.0417 | 181.9583 | 612.0417 | 0.00575% | 22.92% |  | -181.9583 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 794 | 794 | 0% | -612.0417 | 181.9583 | 612.0417 | 0.00575% | 22.92% |  | -181.9583 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 80 | 20% | -50 | 30 | 70 | 0.01725% | 30% | 20 | -10 |  |  | 20% | 20% | 20% | 20% | 0% | 20% | 0%
|  | Field |  | 0 | 0 | 21.19% | 0 | 0 | 0 | 12.56% | 22.51% |  | 0 |  |  | 18.68% | 14.96% | 19.68% | 19.68% | 0% | 20.87% | 0%
|  | Carbon Steel |  | 0 | 0 | 22.92% | 0 | 0 | 0 | 6.478% | 24.11% |  | 0 |  |  | 20.95% | 17.25% | 22.7% | 22.7% | 0% | 22.25% | 0%
|  | Material Handling From Shop To Field | ID | 42944 | 22000 | 15.55% | 0 | 22000 | 20944 | 0.3239% | 51.23% | 452 | -21548 |  |  | 13.99% | 7.94% | 13.99% | 13.99% | 0% | 13.99% | 0%
|  | Scaffolding | m2 | 8000 | 7349 | 91.86% | 0 | 7349 | 651 | 0.8422% | 91.86% | 2350 | -4999 |  |  | 91.86% | 83.08% | 91.86% | 91.86% | 0% | 91.86% | 0%
|  | Erection & Fit Up | ID | 30060 | 3619 | 12.49% | 0 | 3619 | 26441 | 1.231% | 12.04% | 452 | -3167 |  |  | 12.04% | 5.34% | 12.04% | 12.04% | 0% | 12.04% | 0%
|  | Valve Installation | ID | 280 | 0 | 0% | 0 | 0 | 280 | 0.3239% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 30060 | 2970 | 11.41% | 0 | 2970 | 27090 | 2.138% | 9.88% | 408 | -2562 |  |  | 6.128% | 3.16% | 11.41% | 6.128% | 5.286% | 9.88% | 0%
|  | NDT | ID | 6012 | 722 | 2.392% | -577.6 | 144.4 | 5867.6 | 0.162% | 2.402% |  | -144.4 |  |  | 0% | 0% | 0% | 0% | 0% | 2.402% | 0%
|  | PWHT | ID | 30060 | 0 | 0% | 0 | 0 | 30060 | 0.1944% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 30060 | 0 | 0% | 0 | 0 | 30060 | 0.6155% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.6478% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Low Temperature CS |  | 0 | 0 | 21.53% | 0 | 0 | 0 | 3.702% | 22.83% |  | 0 |  |  | 16.48% | 12.52% | 16.81% | 16.81% | 0% | 21.61% | 0%
|  | Material Handling From Shop To Field | ID | 27889 | 10000 | 12.02% | 0 | 10000 | 17889 | 0.1851% | 35.86% |  | -10000 |  |  | 1.778% | 0% | 1.778% | 1.778% | 0% | 11.47% | 0%
|  | Scaffolding | m2 | 8000 | 7349 | 91.86% | 0 | 7349 | 651 | 0.4813% | 91.86% | 2350 | -4999 |  |  | 91.86% | 65.56% | 91.86% | 91.86% | 0% | 91.86% | 0%
|  | Erection & Fit Up | ID | 19522 | 1864 | 9.341% | 0 | 1864 | 17658 | 0.7034% | 9.548% |  | -1864 |  |  | 1.967% | 0% | 1.967% | 1.967% | 0% | 9.548% | 0%
|  | Valve Installation | ID | 280 | 0 | 0% | 0 | 0 | 280 | 0.1851% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 19522 | 1864 | 9.341% | 0 | 1864 | 17658 | 1.222% | 9.548% |  | -1864 |  |  | 0.2254% | 0% | 1.229% | 0.2254% | 1.004% | 9.548% | 0%
|  | NDT | ID | 19522 | 1008 | 5.049% | 0 | 1008 | 18514 | 0.09255% | 5.163% |  | -1008 |  |  | 0% | 0% | 0% | 0% | 0% | 5.163% | 0%
|  | PWHT | ID | 19522 | 0 | 0% | 0 | 0 | 19522 | 0.1111% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 19522 | 0 | 0% | 0 | 0 | 19522 | 0.3517% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.3702% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Stainless Steel |  | 0 | 0 | 15.94% | 0 | 0 | 0 | 2.166% | 15.94% |  | 0 |  |  | 15.94% | 12.52% | 15.94% | 15.94% | 0% | 15.94% | 0%
|  | Material Handling From Shop To Field | ID | 13845 | 0 | 0% | 0 | 0 | 13845 | 0.1083% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Scaffolding | m2 | 8000 | 7349 | 91.86% | 0 | 7349 | 651 | 0.2816% | 91.86% | 2350 | -4999 |  |  | 91.86% | 65.56% | 91.86% | 91.86% | 0% | 91.86% | 0%
|  | Erection & Fit Up | ID | 9692 | 0 | 0% | 0 | 0 | 9692 | 0.4116% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 280 | 0 | 0% | 0 | 0 | 280 | 0.1083% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 9692 | 0 | 0% | 0 | 0 | 9692 | 0.7149% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 9692 | 0 | 0% | 0 | 0 | 9692 | 0.05416% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 9692 | 0 | 0% | 0 | 0 | 9692 | 0.06499% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 9692 | 0 | 0% | 0 | 0 | 9692 | 0.2058% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.2166% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Galva |  | 0 | 0 | 15.94% | 0 | 0 | 0 | 0.2136% | 35.27% |  | 0 |  |  | 15.94% | 12.52% | 15.94% | 15.94% | 0% | 15.94% | 0%
|  | Material Handling From Shop To Field | ID | 2645 | 2645 | 0% | 0 | 2645 | 0 | 0.01068% | 100% |  | -2645 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Scaffolding | m2 | 8000 | 7349 | 91.86% | 0 | 7349 | 651 | 0.02776% | 91.86% | 2350 | -4999 |  |  | 91.86% | 65.56% | 91.86% | 91.86% | 0% | 91.86% | 0%
|  | Erection & Fit Up | ID | 1852 | 1000 | 0% | -575.5833 | 424.4167 | 1427.5833 | 0.04058% | 22.92% |  | -424.4167 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 280 | 280 | 0% | -215.8333 | 64.1667 | 215.8333 | 0.01068% | 22.92% |  | -64.1667 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 1852 | 1000 | 0% | -575.5833 | 424.4167 | 1427.5833 | 0.07048% | 22.92% |  | -424.4167 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 1852 | 100 | 0% | 324.4167 | 424.4167 | 1427.5833 | 0.005339% | 22.92% |  | -424.4167 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 1852 | 100 | 0% | 324.4167 | 424.4167 | 1427.5833 | 0.006407% | 22.92% |  | -424.4167 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 1852 | 0 | 0% | 0 | 0 | 1852 | 0.02029% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 55 | 40% | -15 | 40 | 60 | 0.02136% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Pipe Support |  | 0 | 0 | 22.92% | 0 | 0 | 0 | 0.1995% | 27.97% |  | 0 |  |  | 5.257% | 0% | 24.55% | 24.55% | 0% | 14.32% | 0%
|  | Shop |  | 0 | 0 | 61.4% | 0 | 0 | 0 | 0.06982% | 69.05% |  | 0 |  |  | 11% | 0% | 66.13% | 66.13% | 0% | 20.48% | 0%
|  | Handling | Kg | 60354.4 | 43200 | 100% | 0 | 43200 | 17154.4 | 0.007681% | 71.58% |  | -43200 |  |  | 100% | 0% | 100% | 100% | 0% | 20.71% | 0%
|  | shop drawing | Kg | 60354.4 | 43200 | 60% | 0 | 43200 | 17154.4 | 0.01117% | 71.58% |  | -43200 |  |  | 0% | 0% | 0.2315% | 0% | 0.2315% | 20.71% | 0%
|  | Cutting & assembling | Kg | 60354.4 | 43200 | 60% | 0 | 43200 | 17154.4 | 0.01536% | 71.58% |  | -43200 |  |  | 0% | 0% | 81.02% | 0% | 81.02% | 20.71% | 0%
|  | Welding | Kg | 60354.4 | 43200 | 60% | 0 | 43200 | 17154.4 | 0.03212% | 71.58% |  | -43200 |  |  | 0% | 0% | 81.02% | 0% | 81.02% | 20.71% | 0%
|  | Final Certificate | % | 100 | 16 | 0% | 5 | 21 | 79 | 0.003491% | 21% |  | -21 |  |  | 0% | 0% | 0% | 0% | 0% | 16% | 0%
|  | Field |  | 0 | 0 | 2.2% | 0 | 0 | 0 | 0.1297% | 5.849% |  | 0 |  |  | 2.164% | 0% | 2.164% | 2.164% | 0% | 11% | 0%
|  | Material Handling From Shop To Field | Kg | 90531.6 | 43200 | 20% | 0 | 43200 | 47331.6 | 0.01426% | 47.72% |  | -43200 |  |  | 19.68% | 0% | 19.68% | 19.68% | 0% | 100% | 0%
|  | Erection | Kg | 90531.6 | 0 | 0% | 0 | 0 | 90531.6 | 0.02723% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | Kg | 90531.6 | 0 | 0% | 0 | 0 | 90531.6 | 0.06743% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | Kg | 90531.6 | 0 | 0% | 0 | 0 | 90531.6 | 0.01426% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 0 | 0% | 12 | 12 | 88 | 0.006484% | 12% |  | -12 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Painting & Sandblasting | pan | 0 | 0 | 12.47% | 0 | 0 | 0 | 2.557% | 19.52% |  | 0 |  |  | 7.621% | 7.621% | 3.266% | 3.266% | 0% | 16.02% | 0%
|  | Pipe |  | 0 | 0 | 12.6% | 0 | 0 | 0 | 2.531% | 19.73% |  | 0 |  |  | 7.7% | 7.7% | 3.3% | 3.3% | 0% | 16.19% | 0%
|  | Sand Blast | m2 | 39250 | 21000 | 36% | 0 | 21000 | 18250 | 0.3797% | 53.5% | 1886 | -19114 |  |  | 22% | 22% | 22% | 22% | 0% | 46.25% | 0%
|  | Primer | m2 | 39250 | 21000 | 36% | 0 | 21000 | 18250 | 0.5062% | 53.5% | 1886 | -19114 |  |  | 22% | 22% | 0% | 22% | -22% | 46.25% | 0%
|  | Middle Paint | m2 | 39250 | 0 | 0% | 0 | 0 | 39250 | 0.8859% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Paint | m2 | 39250 | 0 | 0% | 0 | 0 | 39250 | 0.5062% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Touch Up & Punch | m2 | 39250 | 0 | 0% | 0 | 0 | 39250 | 0.1266% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 3707%
|  | Final Certificate | % | 100 | 0 | 0% | 20 | 20 | 80 | 0.1266% | 20% |  | -20 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Support |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.02613% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Sand Blast | m2 | 800 | 0 | 0% | 0 | 0 | 800 | 0.00392% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Primer | m2 | 800 | 0 | 0% | 0 | 0 | 800 | 0.005226% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Middle Paint | m2 | 800 | 0 | 0% | 0 | 0 | 800 | 0.009146% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Paint | m2 | 800 | 0 | 0% | 0 | 0 | 800 | 0.005226% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Touch Up & Punch | m2 | 800 | 0 | 0% | 0 | 0 | 800 | 0.001307% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.001307% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Steel Structure | str | 0 | 0 | 81.29% | 0 | 0 | 0 | 7.466% | 86.6% |  | 0 |  |  | 80.68% | 80.2% | 84.12% | 84.12% | 0% | 81.81% | 0%
|  | Installation Steel Structure |  | 0 | 0 | 82.03% | 0 | 0 | 0 | 7.399% | 87.38% |  | 0 |  |  | 81.41% | 80.93% | 84.88% | 84.88% | 0% | 82.55% | 0%
|  | 140-IM-A1 |  | 0 | 0 | 94.84% | 0 | 0 | 0 | 0.2474% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 93233 | 93233 | 100% | 0 | 93233 | 0 | 0.02474% | 100% | 94004 | 771 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 14 | 14 | 100% | 0 | 14 | 0 | 0.01237% | 100% | 14 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 93233 | 93233 | 99.65% | 0 | 93233 | 0 | 0.09894% | 100% | 94004 | 771 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 93233 | 93233 | 99.65% | 0 | 93233 | 0 | 0.02968% | 100% | 94004 | 771 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 93233 | 93233 | 99.65% | 0 | 93233 | 0 | 0.01979% | 100% | 94004 | 771 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 14 | 14 | 100% | 0 | 14 | 0 | 0.02474% | 100% | 14 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.0371% | 100% | 62 | -38 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-A2 |  | 0 | 0 | 94.33% | 0 | 0 | 0 | 0.3595% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 135196 | 135196 | 98.97% | 0 | 135196 | 0 | 0.03595% | 100% | 136607 | 1411 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 14 | 14 | 100% | 0 | 14 | 0 | 0.01797% | 100% | 16 | 2 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 135196 | 135196 | 98.97% | 0 | 135196 | 0 | 0.1438% | 100% | 136607 | 1411 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 135196 | 135196 | 98.97% | 0 | 135196 | 0 | 0.04313% | 100% | 136607 | 1411 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 135196 | 135196 | 98.97% | 0 | 135196 | 0 | 0.02876% | 100% | 136607 | 1411 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 14 | 14 | 100% | 0 | 14 | 0 | 0.03595% | 100% | 16 | 2 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.05392% | 100% | 63 | -37 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-A3 |  | 0 | 0 | 94.62% | 0 | 0 | 0 | 0.2126% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 83004 | 83004 | 100% | 0 | 83004 | 0 | 0.02126% | 100% | 80800 | -2204 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 16 | 16 | 100% | 0 | 16 | 0 | 0.01063% | 100% | 16 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 83004 | 83004 | 99.28% | 0 | 83004 | 0 | 0.08504% | 100% | 80800 | -2204 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 83004 | 83004 | 99.28% | 0 | 83004 | 0 | 0.02551% | 100% | 80800 | -2204 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 83004 | 83004 | 99.28% | 0 | 83004 | 0 | 0.01701% | 100% | 80800 | -2204 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 16 | 16 | 100% | 0 | 16 | 0 | 0.02126% | 100% | 16 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.03189% | 100% | 63 | -37 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-A4 |  | 0 | 0 | 94.94% | 0 | 0 | 0 | 0.1649% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 62652 | 62652 | 100% | 0 | 62652 | 0 | 0.01649% | 100% | 62652 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 14 | 14 | 100% | 0 | 14 | 0 | 0.008243% | 100% | 14 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 62652 | 62652 | 99.82% | 0 | 62652 | 0 | 0.06594% | 100% | 62652 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 62652 | 62652 | 99.82% | 0 | 62652 | 0 | 0.01978% | 100% | 62652 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 62652 | 62652 | 99.82% | 0 | 62652 | 0 | 0.01319% | 100% | 62652 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 14 | 14 | 100% | 0 | 14 | 0 | 0.01649% | 100% | 14 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.02473% | 100% | 62 | -38 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-A5 |  | 0 | 0 | 95.05% | 0 | 0 | 0 | 0.4729% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 179726 | 179726 | 100% | 0 | 179726 | 0 | 0.04729% | 100% | 179726 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 32 | 32 | 100% | 0 | 32 | 0 | 0.02365% | 100% | 32 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 179726 | 179726 | 100% | 0 | 179726 | 0 | 0.1892% | 100% | 179726 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 179726 | 179726 | 100% | 0 | 179726 | 0 | 0.05675% | 100% | 179726 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 179726 | 179726 | 100% | 0 | 179726 | 0 | 0.03783% | 100% | 179726 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 32 | 32 | 100% | 0 | 32 | 0 | 0.04729% | 100% | 32 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.07094% | 100% | 64 | -36 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-A6& A6/1 |  | 0 | 0 | 91.56% | 0 | 0 | 0 | 0.3567% | 99.66% |  | 0 |  |  | 94.86% | 94.86% | 98.91% | 98.91% | 0% | 94.86% | 0%
|  | Handling | Kg | 160153 | 159708.8393 | 99.47% | 0 | 159708.8393 | 444.1607 | 0.03567% | 99.72% | 135200 | -24508.8393 |  |  | 99.72% | 99.72% | 99.72% | 99.72% | 0% | 99.72% | 0%
|  | Chip&Padding | NO | 85 | 85 | 100% | 0 | 85 | 0 | 0.01784% | 100% | 33 | -52 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 160153 | 159708.8393 | 96.52% | 0 | 159708.8393 | 444.1607 | 0.1427% | 99.72% | 135199 | -24509.8393 |  |  | 99.72% | 99.72% | 99.72% | 99.72% | 0% | 99.72% | 0%
|  | Alignment | Kg | 160153 | 159708.8393 | 93.52% | 0 | 159708.8393 | 444.1607 | 0.04281% | 99.72% | 135199 | -24509.8393 |  |  | 99.72% | 99.72% | 99.72% | 99.72% | 0% | 99.72% | 0%
|  | Bolt Tightening & Test | Kg | 160153 | 159708.8393 | 84.18% | 0 | 159708.8393 | 444.1607 | 0.02854% | 99.72% | 135199 | -24509.8393 |  |  | 99.72% | 99.72% | 99.72% | 99.72% | 0% | 99.72% | 0%
|  | Grouting | NO | 85 | 85 | 100% | 0 | 85 | 0 | 0.03567% | 100% | 33 | -52 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 32 | 99 | 1 | 0.05351% | 99% | 64 | -35 |  |  | 67% | 67% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-A7 |  | 0 | 0 | 11.5% | 0 | 0 | 0 | 0.1538% | 16.25% |  | 0 |  |  | 14% | 14% | 14.6% | 14.6% | 0% | 14% | 0%
|  | Handling | Kg | 58446 | 58446 | 100% | 0 | 58446 | 0 | 0.01538% | 100% | 58446 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 16 | 8 | 0% | 0 | 8 | 8 | 0.007689% | 50% | 8 | 0 |  |  | 50% | 50% | 50% | 50% | 0% | 50% | 0%
|  | Erection | Kg | 58446 | 0 | 0% | 0 | 0 | 58446 | 0.06152% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 58446 | 0 | 0% | 0 | 0 | 58446 | 0.01845% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Bolt Tightening & Test | Kg | 58446 | 0 | 0% | 0 | 0 | 58446 | 0.0123% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | NO | 16 | 0 | 0% | 0 | 0 | 16 | 0.01538% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final test & Documents | % | 100 | 10 | 10% | 15 | 25 | 75 | 0.02307% | 25% | 10 | -15 |  |  | 10% | 10% | 14% | 10% | 4% | 10% | 0%
|  | 140-IM-B1 |  | 0 | 0 | 9.6% | 0 | 0 | 0 | 0.1758% | 12.6% |  | 0 |  |  | 9.6% | 9.6% | 10.95% | 10.95% | 0% | 9.6% | 0%
|  | Handling | Kg | 65946 | 63311.1216 | 96% | 0 | 63311.1216 | 2634.8784 | 0.01758% | 96% | 64131 | 819.8784 |  |  | 96% | 96% | 96% | 96% | 0% | 96% | 0%
|  | Chip&Padding | NO | 10 | 0 | 0% | 0 | 0 | 10 | 0.008789% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection | Kg | 65946 | 0 | 0% | 0 | 0 | 65946 | 0.07031% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 65946 | 0 | 0% | 0 | 0 | 65946 | 0.02109% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Bolt Tightening & Test | Kg | 65946 | 0 | 0% | 0 | 0 | 65946 | 0.01406% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | NO | 10 | 0 | 0% | 0 | 0 | 10 | 0.01758% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final test & Documents | % | 100 | 0 | 0% | 20 | 20 | 80 | 0.02637% | 20% | 7 | -13 |  |  | 0% | 0% | 9% | 0% | 9% | 0% | 0%
|  | 140-IM-B2 |  | 0 | 0 | 9.944% | 0 | 0 | 0 | 0.4518% | 12.94% |  | 0 |  |  | 9.944% | 9.944% | 11.44% | 11.44% | 0% | 9.944% | 0%
|  | Handling | Kg | 171694 | 170741 | 99.44% | 0 | 170741 | 953 | 0.04518% | 99.44% | 170741 | 0 |  |  | 99.44% | 99.44% | 99.44% | 99.44% | 0% | 99.44% | 0%
|  | Chip&Padding | NO | 12 | 0 | 0% | 0 | 0 | 12 | 0.02259% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection | Kg | 171694 | 0 | 0% | 0 | 0 | 171694 | 0.1807% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 171694 | 0 | 0% | 0 | 0 | 171694 | 0.05421% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Bolt Tightening & Test | Kg | 171694 | 0 | 0% | 0 | 0 | 171694 | 0.03614% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | NO | 12 | 0 | 0% | 0 | 0 | 12 | 0.04518% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final test & Documents | % | 100 | 0 | 0% | 20 | 20 | 80 | 0.06777% | 20% | 7 | -13 |  |  | 0% | 0% | 10% | 0% | 10% | 0% | 0%
|  | 140-IM-B3 |  | 0 | 0 | 95.02% | 0 | 0 | 0 | 0.4453% | 100% |  | 0 |  |  | 95.05% | 93.7% | 98.95% | 98.95% | 0% | 95.05% | 0%
|  | Handling | Kg | 169239 | 169239 | 100% | 0 | 169239 | 0 | 0.04453% | 100% | 167795 | -1444 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 28 | 28 | 100% | 0 | 28 | 0 | 0.02227% | 100% | 28 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 169239 | 169239 | 100% | 0 | 169239 | 0 | 0.1781% | 100% | 167795 | -1444 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 169239 | 169239 | 100% | 0 | 169239 | 0 | 0.05344% | 100% | 167795 | -1444 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 169239 | 169239 | 99.6% | 0 | 169239 | 0 | 0.03563% | 100% | 0 | -169239 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 28 | 28 | 100% | 0 | 28 | 0 | 0.04453% | 100% | 0 | -28 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.0668% | 100% | 48 | -52 |  |  | 67% | 58% | 93% | 67% | 26% | 67% | 0%
|  | 140-IM-B4 |  | 0 | 0 | 94.96% | 0 | 0 | 0 | 0.3028% | 99.79% |  | 0 |  |  | 94.99% | 94.39% | 99.04% | 99.04% | 0% | 94.99% | 0%
|  | Handling | Kg | 115066 | 115066 | 100% | 0 | 115066 | 0 | 0.03028% | 100% | 115066 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 20 | 20 | 100% | 0 | 20 | 0 | 0.01514% | 100% | 20 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 115066 | 114950.6 | 99.85% | 0 | 114950.6 | 115.4 | 0.1211% | 99.9% | 113646 | -1304.6 |  |  | 99.9% | 99.9% | 99.9% | 99.9% | 0% | 99.9% | 0%
|  | Alignment | Kg | 115066 | 114951 | 99.85% | 0 | 114951 | 115 | 0.03633% | 99.9% | 113646 | -1305 |  |  | 99.9% | 99.9% | 99.9% | 99.9% | 0% | 99.9% | 0%
|  | Bolt Tightening & Test | Kg | 115066 | 114951 | 99.85% | 0 | 114951 | 115 | 0.02422% | 99.9% | 113646 | -1305 |  |  | 99.9% | 99.9% | 99.9% | 99.9% | 0% | 99.9% | 0%
|  | Grouting | NO | 20 | 20 | 100% | 0 | 20 | 0 | 0.03028% | 100% | 20 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 32 | 99 | 1 | 0.04542% | 99% | 62 | -37 |  |  | 67% | 63% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-B5 |  | 0 | 0 | 94.99% | 0 | 0 | 0 | 0.1895% | 99.79% |  | 0 |  |  | 94.72% | 94.12% | 98.77% | 98.77% | 0% | 94.99% | 0%
|  | Handling | Kg | 72007 | 72007 | 100% | 0 | 72007 | 0 | 0.01895% | 100% | 72293 | 286 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 10 | 10 | 100% | 0 | 10 | 0 | 0.009473% | 100% | 10 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 72007 | 71935 | 99.9% | 0 | 71935 | 72 | 0.07579% | 99.9% | 72293 | 358 |  |  | 99.45% | 99.45% | 99.45% | 99.45% | 0% | 99.9% | 0%
|  | Alignment | Kg | 72007 | 71935 | 99.9% | 0 | 71935 | 72 | 0.02274% | 99.9% | 72293 | 358 |  |  | 99.45% | 99.45% | 99.45% | 99.45% | 0% | 99.9% | 0%
|  | Bolt Tightening & Test | Kg | 72007 | 71935 | 99.9% | 0 | 71935 | 72 | 0.01516% | 99.9% | 72293 | 358 |  |  | 99.45% | 99.45% | 99.45% | 99.45% | 0% | 99.9% | 0%
|  | Grouting | NO | 10 | 10 | 100% | 0 | 10 | 0 | 0.01895% | 100% | 10 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 32 | 99 | 1 | 0.02842% | 99% | 62 | -37 |  |  | 67% | 63% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-B6 |  | 0 | 0 | 94.93% | 0 | 0 | 0 | 0.4257% | 99.77% |  | 0 |  |  | 94.97% | 94.37% | 99.02% | 99.02% | 0% | 94.97% | 0%
|  | Handling | Kg | 161771 | 161771 | 100% | 0 | 161771 | 0 | 0.04257% | 100% | 161544 | -227 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 26 | 26 | 100% | 0 | 26 | 0 | 0.02128% | 100% | 26 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 161771 | 161544.3 | 99.8% | 0 | 161544.3 | 226.7 | 0.1703% | 99.86% | 161544 | -0.3 |  |  | 99.86% | 99.86% | 99.86% | 99.86% | 0% | 99.86% | 0%
|  | Alignment | Kg | 161771 | 161544 | 99.8% | 0 | 161544 | 227 | 0.05108% | 99.86% | 161544 | 0 |  |  | 99.86% | 99.86% | 99.86% | 99.86% | 0% | 99.86% | 0%
|  | Bolt Tightening & Test | Kg | 161771 | 161544 | 99.8% | 0 | 161544 | 227 | 0.03405% | 99.86% | 161544 | 0 |  |  | 99.86% | 99.86% | 99.86% | 99.86% | 0% | 99.86% | 0%
|  | Grouting | NO | 26 | 26 | 100% | 0 | 26 | 0 | 0.04257% | 100% | 26 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 32 | 99 | 1 | 0.06385% | 99% | 62 | -37 |  |  | 67% | 63% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-B7 |  | 0 | 0 | 94.79% | 0 | 0 | 0 | 0.2262% | 99.78% |  | 0 |  |  | 94.98% | 94.38% | 99.03% | 99.03% | 0% | 94.98% | 0%
|  | Handling | Kg | 85977 | 85977 | 100% | 0 | 85977 | 0 | 0.02262% | 100% | 85857 | -120 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.01131% | 100% | 12 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 85977 | 85876.7 | 99.56% | 0 | 85876.7 | 100.3 | 0.09049% | 99.88% | 83375 | -2501.7 |  |  | 99.88% | 99.88% | 99.88% | 99.88% | 0% | 99.88% | 0%
|  | Alignment | Kg | 85977 | 85877 | 99.56% | 0 | 85877 | 100 | 0.02715% | 99.88% | 83375 | -2502 |  |  | 99.88% | 99.88% | 99.88% | 99.88% | 0% | 99.88% | 0%
|  | Bolt Tightening & Test | Kg | 85977 | 85877 | 99.56% | 0 | 85877 | 100 | 0.0181% | 99.88% | 83375 | -2502 |  |  | 99.88% | 99.88% | 99.88% | 99.88% | 0% | 99.88% | 0%
|  | Grouting | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.02262% | 100% | 12 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 32 | 99 | 1 | 0.03393% | 99% | 61 | -38 |  |  | 67% | 63% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-B8 |  | 0 | 0 | 94.87% | 0 | 0 | 0 | 0.2579% | 99.67% |  | 0 |  |  | 94.87% | 94.57% | 98.92% | 98.92% | 0% | 94.87% | 0%
|  | Handling | Kg | 98013 | 98013 | 100% | 0 | 98013 | 0 | 0.02579% | 100% | 97681 | -332 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.0129% | 100% | 12 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 98013 | 97714 | 99.69% | 0 | 97714 | 299 | 0.1032% | 99.69% | 97320 | -394 |  |  | 99.69% | 99.69% | 99.69% | 99.69% | 0% | 99.69% | 0%
|  | Alignment | Kg | 98013 | 97714 | 99.69% | 0 | 97714 | 299 | 0.03095% | 99.69% | 97320 | -394 |  |  | 99.69% | 99.69% | 99.69% | 99.69% | 0% | 99.69% | 0%
|  | Bolt Tightening & Test | Kg | 98013 | 97714 | 99.69% | 0 | 97714 | 299 | 0.02063% | 99.69% | 97320 | -394 |  |  | 99.69% | 99.69% | 99.69% | 99.69% | 0% | 99.69% | 0%
|  | Grouting | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.02579% | 100% | 12 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 32 | 99 | 1 | 0.03869% | 99% | 62 | -37 |  |  | 67% | 65% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-B9 |  | 0 | 0 | 95.05% | 0 | 0 | 0 | 0.1566% | 100% |  | 0 |  |  | 95.05% | 94.45% | 99.1% | 99.1% | 0% | 95.05% | 0%
|  | Handling | Kg | 59041 | 59041 | 100% | 0 | 59041 | 0 | 0.01566% | 100% | 59500 | 459 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 8 | 8 | 100% | 0 | 8 | 0 | 0.007828% | 100% | 8 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 59041 | 59041 | 100% | 0 | 59041 | 0 | 0.06262% | 100% | 59500 | 459 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 59041 | 59041 | 100% | 0 | 59041 | 0 | 0.01879% | 100% | 59500 | 459 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 59041 | 59041 | 100% | 0 | 59041 | 0 | 0.01252% | 100% | 59500 | 459 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 8 | 8 | 100% | 0 | 8 | 0 | 0.01566% | 100% | 8 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.02348% | 100% | 62 | -38 |  |  | 67% | 63% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-B10 |  | 0 | 0 | 68.1% | 0 | 0 | 0 | 0.2676% | 80.49% |  | 0 |  |  | 74.79% | 73.89% | 77.94% | 77.94% | 0% | 74.79% | 0%
|  | Handling | Kg | 101233 | 101233 | 100% | 0 | 101233 | 0 | 0.02676% | 100% | 101700 | 467 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.01338% | 100% | 12 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 101233 | 80030.8083 | 66.18% | 0 | 80030.8083 | 21202.1917 | 0.107% | 79.06% | 80400 | 369.1917 |  |  | 79.06% | 79.06% | 79.06% | 79.06% | 0% | 79.06% | 0%
|  | Alignment | Kg | 101233 | 80030.8083 | 66.18% | 0 | 80030.8083 | 21202.1917 | 0.03211% | 79.06% | 80400 | 369.1917 |  |  | 79.06% | 79.06% | 79.06% | 79.06% | 0% | 79.06% | 0%
|  | Bolt Tightening & Test | Kg | 101233 | 63898.2298 | 63.12% | 0 | 63898.2298 | 37334.7702 | 0.02141% | 63.12% | 0 | -63898.2298 |  |  | 63.12% | 63.12% | 63.12% | 63.12% | 0% | 63.12% | 0%
|  | Grouting | NO | 12 | 7 | 58.33% | 0 | 7 | 5 | 0.02676% | 58.33% | 0 | -7 |  |  | 58.33% | 58.33% | 58.33% | 58.33% | 0% | 58.33% | 0%
|  | Final test & Documents | % | 100 | 52 | 52% | 38 | 90 | 10 | 0.04014% | 90% | 42 | -48 |  |  | 52% | 46% | 73% | 52% | 21% | 52% | 0%
|  | 140-IM-B11 |  | 0 | 0 | 94.69% | 0 | 0 | 0 | 0.3757% | 100% |  | 0 |  |  | 95.05% | 94.45% | 99.1% | 99.1% | 0% | 95.05% | 0%
|  | Handling | Kg | 142969 | 142969 | 100% | 0 | 142969 | 0 | 0.03757% | 100% | 142783 | -186 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 24 | 24 | 100% | 0 | 24 | 0 | 0.01879% | 100% | 24 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 142969 | 142969 | 99.41% | 0 | 142969 | 0 | 0.1503% | 100% | 142783 | -186 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 142969 | 142969 | 99.41% | 0 | 142969 | 0 | 0.04508% | 100% | 142783 | -186 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 142969 | 142969 | 99.41% | 0 | 142969 | 0 | 0.03006% | 100% | 142783 | -186 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 24 | 24 | 100% | 0 | 24 | 0 | 0.03757% | 100% | 24 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.05636% | 100% | 57 | -43 |  |  | 67% | 63% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-B12 |  | 0 | 0 | 62.41% | 0 | 0 | 0 | 0.2155% | 70% |  | 0 |  |  | 62.5% | 61.15% | 64.15% | 64.15% | 0% | 62.5% | 0%
|  | Handling | Kg | 81227 | 81227 | 100% | 0 | 81227 | 0 | 0.02155% | 100% | 81169 | -58 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 6 | 6 | 100% | 0 | 6 | 0 | 0.01078% | 100% | 6 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 81227 | 81227 | 99.78% | 0 | 81227 | 0 | 0.0862% | 100% | 81000 | -227 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 81227 | 0 | 0% | 0 | 0 | 81227 | 0.02586% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Bolt Tightening & Test | Kg | 81227 | 0 | 0% | 0 | 0 | 81227 | 0.01724% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | NO | 6 | 0 | 0% | 0 | 0 | 6 | 0.02155% | 0% | 0 | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final test & Documents | % | 100 | 50 | 50% | 50 | 100 | 0 | 0.03233% | 100% | 41 | -59 |  |  | 50% | 41% | 61% | 50% | 11% | 50% | 0%
|  | 140-IM-B13 |  | 0 | 0 | 68.5% | 0 | 0 | 0 | 0.3027% | 73.18% |  | 0 |  |  | 47.36% | 46.01% | 48.26% | 48.26% | 0% | 67.18% | 0%
|  | Handling | Kg | 115037 | 115037 | 100% | 0 | 115037 | 0 | 0.03027% | 100% | 114739 | -298 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 14 | 14 | 100% | 0 | 14 | 0 | 0.01513% | 100% | 14 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 115037 | 77582 | 67.09% | 0 | 77582 | 37455 | 0.1211% | 67.44% | 75656 | -1926 |  |  | 65.9% | 65.9% | 65.9% | 65.9% | 0% | 67.44% | 0%
|  | Alignment | Kg | 115037 | 77582 | 67.09% | 0 | 77582 | 37455 | 0.03632% | 67.44% | 0 | -77582 |  |  | 0% | 0% | 0% | 0% | 0% | 67.44% | 0%
|  | Bolt Tightening & Test | Kg | 115037 | 77582 | 67.09% | 0 | 77582 | 37455 | 0.02422% | 67.44% | 0 | -77582 |  |  | 0% | 0% | 0% | 0% | 0% | 67.44% | 0%
|  | Grouting | NO | 14 | 8 | 50% | 0 | 8 | 6 | 0.03027% | 57.14% | 0 | -8 |  |  | 0% | 0% | 0% | 0% | 0% | 57.14% | 0%
|  | Final test & Documents | % | 100 | 40 | 55% | 40 | 80 | 20 | 0.0454% | 80% | 31 | -49 |  |  | 40% | 31% | 46% | 40% | 6% | 40% | 0%
|  | 140-IM-C1 |  | 0 | 0 | 93.62% | 0 | 0 | 0 | 0.08789% | 100% |  | 0 |  |  | 95.05% | 93.4% | 98.95% | 98.95% | 0% | 95.05% | 0%
|  | Handling | Kg | 34919 | 34919 | 100% | 0 | 34919 | 0 | 0.008789% | 100% | 33400 | -1519 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.004394% | 100% | 12 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 34919 | 34919 | 97.62% | 0 | 34919 | 0 | 0.03515% | 100% | 33400 | -1519 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 34919 | 34919 | 97.62% | 0 | 34919 | 0 | 0.01055% | 100% | 0 | -34919 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 34919 | 34919 | 97.62% | 0 | 34919 | 0 | 0.007031% | 100% | 0 | -34919 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.008789% | 100% | 0 | -12 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.01318% | 100% | 41 | -59 |  |  | 67% | 56% | 93% | 67% | 26% | 67% | 0%
|  | 140-IM-C2 |  | 0 | 0 | 95.05% | 0 | 0 | 0 | 0.1658% | 100% |  | 0 |  |  | 95.05% | 94.45% | 99.1% | 99.1% | 0% | 95.05% | 0%
|  | Handling | Kg | 63237 | 63237 | 100% | 0 | 63237 | 0 | 0.01658% | 100% | 63000 | -237 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 22 | 22 | 100% | 0 | 22 | 0 | 0.008289% | 100% | 22 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 63237 | 63237 | 100% | 0 | 63237 | 0 | 0.06631% | 100% | 61847 | -1390 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 63237 | 63237 | 100% | 0 | 63237 | 0 | 0.01989% | 100% | 0 | -63237 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 63237 | 63237 | 100% | 0 | 63237 | 0 | 0.01326% | 100% | 0 | -63237 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 22 | 22 | 100% | 0 | 22 | 0 | 0.01658% | 100% | 0 | -22 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.02487% | 100% | 41 | -59 |  |  | 67% | 63% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-C3 |  | 0 | 0 | 95.05% | 0 | 0 | 0 | 0.08368% | 100% |  | 0 |  |  | 95.05% | 94.45% | 99.1% | 99.1% | 0% | 95.05% | 0%
|  | Handling | Kg | 32631 | 32631 | 100% | 0 | 32631 | 0 | 0.008368% | 100% | 31800 | -831 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.004184% | 100% | 12 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 32631 | 32631 | 100% | 0 | 32631 | 0 | 0.03347% | 100% | 31800 | -831 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 32631 | 32631 | 100% | 0 | 32631 | 0 | 0.01004% | 100% | 0 | -32631 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 32631 | 32631 | 100% | 0 | 32631 | 0 | 0.006694% | 100% | 0 | -32631 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 12 | 12 | 100% | 0 | 12 | 0 | 0.008368% | 100% | 0 | -12 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.01255% | 100% | 41 | -59 |  |  | 67% | 63% | 94% | 67% | 27% | 67% | 0%
|  | 140-IM-D1 |  | 0 | 0 | 94.95% | 0 | 0 | 0 | 0.1514% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 57553 | 57553 | 100% | 0 | 57553 | 0 | 0.01514% | 100% | 57553 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 18 | 18 | 100% | 0 | 18 | 0 | 0.007572% | 100% | 18 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 57553 | 57553 | 99.83% | 0 | 57553 | 0 | 0.06058% | 100% | 57553 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 57553 | 57553 | 99.83% | 0 | 57553 | 0 | 0.01817% | 100% | 57553 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 57553 | 57553 | 99.83% | 0 | 57553 | 0 | 0.01212% | 100% | 57533 | -20 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 18 | 18 | 100% | 0 | 18 | 0 | 0.01514% | 100% | 18 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.02272% | 100% | 61 | -39 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-D2 |  | 0 | 0 | 95.05% | 0 | 0 | 0 | 0.1342% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 51015 | 51015 | 100% | 0 | 51015 | 0 | 0.01342% | 100% | 50938 | -77 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 16 | 16 | 100% | 0 | 16 | 0 | 0.006712% | 100% | 16 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 51015 | 51015 | 100% | 0 | 51015 | 0 | 0.05369% | 100% | 50588 | -427 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 51015 | 51015 | 100% | 0 | 51015 | 0 | 0.01611% | 100% | 50588 | -427 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 51015 | 51015 | 100% | 0 | 51015 | 0 | 0.01074% | 100% | 50588 | -427 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 16 | 16 | 100% | 0 | 16 | 0 | 0.01342% | 100% | 16 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.02014% | 100% | 62 | -38 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-D3 |  | 0 | 0 | 94.03% | 0 | 0 | 0 | 0.178% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 67658 | 67658 | 100% | 0 | 67658 | 0 | 0.0178% | 100% | 67658 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 26 | 26 | 100% | 0 | 26 | 0 | 0.008901% | 100% | 26 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 67658 | 67658 | 98.31% | 0 | 67658 | 0 | 0.07121% | 100% | 67658 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 67658 | 67658 | 98.31% | 0 | 67658 | 0 | 0.02136% | 100% | 67658 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 67658 | 67658 | 98.31% | 0 | 67658 | 0 | 0.01424% | 100% | 67658 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 26 | 26 | 100% | 0 | 26 | 0 | 0.0178% | 100% | 26 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.0267% | 100% | 61 | -39 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-D4 |  | 0 | 0 | 94.7% | 0 | 0 | 0 | 0.1544% | 100% |  | 0 |  |  | 95.05% | 93.4% | 98.95% | 98.95% | 0% | 95.05% | 0%
|  | Handling | Kg | 58695 | 58695 | 100% | 0 | 58695 | 0 | 0.01544% | 100% | 58695 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 18 | 18 | 100% | 0 | 18 | 0 | 0.007722% | 100% | 18 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 58695 | 58695 | 99.42% | 0 | 58695 | 0 | 0.06178% | 100% | 58695 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 58695 | 58695 | 99.42% | 0 | 58695 | 0 | 0.01853% | 100% | 0 | -58695 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 58695 | 58695 | 99.42% | 0 | 58695 | 0 | 0.01236% | 100% | 0 | -58695 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 18 | 18 | 100% | 0 | 18 | 0 | 0.01544% | 100% | 0 | -18 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.02317% | 100% | 41 | -59 |  |  | 67% | 56% | 93% | 67% | 26% | 67% | 0%
|  | 140-IM-E1 |  | 0 | 0 | 78% | 0 | 0 | 0 | 0.1329% | 82.5% |  | 0 |  |  | 73.17% | 72.12% | 75.72% | 75.72% | 0% | 77.25% | 0%
|  | Handling | Kg | 53769 | 53769 | 100% | 0 | 53769 | 0 | 0.01329% | 100% | 50500 | -3269 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 20 | 20 | 100% | 0 | 20 | 0 | 0.006644% | 100% | 20 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 53769 | 43069.5014 | 80.1% | 0 | 43069.5014 | 10699.4986 | 0.05315% | 80.1% | 35264 | -7805.5014 |  |  | 80.1% | 80.1% | 80.1% | 80.1% | 0% | 80.1% | 0%
|  | Alignment | Kg | 53769 | 40221 | 74.8% | 0 | 40221 | 13548 | 0.01595% | 74.8% | 0 | -40221 |  |  | 59.41% | 59.41% | 59.41% | 59.41% | 0% | 74.8% | 0%
|  | Bolt Tightening & Test | Kg | 53769 | 40221 | 74.8% | 0 | 40221 | 13548 | 0.01063% | 74.8% | 0 | -40221 |  |  | 59.41% | 59.41% | 59.41% | 59.41% | 0% | 74.8% | 0%
|  | Grouting | NO | 20 | 14 | 70% | 0 | 14 | 6 | 0.01329% | 70% | 0 | -14 |  |  | 60% | 60% | 60% | 60% | 0% | 70% | 0%
|  | Final test & Documents | % | 100 | 55 | 60% | 35 | 90 | 10 | 0.01993% | 90% | 40 | -50 |  |  | 55% | 48% | 72% | 55% | 17% | 55% | 0%
|  | 140-IM-E2 |  | 0 | 0 | 95.05% | 0 | 0 | 0 | 0.1702% | 100% |  | 0 |  |  | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 64679 | 64679 | 100% | 0 | 64679 | 0 | 0.01702% | 100% | 64431 | -248 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 26 | 26 | 100% | 0 | 26 | 0 | 0.008509% | 100% | 26 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 64679 | 64679 | 100% | 0 | 64679 | 0 | 0.06808% | 100% | 63845 | -834 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 64679 | 64679 | 100% | 0 | 64679 | 0 | 0.02042% | 100% | 63845 | -834 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 64679 | 64679 | 100% | 0 | 64679 | 0 | 0.01362% | 100% | 63845 | -834 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 26 | 26 | 100% | 0 | 26 | 0 | 0.01702% | 100% | 26 | 0 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.02553% | 100% | 62 | -38 |  |  | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | 140-IM-E3 |  | 0 | 0 | 94.75% | 0 | 0 | 0 | 0.1053% | 100% |  | 0 |  |  | 80.38% | 79.18% | 83.23% | 83.23% | 0% | 94% | 0%
|  | Handling | Kg | 38933 | 38933 | 100% | 0 | 38933 | 0 | 0.01053% | 100% | 38834 | -99 |  | 75.87% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 16 | 16 | 100% | 0 | 16 | 0 | 0.005263% | 100% | 16 | 0 |  | 82.85% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 38933 | 38933 | 100% | 0 | 38933 | 0 | 0.0421% | 100% | 37088 | -1845 |  | 87.36% | 98.81% | 98.81% | 98.81% | 98.81% | 0% | 100% | 0%
|  | Alignment | Kg | 38933 | 38933 | 100% | 0 | 38933 | 0 | 0.01263% | 100% | 37088 | -1845 |  | 83.84% | 98.81% | 98.81% | 98.81% | 98.81% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 38933 | 38933 | 100% | 0 | 38933 | 0 | 0.00842% | 100% | 37088 | -1845 |  | 82.2% | 62.5% | 62.5% | 62.5% | 62.5% | 0% | 100% | 0%
|  | Grouting | NO | 16 | 16 | 100% | 0 | 16 | 0 | 0.01053% | 100% | 0 | -16 |  | 10.5% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 60 | 65% | 40 | 100 | 0 | 0.01579% | 100% | 52 | -48 |  | 95.05% | 60% | 52% | 79% | 60% | 19% | 60% | 0%
|  | 140-IM-E4 |  | 0 | 0 | 94.75% | 0 | 0 | 0 | 0.03736% | 100% |  | 0 |  | 95% | 84.23% | 83.03% | 87.38% | 87.38% | 0% | 94.3% | 0%
|  | Handling | Kg | 14165 | 14165 | 100% | 0 | 14165 | 0 | 0.003736% | 100% | 14200 | 35 |  | 95% | 99.75% | 99.75% | 99.75% | 99.75% | 0% | 100% | 0%
|  | Chip&Padding | NO | 6 | 6 | 100% | 0 | 6 | 0 | 0.001868% | 100% | 6 | 0 |  | 95% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 14165 | 14165 | 100% | 0 | 14165 | 0 | 0.01495% | 100% | 14200 | 35 |  | 95% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 14165 | 14165 | 100% | 0 | 14165 | 0 | 0.004484% | 100% | 14200 | 35 |  | 95% | 99.75% | 99.75% | 99.75% | 99.75% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 14165 | 14165 | 100% | 0 | 14165 | 0 | 0.002989% | 100% | 14200 | 35 |  | 14% | 99.75% | 99.75% | 99.75% | 99.75% | 0% | 100% | 0%
|  | Grouting | NO | 6 | 6 | 100% | 0 | 6 | 0 | 0.003736% | 100% | 0 | -6 |  | 11% | 0% | 0% | 0% | 0% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 62 | 65% | 38 | 100 | 0 | 0.005605% | 100% | 54 | -46 |  | 11% | 62% | 54% | 83% | 62% | 21% | 62% | 0%
|  | 140-IM-F1 |  | 0 | 0 | 62.5% | 0 | 0 | 0 | 0.0942% | 66.25% |  | 0 |  | 95% | 63.25% | 62.2% | 64.3% | 64.3% | 0% | 63.25% | 0%
|  | Handling | Kg | 36958 | 36958 | 100% | 0 | 36958 | 0 | 0.00942% | 100% | 35800 | -1158 |  | 95% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 18 | 18 | 100% | 0 | 18 | 0 | 0.00471% | 100% | 20 | 2 |  | 95% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 36958 | 36958 | 98.12% | 0 | 36958 | 0 | 0.03768% | 100% | 34945 | -2013 |  | 95% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 36958 | 0 | 0% | 0 | 0 | 36958 | 0.0113% | 0% | 0 | 0 |  | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Bolt Tightening & Test | Kg | 36958 | 0 | 0% | 0 | 0 | 36958 | 0.007536% | 0% | 0 | 0 |  | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | NO | 18 | 0 | 0% | 0 | 0 | 18 | 0.00942% | 0% | 0 | 0 |  | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final test & Documents | % | 100 | 55 | 55% | 20 | 75 | 25 | 0.01413% | 75% | 48 | -27 |  | 79% | 55% | 48% | 62% | 55% | 7% | 55% | 0%
|  | 140-IM-F2 |  | 0 | 0 | 95.01% | 0 | 0 | 0 | 0.1429% | 100% |  | 0 |  | 95% | 95.05% | 95.05% | 99.25% | 99.25% | 0% | 95.05% | 0%
|  | Handling | Kg | 57287 | 57287 | 100% | 0 | 57287 | 0 | 0.01429% | 100% | 54300 | -2987 |  | 68% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Chip&Padding | NO | 22 | 22 | 100% | 0 | 22 | 0 | 0.007144% | 100% | 22 | 0 |  | 50% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Erection | Kg | 57287 | 57287 | 99.93% | 0 | 57287 | 0 | 0.05715% | 100% | 54300 | -2987 |  | 93% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Alignment | Kg | 57287 | 57287 | 99.93% | 0 | 57287 | 0 | 0.01715% | 100% | 0 | -57287 |  | 95% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Bolt Tightening & Test | Kg | 57287 | 57287 | 99.93% | 0 | 57287 | 0 | 0.01143% | 100% | 0 | -57287 |  | 95% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Grouting | NO | 22 | 22 | 100% | 0 | 22 | 0 | 0.01429% | 100% | 0 | -22 |  | 95% | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Final test & Documents | % | 100 | 67 | 67% | 33 | 100 | 0 | 0.02143% | 100% | 55 | -45 |  | 95% | 67% | 67% | 95% | 67% | 28% | 67% | 0%
|  | Fireproofing |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.06706% | 0% |  | 0 |  | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Fireproofing | m2 | 200 | 0 | 0% | 0 | 0 | 200 | 0.06706% | 0% |  | 0 |  | 94% | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Insulation | ins | 0 | 0 | 0% | 0 | 0 | 0 | 0.212% | 0% |  | 0 |  | 82% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cold Insulation | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.106% | 0% |  | 0 |  | 95% | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hot Insulation | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.106% | 0% |  | 0 |  | 80% | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Equipment Packages | equ | 0 | 0 | 0% | 0 | 0 | 0 | 5.941% | 0% |  | 0 |  | 83% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Static Equipment |  | 0 | 0 | 0% | 0 | 0 | 0 | 3.268% | 0% |  | 0 |  | 83% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP FLARE 140-X-101 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.7275% | 0% |  | 0 |  | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.2546% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.1091% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.1091% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.1455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP FLARE 140-X-201 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.7275% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.2546% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.1091% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.1091% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.1455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LP FLARE 140-X-102 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.08424% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.004212% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.004212% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.02948% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01264% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01264% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01685% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.004212% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LP FLARE 140-X-202 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.08424% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.004212% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.004212% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.02948% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01264% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01264% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01685% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.004212% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MP FLARE 140-X-103 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.7275% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.2546% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.1091% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.1091% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.1455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MP FLARE 140-X-203 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.7275% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.2546% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.1091% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.1091% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.1455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Wet Flare K.O. Drum Heater 140-DH-101 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0009343% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.000327% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001869% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Wet Flare K.O. Drum Heater 140-DH-103 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0009343% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.000327% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001869% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Cold Flare K.O. Drum Heater 140-DH-104 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0009534% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 4.767e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.767e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0003337% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.000143% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.000143% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001907% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.767e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Wet Flare K.O. Drum Heater 140-DH-201 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0009343% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.000327% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001869% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MP Flare K.O. Drum Heater 140-DH-203 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0009343% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.000327% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001869% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.671e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Cold Flare K.O. Drum Heater 140-DH-204 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0009534% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 4.767e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.767e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0003337% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.000143% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.000143% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001907% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 4.767e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Flare Stack K.O. Drum Heater 140-DH-105 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.04595% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01608% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.006892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.006892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.00919% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Flare Stack K.O. Drum Heater 140-DH-106 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.04595% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01608% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.006892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.006892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.00919% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Flare Stack K.O. Drum Heater 140-DH-205 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.04595% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01608% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.006892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.006892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.00919% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP Flare Stack K.O. Drum Heater 140-DH-206 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.04595% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01608% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.006892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.006892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.00919% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.002297% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Rotary Equipment |  | 0 | 0 | 0% | 0 | 0 | 0 | 2.673% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP FLARE STACKS PUMPS, 140-P-104A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP FLARE STACKS PUMPS, 140-P-104B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LP FLARE STACKS PUMPS, 140-P-105A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LP FLARE STACKS PUMPS, 140-P-105B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MP FLARE STACKS PUMPS, 140-P-106A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MP FLARE STACKS PUMPS, 140-P-106B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP FLARE STACKS PUMPS, 140-P-204A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HP FLARE STACKS PUMPS, 140-P-204B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LP FLARE STACKS PUMPS, 140-P-205A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LP FLARE STACKS PUMPS, 140-P-205B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MP FLARE STACKS PUMPS, 140-P-206A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MP FLARE STACKS PUMPS, 140-P-206B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2227% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.07796% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.03341% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation | Kg | 1 | 0 | 0% | 0 | 0 | 1 | 0.04455% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.01114% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Unit 143 |  | 0 | 0 | 13.88% | 0 | 0 | 0 | 15.14% | 13.45% |  | 0 | 2.037% |  | 13.34% | 8.298% | 7.646% | 7.646% | 0% | 14.02% | 0%
|  | Welding & NDT Procedures | pip | 0 | 0 | 45.2% | 0 | 0 | 0 | 1.15% | 29.6% |  | 0 |  |  | 45.2% | 45.2% | 23.8% | 23.8% | 0% | 50.9% | 0%
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100% | 100% | 100% | -74% | 26% | 74% | 0.00575% | 26% | 100 | 99.74 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100% | 100% | 100% | -74% | 26% | 74% | 0.00575% | 26% | 100 | 99.74 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Qualification of Welding Equipments | % | 100% | 100% | 100% | -74% | 26% | 74% | 0.00575% | 26% | 100 | 99.74 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Maintaining Welder Qualification Records | % | 100% | 100% | 100% | -74% | 26% | 74% | 0.00575% | 26% | 100 | 99.74 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Monitoring Welder Performance | % | 100% | 100% | 100% | -74% | 26% | 74% | 0.00575% | 26% | 100 | 99.74 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Prepare NDT Procedures & Obtain Certification | % | 100% | 50% | 100% | -12% | 38% | 62% | 0.345% | 38% |  | -0.38 |  |  | 100% | 100% | 50% | 100% | -50% | 100% | 0%
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100% | 24% | 20% | 2% | 26% | 74% | 0.00575% | 26% |  | -0.26 |  |  | 20% | 20% | 20% | 20% | 0% | 20% | 0%
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100% | 24% | 20% | 2% | 26% | 74% | 0.00575% | 26% |  | -0.26 |  |  | 20% | 20% | 20% | 20% | 0% | 20% | 0%
|  | Perform NDT as per the Procedures | % | 100% | 24% | 20% | 2% | 26% | 74% | 0.092% | 26% |  | -0.26 |  |  | 20% | 20% | 20% | 20% | 0% | 20% | 0%
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100% | 100% | 100% | -74% | 26% | 74% | 0.092% | 26% | 100 | 99.74 |  |  | 100% | 100% | 20% | 100% | -80% | 100% | 0%
|  | Prepare PWHT Procedures & Obtain Certification | % | 100% | 0% | 0% | 26% | 26% | 74% | 0.2875% | 26% |  | -0.26 |  |  | 0% | 0% | 0% | 0% | 0% | 15% | 0%
|  | Perform PWHT Testing | % | 100% | 0% | 0% | 26% | 26% | 74% | 0.1495% | 26% |  | -0.26 |  |  | 0% | 0% | 0% | 0% | 0% | 15% | 0%
|  | Provide and maintain secure storage for radioactive sources | % | 100% | 24% | 20% | 2% | 26% | 74% | 0.138% | 26% |  | -0.26 |  |  | 20% | 20% | 20% | 20% | 0% | 20% | 0%
|  | Implement specific safety procedures relating to radioactive sources | % | 100% | 100% | 100% | -74% | 26% | 74% | 0.00575% | 26% | 100 | 99.74 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Piping | pip | 0 | 0 | 15.79% | 0 | 0 | 0 | 8.885% | 16.92% |  | 0 |  |  | 11.67% | 6.369% | 7.674% | 7.674% | 0% | 15.28% | 0%
|  | AG Piping |  | 0 | 0 | 15.95% | 0 | 0 | 0 | 8.794% | 17.09% |  | 0 |  |  | 11.79% | 6.435% | 7.753% | 7.753% | 0% | 15.44% | 0%
|  | Shop |  | 0 | 0 | 32.08% | 0 | 0 | 0 | 3.078% | 32.49% |  | 0 |  |  | 24.05% | 10.43% | 10.43% | 10.43% | 0% | 30.07% | 0%
|  | Carbon Steel |  | 0 | 0 | 45.62% | 0 | 0 | 0 | 2.083% | 46.22% |  | 0 |  |  | 33.75% | 13.63% | 13.63% | 13.63% | 0% | 42.66% | 0%
|  | Material Handling From Lay down To Shop | ID | 26984 | 17000 | 51.76% | 0 | 17000 | 9984 | 0.1041% | 63% | 2000 | -15000 |  |  | 51.76% | 24.24% | 24.24% | 51.76% | -27.52% | 51.76% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 8095 | 4200 | 60.35% | 0 | 4200 | 3895 | 0.7289% | 51.88% |  | -4200 |  |  | 50.29% | 12.94% | 12.94% | 50.29% | -37.35% | 51.88% | 0%
|  | Welding | ID | 8095 | 4200 | 51.88% | 0 | 4200 | 3895 | 0.7289% | 51.88% |  | -4200 |  |  | 28.02% | 11.82% | 11.82% | 28.02% | -16.2% | 51.88% | 0%
|  | NDT | ID | 1619 | 0 | 0% | 0 | 0 | 1619 | 0.1041% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 8095 | 0 | 0% | 0 | 0 | 8095 | 0.1041% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 20 | 45 | 55 | 0.3124% | 45% | 25 | -20 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | Low Temperature CS |  | 0 | 0 | 3.75% | 0 | 0 | 0 | 0.3407% | 3.75% |  | 0 |  |  | 3.75% | 3.75% | 3.75% | 3.75% | 0% | 3.75% | 0%
|  | Material Handling From Lay down To Shop | ID | 93 | 0 | 0% | 0 | 0 | 93 | 0.01704% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 28 | 0 | 0% | 0 | 0 | 28 | 0.1193% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 28 | 0 | 0% | 0 | 0 | 28 | 0.1193% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 28 | 0 | 0% | 0 | 0 | 28 | 0.01704% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 28 | 0 | 0% | 0 | 0 | 28 | 0.01704% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 0.05111% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | Stainless Steel |  | 0 | 0 | 3.75% | 0 | 0 | 0 | 0.0001235% | 3.75% |  | 0 |  |  | 3.75% | 3.75% | 3.75% | 3.75% | 0% | 3.75% | 0%
|  | Material Handling From Lay down To Shop | ID | 41 | 0 | 0% | 0 | 0 | 41 | 6.173e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 12 | 0 | 0% | 0 | 0 | 12 | 4.321e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 12 | 0 | 0% | 0 | 0 | 12 | 4.321e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 12 | 0 | 0% | 0 | 0 | 12 | 6.173e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 12 | 0 | 0% | 0 | 0 | 12 | 6.173e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 1.852e-05% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | Galva |  | 0 | 0 | 3.75% | 0 | 0 | 0 | 0.1825% | 3.75% |  | 0 |  |  | 3.75% | 3.75% | 3.75% | 3.75% | 0% | 3.75% | 0%
|  | Material Handling From Lay down To Shop | ID | 1971 | 0 | 0% | 0 | 0 | 1971 | 0.009123% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 591 | 0 | 0% | 0 | 0 | 591 | 0.06386% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 591 | 0 | 0% | 0 | 0 | 591 | 0.06386% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 591 | 0 | 0% | 0 | 0 | 591 | 0.009123% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 591 | 0 | 0% | 0 | 0 | 591 | 0.009123% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 0.02737% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | CU-NI |  | 0 | 0 | 3.75% | 0 | 0 | 0 | 0.472% | 3.75% |  | 0 |  |  | 3.75% | 3.75% | 3.75% | 3.75% | 0% | 3.75% | 0%
|  | Material Handling From Lay down To Shop | ID | 5256 | 0 | 0% | 0 | 0 | 5256 | 0.0236% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 1577 | 0 | 0% | 0 | 0 | 1577 | 0.1652% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 1577 | 0 | 0% | 0 | 0 | 1577 | 0.1652% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 1577 | 0 | 0% | 0 | 0 | 1577 | 0.0236% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 1577 | 0 | 0% | 0 | 0 | 1577 | 0.0236% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 0.07081% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | Field |  | 0 | 0 | 7.269% | 0 | 0 | 0 | 5.716% | 8.803% |  | 0 |  |  | 5.188% | 4.281% | 6.31% | 6.31% | 0% | 7.559% | 0%
|  | Carbon Steel |  | 0 | 0 | 9.549% | 0 | 0 | 0 | 3.868% | 11.64% |  | 0 |  |  | 6.473% | 5.133% | 8.131% | 8.131% | 0% | 9.355% | 0%
|  | Material Handling From Shop To Field | ID | 26984 | 14000 | 23.72% | 0 | 14000 | 12984 | 0.2223% | 51.88% | 1072 | -12928 |  |  | 10.7% | 5.89% | 10.7% | 10.7% | 0% | 23.72% | 0%
|  | Erection & Fit Up | ID | 18889 | 1942 | 13.34% | 0 | 1942 | 16947 | 0.8446% | 10.28% | 756 | -1186 |  |  | 9.672% | 6.06% | 9.672% | 9.672% | 0% | 10.28% | 0%
|  | Valve Installation | ID | 380 | 0 | 0% | 0 | 0 | 380 | 0.2223% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 18889 | 1342 | 9.882% | 378 | 1720 | 17169 | 1.467% | 9.106% | 756 | -964 |  |  | 4.632% | 3.41% | 9.656% | 4.632% | 5.024% | 7.105% | 0%
|  | NDT | ID | 3777.8 | 540 | 2.668% | -432 | 108 | 3669.8 | 0.1111% | 2.859% |  | -108 |  |  | 2.859% | 2.462% | 2.859% | 2.859% | 0% | 2.859% | 0%
|  | PWHT | ID | 18889 | 0 | 0% | 0 | 0 | 18889 | 0.1334% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 18889 | 0 | 0% | 0 | 0 | 18889 | 0.4223% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 0.4446% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | Low Temperature CS |  | 0 | 0 | 2.5% | 0 | 0 | 0 | 0.6328% | 2.874% |  | 0 |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 0% | 3.8% | 0%
|  | Material Handling From Shop To Field | ID | 93 | 0 | 0% | 0 | 0 | 93 | 0.03637% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fit Up | ID | 65 | 0 | 0% | 0 | 0 | 65 | 0.1382% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 380 | 0 | 0% | 0 | 0 | 380 | 0.03637% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 65 | 0 | 0% | 0 | 0 | 65 | 0.24% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 65 | 0 | 0% | 0 | 0 | 65 | 0.01818% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 65 | 0 | 0% | 0 | 0 | 65 | 0.02182% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 65 | 0 | 0% | 0 | 0 | 65 | 0.0691% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 0.07274% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | Stainless Steel |  | 0 | 0 | 2.5% | 0 | 0 | 0 | 0.0002293% | 2.874% |  | 0 |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 0% | 3.8% | 0%
|  | Material Handling From Shop To Field | ID | 41 | 0 | 0% | 0 | 0 | 41 | 1.318e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fit Up | ID | 29 | 0 | 0% | 0 | 0 | 29 | 5.007e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 380 | 0 | 0% | 0 | 0 | 380 | 1.318e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 29 | 0 | 0% | 0 | 0 | 29 | 8.697e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 29 | 0 | 0% | 0 | 0 | 29 | 6.588e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 29 | 0 | 0% | 0 | 0 | 29 | 7.906e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 29 | 0 | 0% | 0 | 0 | 29 | 2.504e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 2.635e-05% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | Galva |  | 0 | 0 | 2.5% | 0 | 0 | 0 | 0.3389% | 2.874% |  | 0 |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 0% | 3.8% | 0%
|  | Material Handling From Shop To Field | ID | 1971 | 0 | 0% | 0 | 0 | 1971 | 0.01948% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fit Up | ID | 1380 | 0 | 0% | 0 | 0 | 1380 | 0.07401% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 381 | 0 | 0% | 0 | 0 | 381 | 0.01948% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 1380 | 0 | 0% | 0 | 0 | 1380 | 0.1285% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 1380 | 0 | 0% | 0 | 0 | 1380 | 0.009738% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 1380 | 0 | 0% | 0 | 0 | 1380 | 0.01169% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 1380 | 0 | 0% | 0 | 0 | 1380 | 0.037% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 0.03895% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | CU-NI |  | 0 | 0 | 2.5% | 0 | 0 | 0 | 0.8766% | 2.874% |  | 0 |  |  | 2.5% | 2.5% | 2.5% | 2.5% | 0% | 3.8% | 0%
|  | Material Handling From Shop To Field | ID | 5256 | 0 | 0% | 0 | 0 | 5256 | 0.05038% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fit Up | ID | 3679 | 0 | 0% | 0 | 0 | 3679 | 0.1914% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 380 | 0 | 0% | 0 | 0 | 380 | 0.05038% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 3679 | 0 | 0% | 0 | 0 | 3679 | 0.3325% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 3679 | 0 | 0% | 0 | 0 | 3679 | 0.02519% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 3679 | 0 | 0% | 0 | 0 | 3679 | 0.03023% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 3679 | 0 | 0% | 0 | 0 | 3679 | 0.09572% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 25 | 25% | 0 | 25 | 75 | 0.1008% | 25% | 25 | 0 |  |  | 25% | 25% | 25% | 25% | 0% | 25% | 0%
|  | Pipe Support |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.09079% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Shop |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.03178% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Handling | Kg | 26579 | 0 | 0% | 0 | 0 | 26579 | 0.003495% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | shop drawing | Kg | 26579 | 0 | 0% | 0 | 0 | 26579 | 0.005084% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & assembling | Kg | 26579 | 0 | 0% | 0 | 0 | 26579 | 0.006991% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | Kg | 26579 | 0 | 0% | 0 | 0 | 26579 | 0.01462% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.001589% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Field |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.05901% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling From Shop To Field | Kg | 39869 | 0 | 0% | 0 | 0 | 39869 | 0.006491% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection | Kg | 39869 | 0 | 0% | 0 | 0 | 39869 | 0.01239% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | Kg | 39869 | 0 | 0% | 0 | 0 | 39869 | 0.03069% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | Kg | 39869 | 0 | 0% | 0 | 0 | 39869 | 0.006491% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.002951% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Painting & Sandblasting | pan | 0 | 0 | 15.4% | 0 | 0 | 0 | 1.164% | 16.64% |  | 0 |  |  | 15.4% | 14.69% | 17.39% | 17.39% | 0% | 15.4% | 0%
|  | Pipe |  | 0 | 0 | 15.56% | 0 | 0 | 0 | 1.152% | 16.81% |  | 0 |  |  | 15.56% | 14.84% | 17.57% | 17.57% | 0% | 15.56% | 0%
|  | Sand Blast | m2 | 11000 | 4891 | 44.46% | 0 | 4891 | 6109 | 0.1728% | 44.46% | 3480 | -1411 |  |  | 44.46% | 42.4% | 52.38% | 44.46% | 7.918% | 44.46% | 0%
|  | Primer | m2 | 11000 | 4891 | 44.46% | 0 | 4891 | 6109 | 0.2304% | 44.46% | 3480 | -1411 |  |  | 44.46% | 42.4% | 48.56% | 44.46% | 4.1% | 44.46% | 0%
|  | Middle Paint | m2 | 11000 | 0 | 0% | 0 | 0 | 11000 | 0.4032% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Paint | m2 | 11000 | 0 | 0% | 0 | 0 | 11000 | 0.2304% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Touch Up & Punch | m2 | 11000 | 0 | 0% | 0 | 0 | 11000 | 0.05759% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 0 | 0% | 25 | 25 | 75 | 0.05759% | 25% |  | -25 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Support |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01189% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Sand Blast | m2 | 400 | 0 | 0% | 0 | 0 | 400 | 0.001784% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Primer | m2 | 400 | 0 | 0% | 0 | 0 | 400 | 0.002378% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Middle Paint | m2 | 400 | 0 | 0% | 0 | 0 | 400 | 0.004162% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Paint | m2 | 400 | 0 | 0% | 0 | 0 | 400 | 0.002378% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Touch Up & Punch | m2 | 400 | 0 | 0% | 0 | 0 | 400 | 0.0005946% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 400 | 0 | 0% | 0 | 0 | 400 | 0.0005946% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Insulation | ins | 0 | 0 | 0% | 0 | 0 | 0 | 0.09649% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cold Insulation | M2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.04825% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hot Insulation | M2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.04825% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Equipment Packages | equ | 0 | 0 | 0% | 0 | 0 | 0 | 3.848% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Static Equipment |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.2516% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Sump Drum 143-D-101 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.1962% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.009808% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.009808% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.06866% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.02942% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.02942% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03923% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.009808% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Degassing Boot 143-D-102 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.05541% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00277% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00277% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01939% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.008311% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.008311% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01108% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00277% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Rotary Equipment |  | 0 | 0 | 0% | 0 | 0 | 0 | 3.597% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 143-P-101 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.5136% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.02568% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.02568% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1798% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.07705% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.07705% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1027% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.02568% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 143-P-102 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.9399% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.329% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.141% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.141% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.188% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 143-P-103 A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.6093% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.2133% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0914% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0914% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1219% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 143-P-103 B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.6093% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.2133% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0914% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0914% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1219% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 143-P-103 C |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.6093% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.2133% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0914% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0914% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1219% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 143-P-104 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.3151% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01575% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01575% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1103% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.04726% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.04726% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.06301% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01575% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Unit 147/148 |  | 0 | 0 | 5.938% | 0 | 0 | 0 | 21.87% | 6.148% |  | 0 | 1.345% |  | 6.569% | 5.205% | 4.673% | 4.673% | 0% | 10.04% | 0%
|  | Welding & NDT Procedures | pip | 0 | 0 | 45.2% | 0 | 0 | 0 | 1.323% | 20.1% |  | 0 |  |  | 45.2% | 45.2% | 33.8% | 33.8% | 0% | 50.14% | 0%
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100% | 100% | 100% | -85% | 15% | 85% | 0.006615% | 15% | 100 | 99.85 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100% | 100% | 100% | -85% | 15% | 85% | 0.006615% | 15% | 100 | 99.85 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Qualification of Welding Equipments | % | 100% | 100% | 100% | -85% | 15% | 85% | 0.006615% | 15% | 100 | 99.85 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Maintaining Welder Qualification Records | % | 100% | 100% | 100% | -85% | 15% | 85% | 0.006615% | 15% | 100 | 99.85 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Monitoring Welder Performance | % | 100% | 100% | 100% | -85% | 15% | 85% | 0.006615% | 15% | 100 | 99.85 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Prepare NDT Procedures & Obtain Certification | % | 100% | 50% | 100% | -18% | 32% | 68% | 0.3969% | 32% |  | -0.32 |  |  | 100% | 100% | 55% | 100% | -45% | 100% | 0%
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100% | 24% | 20% | -9% | 15% | 85% | 0.006615% | 15% |  | -0.15 |  |  | 20% | 20% | 30% | 20% | 10% | 20% | 0%
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100% | 24% | 20% | -9% | 15% | 85% | 0.006615% | 15% |  | -0.15 |  |  | 20% | 20% | 30% | 20% | 10% | 20% | 0%
|  | Perform NDT as per the Procedures | % | 100% | 24% | 20% | -9% | 15% | 85% | 0.1058% | 15% |  | -0.15 |  |  | 20% | 20% | 30% | 20% | 10% | 20% | 0%
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100% | 100% | 100% | -85% | 15% | 85% | 0.1058% | 15% | 100 | 99.85 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Prepare PWHT Procedures & Obtain Certification | % | 100% | 0% | 0% | 15% | 15% | 85% | 0.3307% | 15% |  | -0.15 |  |  | 0% | 0% | 0% | 0% | 0% | 13% | 0%
|  | Perform PWHT Testing | % | 100% | 0% | 0% | 15% | 15% | 85% | 0.172% | 15% |  | -0.15 |  |  | 0% | 0% | 0% | 0% | 0% | 13% | 0%
|  | Provide and maintain secure storage for radioactive sources | % | 100% | 24% | 20% | -9% | 15% | 85% | 0.1588% | 15% |  | -0.15 |  |  | 20% | 20% | 30% | 20% | 10% | 20% | 0%
|  | Implement specific safety procedures relating to radioactive sources | % | 100% | 100% | 100% | -85% | 15% | 85% | 0.006615% | 15% | 100 | 99.85 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Piping | pip | 0 | 0 | 5.842% | 0 | 0 | 0 | 10.22% | 8.691% |  | 0 |  |  | 5.059% | 4.891% | 5.227% | 5.227% | 0% | 13.27% | 0%
|  | AG Piping |  | 0 | 0 | 5.903% | 0 | 0 | 0 | 10.12% | 8.78% |  | 0 |  |  | 5.111% | 4.941% | 5.281% | 5.281% | 0% | 13.41% | 0%
|  | Shop |  | 0 | 0 | 9.436% | 0 | 0 | 0 | 3.541% | 17.66% |  | 0 |  |  | 7.175% | 6.69% | 7.661% | 7.661% | 0% | 30.88% | 0%
|  | Carbon Steel |  | 0 | 0 | 37.29% | 0 | 0 | 0 | 0.3889% | 38.04% |  | 0 |  |  | 16.7% | 12.28% | 21.12% | 21.12% | 0% | 196.4% | 0% |  | 187
|  | Material Handling From Lay down To Shop | ID | 4934 | 2450 | 24.19% | 0 | 2450 | 2484 | 0.01944% | 49.66% | 600 | -1850 |  |  | 23.03% | 23.03% | 23.03% | 23.03% | 0% | 23.02% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 1480 | 4000 | 40.19% | -3375.625 | 624.375 | 855.625 | 0.1361% | 42.19% |  | -624.375 |  |  | 14.65% | 14.65% | 14.65% | 14.65% | 0% | 270.3% | 0%
|  | Welding | ID | 1480 | 4000 | 37.1% | -3375.625 | 624.375 | 855.625 | 0.1361% | 42.19% |  | -624.375 |  |  | 12.64% | 0% | 25.27% | 12.64% | 12.64% | 270.3% | 0%
|  | NDT | ID | 296 | 20 | 0.6183% | -18.6786 | 1.3214 | 294.6786 | 0.01944% | 0.4464% |  | -1.3214 |  |  | 0% | 0% | 0% | 0% | 0% | 1.351% | 0%
|  | PWHT | ID | 1480 | 0 | 0% | 0 | 0 | 1480 | 0.01944% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 60% | 0 | 40 | 60 | 0.05833% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Low Temperature CS |  | 0 | 0 | 6% | 0 | 0 | 0 | 2.875% | 16.02% |  | 0 |  |  | 6% | 6% | 6% | 6% | 0% | 10.89% | 0%
|  | Material Handling From Lay down To Shop | ID | 36676 | 15000 | 0% | 0 | 15000 | 21676 | 0.1438% | 40.9% |  | -15000 |  |  | 0% | 0% | 0% | 0% | 0% | 3.817% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 11003 | 850 | 0% | 390 | 1240 | 9763 | 1.006% | 11.27% |  | -1240 |  |  | 0% | 0% | 0% | 0% | 0% | 7.725% | 0%
|  | Welding | ID | 11003 | 600 | 0% | 640 | 1240 | 9763 | 1.006% | 11.27% |  | -1240 |  |  | 0% | 0% | 0% | 0% | 0% | 5.453% | 0%
|  | NDT | ID | 11003 | 200 | 0% | 0 | 200 | 10803 | 0.1438% | 1.818% |  | -200 |  |  | 0% | 0% | 0% | 0% | 0% | 1.818% | 0%
|  | PWHT | ID | 11003 | 0 | 0% | 0 | 0 | 11003 | 0.1438% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.4313% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Galva |  | 0 | 0 | 6% | 0 | 0 | 0 | 0.04255% | 6% |  | 0 |  |  | 6% | 6% | 6% | 6% | 0% | 6% | 0%
|  | Material Handling From Lay down To Shop | ID | 544 | 0 | 0% | 0 | 0 | 544 | 0.002127% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 163 | 0 | 0% | 0 | 0 | 163 | 0.01489% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 163 | 0 | 0% | 0 | 0 | 163 | 0.01489% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 163 | 0 | 0% | 0 | 0 | 163 | 0.002127% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 163 | 0 | 0% | 0 | 0 | 163 | 0.002127% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.006382% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Copper Alloys |  | 0 | 0 | 6% | 0 | 0 | 0 | 0.2344% | 6% |  | 0 |  |  | 6% | 6% | 6% | 6% | 0% | 6% | 0%
|  | Material Handling From Lay down To Shop | ID | 578 | 0 | 0% | 0 | 0 | 578 | 0.01172% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & Bevelling & Fit Up | ID | 173 | 0 | 0% | 0 | 0 | 173 | 0.08205% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 173 | 0 | 0% | 0 | 0 | 173 | 0.08205% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 173 | 0 | 0% | 0 | 0 | 173 | 0.01172% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 173 | 0 | 0% | 0 | 0 | 173 | 0.01172% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.03516% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Field |  | 0 | 0 | 4% | 0 | 0 | 0 | 6.576% | 4% |  | 0 |  |  | 4% | 4% | 4% | 4% | 0% | 4% | 0%
|  | Carbon Steel |  | 0 | 0 | 4% | 0 | 0 | 0 | 0.7134% | 4% |  | 0 |  |  | 4% | 4% | 4% | 4% | 0% | 4% | 0%
|  | Material Handling From Shop To Field | ID | 4934 | 0 | 0% | 0 | 0 | 4934 | 0.03567% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Scaffolding | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.09275% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fit Up | ID | 3454 | 0 | 0% | 0 | 0 | 3454 | 0.1356% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 611 | 0 | 0% | 0 | 0 | 611 | 0.03567% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 4045 | 0 | 0% | 0 | 0 | 4045 | 0.2354% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 809 | 0 | 0% | 0 | 0 | 809 | 0.01784% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 4045 | 0 | 0% | 0 | 0 | 4045 | 0.0214% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 4045 | 0 | 0% | 0 | 0 | 4045 | 0.06778% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.07134% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Low Temperature CS |  | 0 | 0 | 4% | 0 | 0 | 0 | 5.276% | 4% |  | 0 |  |  | 4% | 4% | 4% | 4% | 0% | 4% | 0%
|  | Material Handling From Shop To Field | ID | 36676 | 0 | 0% | 0 | 0 | 36676 | 0.2638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Scaffolding | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.6858% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fit Up | ID | 25673 | 0 | 0% | 0 | 0 | 25673 | 1.002% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 611 | 0 | 0% | 0 | 0 | 611 | 0.2638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 25673 | 0 | 0% | 0 | 0 | 25673 | 1.741% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 25673 | 0 | 0% | 0 | 0 | 25673 | 0.1319% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 25673 | 0 | 0% | 0 | 0 | 25673 | 0.1583% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 25673 | 0 | 0% | 0 | 0 | 25673 | 0.5012% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.5276% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Galva |  | 0 | 0 | 4% | 0 | 0 | 0 | 0.07807% | 4% |  | 0 |  |  | 4% | 4% | 4% | 4% | 0% | 4% | 0%
|  | Material Handling From Shop To Field | ID | 544 | 0 | 0% | 0 | 0 | 544 | 0.003904% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Scaffolding | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.01015% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fit Up | ID | 381 | 0 | 0% | 0 | 0 | 381 | 0.01483% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 611 | 0 | 0% | 0 | 0 | 611 | 0.003904% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 381 | 0 | 0% | 0 | 0 | 381 | 0.02576% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 381 | 0 | 0% | 0 | 0 | 381 | 0.001952% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 381 | 0 | 0% | 0 | 0 | 381 | 0.002342% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 381 | 0 | 0% | 0 | 0 | 381 | 0.007417% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.007807% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | GRE |  | 0 | 0 | 4% | 0 | 0 | 0 | 0.07876% | 4% |  | 0 |  |  | 4% | 4% | 4% | 4% | 0% | 4% | 0%
|  | Scoffolding | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.01024% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling To Field | ID | 386 | 0 | 0% | 0 | 0 | 386 | 0.004726% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fittup | ID | 270 | 0 | 0% | 0 | 0 | 270 | 0.01496% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Bonding | ID | 270 | 0 | 0% | 0 | 0 | 270 | 0.0315% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 270 | 0 | 0% | 0 | 0 | 270 | 0.009451% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.007876% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Copper Alloys |  | 0 | 0 | 4% | 0 | 0 | 0 | 0.4302% | 4% |  | 0 |  |  | 4% | 4% | 4% | 4% | 0% | 4% | 0%
|  | Material Handling From Shop To Field | ID | 192 | 0 | 0% | 0 | 0 | 192 | 0.02151% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Scaffolding | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.05592% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection & Fit Up | ID | 134 | 0 | 0% | 0 | 0 | 134 | 0.08173% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Valve Installation | ID | 611 | 0 | 0% | 0 | 0 | 611 | 0.02151% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | ID | 134 | 0 | 0% | 0 | 0 | 134 | 0.142% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | ID | 134 | 0 | 0% | 0 | 0 | 134 | 0.01075% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PWHT | ID | 134 | 0 | 0% | 0 | 0 | 134 | 0.0129% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Hydro test | ID | 134 | 0 | 0% | 0 | 0 | 134 | 0.04086% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 40 | 40% | 0 | 40 | 60 | 0.04302% | 40% | 40 | 0 |  |  | 40% | 40% | 40% | 40% | 0% | 40% | 0%
|  | Pipe Support |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.1044% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Shop |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.03656% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Handling | Kg | 37124 | 0 | 0% | 0 | 0 | 37124 | 0.004021% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | shop drawing | Kg | 37124 | 0 | 0% | 0 | 0 | 37124 | 0.005849% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cutting & assembling | Kg | 37124 | 0 | 0% | 0 | 0 | 37124 | 0.008042% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | Kg | 37124 | 0 | 0% | 0 | 0 | 37124 | 0.01682% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.001828% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Field |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.06789% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling From Shop To Field | Kg | 55687 | 0 | 0% | 0 | 0 | 55687 | 0.01086% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Erection | Kg | 55687 | 0 | 0% | 0 | 0 | 55687 | 0.01426% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Welding | Kg | 55687 | 0 | 0% | 0 | 0 | 55687 | 0.02851% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | NDT | Kg | 55687 | 0 | 0% | 0 | 0 | 55687 | 0.01086% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 0 | 0% | 0 | 0 | 100 | 0.003394% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Painting & Sandblasting | pan | 0 | 0 | 6.928% | 0 | 0 | 0 | 1.339% | 13.41% |  | 0 |  |  | 2.858% | 2.858% | 2.858% | 2.858% | 0% | 12.32% | 0%
|  | Pipe |  | 0 | 0 | 7% | 0 | 0 | 0 | 1.325% | 13.55% |  | 0 |  |  | 2.887% | 2.887% | 2.887% | 2.887% | 0% | 12.45% | 0%
|  | Sand Blast | m2 | 5200 | 4850 | 20% | -3000 | 1850 | 3350 | 0.1988% | 35.58% | 415 | -1435 |  |  | 8.25% | 8.25% | 8.25% | 8.25% | 0% | 35.58% | 0%
|  | Primer | m2 | 5200 | 4850 | 20% | -3000 | 1850 | 3350 | 0.265% | 35.58% | 415 | -1435 |  |  | 8.248% | 8.248% | 8.248% | 8.248% | 0% | 35.57% | 0%
|  | Middle Paint | m2 | 5200 | 0 | 0% | 0 | 0 | 5200 | 0.4638% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Paint | m2 | 5200 | 0 | 0% | 0 | 0 | 5200 | 0.265% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Touch Up & Punch | m2 | 5200 | 0 | 0% | 0 | 0 | 5200 | 0.06626% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 100 | 0 | 0% | 22 | 22 | 78 | 0.06626% | 22% |  | -22 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Support |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01368% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Sand Blast | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.002052% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Primer | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.002736% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Middle Paint | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.004788% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Paint | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.002736% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Touch Up & Punch | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.000684% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Certificate | % | 1 | 0 | 0% | 0 | 0 | 1 | 0.000684% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Insulation | ins | 0 | 0 | 0% | 0 | 0 | 0 | 0.111% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Cold Insulation | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.0555% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hot Insulation | m2 | 1 | 0 | 0% | 0 | 0 | 1 | 0.0555% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Equipment Packages | equ | 0 | 0 | 0.1244% | 0 | 0 | 0 | 8.88% | 0.1244% |  | 0 |  |  | 0.1244% | 0.0274% | 0.0274% | 0.0274% | 0% | 0.1244% | 0%
|  | Static Equipment |  | 0 | 0 | 0.9081% | 0 | 0 | 0 | 1.217% | 0.9081% |  | 0 |  |  | 0.9081% | 0.2% | 0.2% | 0.2% | 0% | 0.9081% | 0%
|  | Air cooler 147-A-101 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.7488% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03744% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03744% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.2621% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1123% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1123% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1498% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03744% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Vert.) 147-D-101 A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.03062% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001531% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001531% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01072% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004594% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004594% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.006125% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001531% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Vert.) 147-D-101 B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.03062% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001531% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001531% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01072% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004594% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004594% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.006125% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001531% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Vert.) 147-D-102 A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0161% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008049% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008049% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005635% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002415% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002415% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00322% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008049% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Vert.) 147-D-102 B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0161% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008049% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008049% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005635% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002415% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002415% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00322% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008049% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Vert.) 147-D-103 A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01662% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008311% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008311% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005818% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002493% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002493% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003325% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008311% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Vert.) 147-D-103 B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01662% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008311% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008311% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005818% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002493% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002493% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003325% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0008311% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Hori) 147-D-104 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0912% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00456% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00456% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.03192% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01368% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01368% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01824% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00456% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Vert.) 147-D-105 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01977% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009884% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009884% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.006919% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002965% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002965% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003954% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009884% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Hori) 147-D-106 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01018% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005092% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005092% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003564% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001527% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001527% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002037% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005092% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Hori) 147-D-107 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01947% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009734% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009734% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.006814% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00292% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00292% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003894% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009734% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Hori) 147-D-108 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0001498% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 7.488e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 7.488e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 5.241e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 2.246e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 2.246e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 2.995e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 7.488e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Hori.) in Sump 147-D-109 |  | 0 | 0 | 44.88% | 0 | 0 | 0 | 0.02462% | 44.88% |  | 0 |  |  | 44.88% | 9.884% | 9.884% | 9.884% | 0% | 44.88% | 0%
|  | Material Handling | Kg | 16440 | 16060 | 97.69% | 0 | 16060 | 380 | 0.001231% | 97.69% |  | -16060 |  |  | 97.69% | 97.69% | 97.69% | 97.69% | 0% | 97.69% | 0%
|  | Chipping & Padding | % | 100 | 100 | 100% | 0 | 100 | 0 | 0.001231% | 100% |  | -100 |  |  | 100% | 100% | 100% | 100% | 0% | 100% | 0%
|  | Installation |  | 16440 | 16440 | 100% | 0 | 16440 | 0 | 0.008617% | 100% |  | -16440 |  |  | 100% | 0% | 0% | 100% | -100% | 100% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003693% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003693% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004924% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001231% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Drum (Hori) on St. 147-D-110 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.05272% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002636% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002636% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01845% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007908% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007908% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01054% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002636% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LP FLARE K.O. DRUM 147-D-111 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.007937% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0003968% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0003968% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002778% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001191% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001191% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001587% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0003968% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Electric Heater 147-DH-107 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0001857% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 9.285e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 9.285e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 6.499e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 2.785e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 2.785e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 3.714e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 9.285e-06% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Electric Heater 147-DH-108 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0003519% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.76e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.76e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001232% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 5.279e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 5.279e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 7.038e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.76e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Electric Heater 147-DH-109 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.000292% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.46e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.46e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001022% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 4.38e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 4.38e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 5.84e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.46e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Electric Heater 147-DH-110 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.0003654% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.827e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.827e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0001279% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 5.481e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 5.481e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 7.308e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 1.827e-05% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LPG TANK FLARE 147-X-101 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.03744% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001872% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001872% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0131% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005616% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005616% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007488% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001872% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | LOW PRESSURE PROPANE CHILLER 147-E-101 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01481% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0007405% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0007405% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005184% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002222% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002222% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002962% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0007405% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | MEDUIM PRESSURE PROPANE CHILLER 147-E-102 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.031% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00155% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00155% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01085% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00465% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00465% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0062% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.00155% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | HIGH PRESSURE PROPANE CHILLER 147-E-103 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.02037% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001018% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001018% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007128% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003055% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003055% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004073% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001018% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | PROPANE BOIL OFF GAS CONDENSER 147-E-104 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01048% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005241% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005241% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003669% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001572% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001572% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002097% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005241% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Rotary Equipment |  | 0 | 0 | 0% | 0 | 0 | 0 | 7.663% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Compressor 147-K-101A |  | 0 | 0 | 0% | 0 | 0 | 0 | 2.677% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1339% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1339% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.937% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.4016% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.4016% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.5354% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1339% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Compressor 147-K-101B |  | 0 | 0 | 0% | 0 | 0 | 0 | 2.677% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1339% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1339% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.937% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.4016% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.4016% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.5354% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1339% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Compressor 147-K-102A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.9691% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.04845% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.04845% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.3392% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1454% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1454% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1938% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.04845% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Compressor 147-K-101B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.9691% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.04845% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.04845% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.3392% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1454% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1454% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.1938% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.04845% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-101A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.03634% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01272% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005451% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005451% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007268% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-101B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.03634% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01272% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005451% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005451% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007268% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-101C |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.03634% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.01272% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005451% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.005451% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007268% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001817% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-102 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-103A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-103B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-103C |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-104 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-106 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.02261% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001131% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001131% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007914% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003392% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003392% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004522% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001131% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-107 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.02112% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001056% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001056% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007391% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003168% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003168% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004224% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001056% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-108 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01928% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.000964% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.000964% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.006748% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002892% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003856% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.000964% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-109A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01878% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009388% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009388% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.006571% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002816% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002816% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003755% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009388% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 147-P-109B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01878% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009388% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009388% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.006571% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002816% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002816% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003755% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0009388% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 148-P-101A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.02019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007066% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003028% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003028% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004038% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 148-P-101B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.02019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007066% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003028% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003028% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004038% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 148-P-101C |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.02019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.007066% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003028% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003028% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.004038% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 148-P-102 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 148-P-103A |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 148-P-103B |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 148-P-103C |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Pump 148-P-104 |  | 0 | 0 | 0% | 0 | 0 | 0 | 0.01009% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Material Handling |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Chipping & Padding |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.003533% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Alignment |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Grouting |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.001514% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | External Installation |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.002019% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Final Inspection |  | 1 | 0 | 0% | 0 | 0 | 1 | 0.0005047% | 0% |  | 0 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[13 empty] | 0 | [6 empty] | 0% |  | 0%
0

## Supervisor (hidden)
South Pars Gas Field Development Phase 14 Package Number 2
|  | Cut Of Date : | 2014-05-01 | [13 empty] | 27365% |  |  | 24.55%
Description |  |  | Quantity |  |  |  |  | Progress Approved | Quantity Approved Planning | Price
|  |  | Unit | Estimate | Up To Last | This Month | Work Performed Approved | [12 empty] | 23205
|  | Package NO.2 | [5 empty] | 34.86% |  | 273000000000 |  | 0 |  | تاییدی حجم | اختلاف | تاییدی قبل | دوره | پیمانکار | اختلاف |  | ادعای پیمانکار
|  | Procurement | per |  |  | 0 |  | 93.48% |  | #REF! |  | 0 |  |  | 0% | 85.33% | 8.142% | 90% | 3.473% |  | 93.48%
|  | fire proof | per |  |  | 0 |  | 0% |  | #REF! |  |  |  |  | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PO Placement | m2 | 200 | 0 | 0 | 0 | 0% | [6 empty] | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Fabrication & Test | m2 | 200 | 0 | 0 | 0 | 0% | [6 empty] | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Delivery | m2 | 200 | 0 | 0 | 0 | 0% | [6 empty] | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Rebar | per |  |  | 0 |  | 100% |  | #REF! | 308693 |  |  |  | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | PO Placement | Kg | 308693 | 308693 | 0 | 308693 | 100% | [5 empty] | 308693 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Fabrication & Test | Kg | 308693 | 308693 | 0 | 308693 | 100% | [5 empty] | 308693 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Delivery | Kg | 308693 | 308693 | 0 | 308693 | 100% | [5 empty] | 308693 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Piping Support | per |  |  | 0 |  | 100% |  | #REF! |  |  |  |  | 0% | 25% | 75% | 100% | 0% |  | 100%
|  | PO Placement | Kg | 80000 | 80000 | 0 | 80000 | 100% | [5 empty] | 72000 | 0% | 25% | 75% | 100% | 0% |  | 100%
|  | Fabrication & Test | Kg | 80000 | 80000 | 0 | 80000 | 100% | [5 empty] | 72000 | 0% | 25% | 75% | 100% | 0% |  | 100%
|  | Delivery | Kg | 80000 | 80000 | 0 | 80000 | 100% | [6 empty] | 0% | 25% | 75% | 100% | 0% |  | 100%
|  | Cold Insulating | per |  |  | 0 |  | 0% |  | #REF! |  |  |  |  | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PO Placement | m2 | 5862 | 0 | 0 | 0 | 0% | [6 empty] | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Fabrication & Test | m2 | 5862 | 0 | 0 | 0 | 0% | [6 empty] | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Delivery | m2 | 5862 | 0 | 0 | 0 | 0% | [6 empty] | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Warm Insulating | per |  |  | 0 |  | 100% |  | #REF! |  |  |  |  | 0% | 0% | 100% | 0% | 100% |  | 100%
|  | PO Placement | m2 | 2937 | 0 | 2937 | 2937 | 100% | [6 empty] | 0% | 0% | 100% | 0% | 100% |  | 100%
|  | Fabrication & Test | m2 | 2937 | 0 | 2937 | 2937 | 100% | [6 empty] | 0% | 0% | 100% | 0% | 100% |  | 100%
|  | Delivery | m2 | 2937 | 0 | 2937 | 2937 | 100% | [6 empty] | 0% | 0% | 100% | 0% | 100% |  | 100%
|  | Paint | per |  |  | 0 |  | 100% |  | #REF! | 13900 |  |  |  | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | PO Placement | Kg | 57000 | 57000 | 0 | 57000 | 100% | [5 empty] | 57000 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Delivery | Kg | 57000 | 57000 | 0 | 57000 | 100% | [5 empty] | 12730 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Electrode | per |  |  | 0 |  | 100% |  | #REF! | 18080 |  |  |  | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | PO Placement | Kg | 27000 | 27000 | 0 | 27000 | 100% | [5 empty] | 18080 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Fabrication & Test | Kg | 27000 | 27000 | 0 | 27000 | 100% | [5 empty] | 18080 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Delivery | Kg | 27000 | 27000 | 0 | 27000 | 100% | [5 empty] | 18080 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Plant Construction |  |  |  | 0 |  | 24.51% |  | #REF! |  | 0 |  | 0 | -8.3% | 25.39% | -0.8759% | 27.9% | -3.389% |  | 32.81%
|  | General |  |  |  | 0 |  | 59.93% |  | #REF! |  | 0 |  | 0 | -35.21% | 55.07% | 4.857% | 55.62% | 4.315% | 0.0123* | 95.14%
|  | mobolization |  |  |  | 0 |  | 61% |  | #REF! |  | 0 |  | 0 | -39% | 61% | 0% | 61.6% | -0.6% |  | 100%
|  | primary mobilozation | % | 100 | 100 | 0 | 100 | 100% |  | #REF! | 100 | 0 |  | 100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | countiuse mobilization | % | 100 | 35 | 0 | 35 | 35% |  | #REF! | 27 | -8 |  | 21 | -65% | 35% | 0% | 36% | -1% |  | 100%
|  | Demobilizaton |  |  |  | 0 |  | 50% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 50% | 0% | 50% |  | 50%
|  | Demobilizaton | % | 100 | 0 | 50 | 50 | 50% |  | #REF! |  | -50 |  | 0 | 0% | 0% | 50% | 0% | 50% |  | 50%
|  | Gate House | civ |  |  | 0 |  | 25% |  | #REF! |  | 0 |  | 0 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | civil | civ |  |  | 0 |  | 100% |  | #REF! |  | 0 |  | 0 | 0% | 100% | 0% | 100% | 0% |  | 100%
| ` | Foundation | % | 100 | 100 | 0 | 100 | 100% |  | #REF! | 100 | 0 |  | 100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | columns | % | 100 | 100 | 0 | 100 | 100% |  | #REF! | 100 | 0 |  | 100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Wall | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  | -100 |  | 100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Floor | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  | -100 |  | 100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Roof | % | 100 | 100 | 0 | 100 | 100% |  | #REF! | 95 | -5 |  | 100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Mechanical | civ |  |  | 0 |  | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Piping | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | electrical | civ |  |  | 0 |  | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cabling | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | telecom | civ |  |  | 0 |  | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | telecom | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | architect | civ |  |  | 0 |  | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | architect | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | final works | civ |  |  | 0 |  | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | final works | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Unit 140 |  |  |  | 0 |  | 34.61% |  | #REF! |  | 0 |  | 0 | -5.749% | 33.98% | 0.6289% | 37.48% | -2.873% |  | 40.36%
|  | Welding & NDT Procedures | pip |  |  | 0 |  | 30.4% |  | #REF! |  | 0 |  | 0 | -69.6% | 39.21% | -8.81% | 86.63% | -56.23% |  | 100%
|  | Prepare and qualify welding procedures (welding procedures qualfication tests (WPQT) including lab. Tests) for structural and pipe welding | % | 100% | 100% | -72% | 28% | 28% |  | #REF! | 100 | 99.72 |  | 100 | -72% | 100% | -72% | 100% | -72% |  | 100%
|  | Qualification of welders including lab testing for structural and pipe welding | % | 100% | 100% | -72% | 28% | 28% |  | #REF! | 100 | 99.72 |  | 100 | -72% | 100% | -72% | 100% | -72% |  | 100%
|  | Qualification of welding equipment | % | 100% | 100% | -72% | 28% | 28% |  | #REF! | 100 | 99.72 |  | 100 | -72% | 100% | -72% | 100% | -72% |  | 100%
|  | Maintaining welder qualification records | % | 100% | 100% | -72% | 28% | 28% |  | #REF! | 100 | 99.72 |  | 100 | -72% | 100% | -72% | 100% | -72% |  | 100%
|  | Monitoring welder performance | % | 100% | 100% | -72% | 28% | 28% |  | #REF! | 100 | 99.72 |  | 100 | -72% | 100% | -72% | 100% | -72% |  | 100%
|  | Prepare and NDT Procedures and obtain certification | % | 100% | 50% | -14% | 36% | 36% |  | #REF! |  | -0.36 |  | 50 | -64% | 50% | -14% | 100% | -64% |  | 100%
|  | Qualification of NDT equipment and dimensional control (UT, RT, MT,...) | % | 100% | 24% | 4% | 28% | 28% |  | #REF! |  | -0.28 |  | 20 | -72% | 25% | 3% | 45% | -17% |  | 100%
|  | Qualification of equipment operators for NDT and dimensional control | % | 100% | 24% | 4% | 28% | 28% |  | #REF! |  | -0.28 |  | 20 | -72% | 25% | 3% | 100% | -72% |  | 100%
|  | Perform NDT as per the procedures | % | 100% | 24% | 4% | 28% | 28% |  | #REF! |  | -0.28 |  | 20 | -72% | 25% | 3% | 100% | -72% |  | 100%
|  | Supply of associated Elec. Power, consumables, Materials construction equipments | % | 100% | 100% | -72% | 28% | 28% |  | #REF! | 100 | 99.72 |  | 100 | -72% | 100% | -72% | 100% | -72% |  | 100%
|  | Prepare PWHT procedure and obtain certification | % | 100% | 0% | 28% | 28% | 28% |  | #REF! |  | -0.28 |  | 0 | -72% | 20% | 8% | 100% | -72% |  | 100%
|  | Perform PWHT testing | % | 100% | 0% | 28% | 28% | 28% |  | #REF! |  | -0.28 |  | 0 | -72% | 20% | 8% | 50% | -22% |  | 100%
|  | Provide and maintain secure storage for radioactive sources | % | 100% | 24% | 4% | 28% | 28% |  | #REF! |  | -0.28 |  | 20 | -72% | 28% | 0% | 45% | -17% |  | 100%
|  | Implement specific safety procedures relating to radioactive sources | % | 100% | 100% | -72% | 28% | 28% |  | #REF! | 100 | 99.72 |  | 100 | -72% | 100% | -72% | 100% | -72% |  | 100%
|  | Civil | civ |  | 0 | 0 | 0 | 52.78% |  | #REF! |  | 0 |  | 0 | -4.975% | 51.85% | 0.9289% | 54.35% | -1.575% |  | 57.75%
|  | Plat Form |  |  | 0 | 0 | 0 | 78.97% |  | #REF! |  | 0 |  | 0 | -0.03452% | 77.77% | 1.2% | 79.38% | -0.413% |  | 79%
|  | West HP |  |  | 0 | 0 | 0 | 85.68% |  | #REF! |  | 0 |  | 0 | -0.19% | 84.38% | 1.3% | 86.35% | -0.668% |  | 85.87%
|  | excavation | m3 | 1983 | 1765 | 0 | 1765 | 89.01% |  | #REF! | 1385 | -380 |  | 1765 | 0% | 89.01% | 0% | 89.01% | 0% |  | 89.01%
|  | level&compact | m2 | 851 | 705 | 0 | 705 | 82.84% |  | #REF! | 588 | -117 |  | 705 | 0% | 82.84% | 0% | 82.84% | 0% |  | 82.84%
|  | lean | m3 | 36.57 | 32 | 0 | 32 | 87.5% |  | #REF! | 40 | 8 |  | 32 | 0% | 87.5% | 0% | 87.5% | 0% |  | 87.5%
|  | footing rebar | Kg | 33778 | 29400 | 0 | 29400 | 87.04% |  | #REF! | 25188 | -4212 |  | 2868 | 0% | 87.04% | 0% | 87.04% | 0% |  | 87.04%
|  | footing form | m2 | 309 | 246 | 0 | 246 | 79.61% |  | #REF! | 195 | -51 |  | 246 | 0% | 79.61% | 0% | 79.61% | 0% |  | 79.61%
|  | foting concrete | m3 | 448 | 390 | 0 | 390 | 87.05% |  | #REF! | 343 | -47 |  | 390 | 0% | 87.05% | 0% | 87.05% | 0% |  | 87.05%
|  | ped rebar | Kg | 22520 | 20892 | 0 | 20892 | 92.77% |  | #REF! | 11666 | -9226 |  | 20892 | 0% | 92.77% | 0% | 92.77% | 0% |  | 92.77%
|  | ped form | m2 | 376 | 306 | 0 | 306 | 81.38% |  | #REF! | 225 | -81 |  | 306 | 0% | 81.38% | 0% | 86.44% | -5.053% |  | 81.38%
|  | anchor | NO. | 418 | 335 | 0 | 335 | 80.14% |  | #REF! | 98 | -237 |  | 324 | 0% | 80.14% | 0% | 88.52% | -8.373% |  | 80.14%
|  | ped concrete | m3 | 146 | 130 | 0 | 130 | 89.04% |  | #REF! | 12 | -118 |  | 130 | 0% | 89.04% | 0% | 89.04% | 0% |  | 89.04%
|  | curing | % | 100 | 60 | 0 | 60 | 60% |  | #REF! | 75 | 15 |  | 60 | -29% | 60% | 0% | 85% | -25% |  | 89%
|  | coating | m2 | 1174 | 864 | 0 | 864 | 73.59% |  | #REF! | 400 | -464 |  | 864 | 0% | 73.59% | 0% | 84.33% | -10.73% |  | 73.59%
|  | back fill | m3 | 1402 | 1240 | 0 | 1240 | 88.45% |  | #REF! | 0 | -1240 |  | 1240 | 0% | 88.45% | 0% | 88.45% | 0% |  | 88.45%
|  | Final Certificate | % | 100 | 60 | 26 | 86 | 86% |  | #REF! | 45 | -41 |  | 60 | 2% | 60% | 26% | 75% | 11% |  | 84%
|  | East HP |  |  | 0 | 0 | 0 | 86.93% |  | #REF! |  | 0 |  | 0 | 0.15% | 85.53% | 1.4% | 87.08% | -0.1543% |  | 86.78%
|  | excavation | m3 | 1983 | 1765 | 0 | 1765 | 89.01% |  | #REF! | 1358 | -407 |  | 1765 | 0% | 89.01% | 0% | 89.01% | 0% |  | 89.01%
|  | level&compact | m2 | 845 | 705 | 0 | 705 | 83.43% |  | #REF! | 575 | -130 |  | 705 | 0% | 83.43% | 0% | 83.43% | 0% |  | 83.43%
|  | lean | m3 | 36 | 32 | 0 | 32 | 88.89% |  | #REF! | 39 | 7 |  | 32 | 0% | 88.89% | 0% | 88.89% | 0% |  | 88.89%
|  | footing rebar | Kg | 33471 | 29750 | 0 | 29750 | 88.88% |  | #REF! | 26445 | -3305 |  | 2868 | 0% | 88.88% | 0% | 88.88% | 0% |  | 88.88%
|  | footing form | m2 | 298 | 246 | 0 | 246 | 82.55% |  | #REF! | 200 | -46 |  | 246 | 0% | 82.55% | 0% | 82.55% | 0% |  | 82.55%
|  | foting concrete | m3 | 444 | 390 | 0 | 390 | 87.84% |  | #REF! | 358 | -32 |  | 390 | 0% | 87.84% | 0% | 87.84% | 0% |  | 87.84%
|  | ped rebar | Kg | 21315 | 20892 | 0 | 20892 | 98.02% |  | #REF! | 12103 | -8789 |  | 20892 | 0% | 98.02% | 0% | 98.02% | 0% |  | 98.02%
|  | ped form | m2 | 389 | 306 | 0 | 306 | 78.66% |  | #REF! | 235 | -71 |  | 306 | 0% | 78.66% | 0% | 86.12% | -7.455% |  | 78.66%
|  | anchor | NO. | 420 | 324 | 0 | 324 | 77.14% |  | #REF! | 132 | -192 |  | 324 | 0% | 77.14% | 0% | 82.14% | -5% |  | 77.14%
|  | ped concrete | m3 | 146 | 130 | 0 | 130 | 89.04% |  | #REF! | 60 | -70 |  | 130 | 0% | 89.04% | 0% | 89.04% | 0% |  | 89.04%
|  | curing | % | 100 | 80 | 0 | 80 | 80% |  | #REF! | 60 | -20 |  | 60 | -5% | 80% | 0% | 85% | -5% |  | 85%
|  | coating | m2 | 1173 | 932 | 0 | 932 | 79.45% |  | #REF! | 500 | -432 |  | 864 | 0% | 79.45% | 0% | 85.08% | -5.627% |  | 79.45%
|  | back fill | m3 | 1406 | 1240 | 0 | 1240 | 88.19% |  | #REF! | 0 | -1240 |  | 1240 | 0% | 88.19% | 0% | 88.19% | 0% |  | 88.19%
|  | Final Certificate | % | 100 | 60 | 28 | 88 | 88% |  | #REF! | 45 | -43 |  | 60 | 4% | 60% | 28% | 75% | 13% |  | 84%
|  | West LP |  |  | 0 | 0 | 0 | 74.77% |  | #REF! |  | 0 |  | 0 | -0.05% | 73.72% | 1.05% | 75.52% | -0.7507% |  | 74.82%
|  | excavation | m3 | 397 | 325 | 0 | 325 | 81.86% |  | #REF! | 145 | -180 |  | 325 | 0% | 81.86% | 0% | 81.86% | 0% |  | 81.86%
|  | level&compact | m2 | 218 | 175 | 0 | 175 | 80.28% |  | #REF! | 99 | -76 |  | 175 | 0% | 80.28% | 0% | 80.28% | 0% |  | 80.28%
|  | lean | m3 | 7 | 5 | 0 | 5 | 71.43% |  | #REF! | 5 | 0 |  | 5 | 0% | 71.43% | 0% | 71.43% | 0% |  | 71.43%
|  | footing rebar | Kg | 7260 | 6154 | 0 | 6154 | 84.77% |  | #REF! | 6702 | 548 |  | 6154 | 0% | 84.77% | 0% | 84.77% | 0% |  | 84.77%
|  | footing form | m2 | 100 | 65 | 0 | 65 | 65% |  | #REF! | 71 | 6 |  | 65 | 0% | 65% | 0% | 70% | -5% |  | 65%
|  | foting concrete | m3 | 65 | 45 | 0 | 45 | 69.23% |  | #REF! | 18 | -27 |  | 45 | 0% | 69.23% | 0% | 69.23% | 0% |  | 69.23%
|  | ped rebar | Kg | 4840 | 3389 | 0 | 3389 | 70.02% |  | #REF! | 2300 | -1089 |  | 3389 | 0% | 70.02% | 0% | 70.02% | 0% |  | 70.02%
|  | ped form | m2 | 107 | 85 | 0 | 85 | 79.44% |  | #REF! | 41 | -44 |  | 85 | 0% | 79.44% | 0% | 79.44% | 0% |  | 79.44%
|  | anchor | NO. | 120 | 95 | 0 | 95 | 79.17% |  | #REF! | 29 | -66 |  | 95 | 0% | 79.17% | 0% | 79.17% | 0% |  | 79.17%
|  | ped concrete | m3 | 35 | 28 | 0 | 28 | 80% |  | #REF! | 21 | -7 |  | 28 | 0% | 80% | 0% | 80% | 0% |  | 80%
|  | curing | % | 100 | 60 | 0 | 60 | 60% |  | #REF! | 40 | -20 |  | 60 | -20% | 60% | 0% | 70% | -10% |  | 80%
|  | coating | m2 | 384 | 287 | 0 | 287 | 74.74% |  | #REF! | 0 | -287 |  | 287 | 0% | 74.74% | 0% | 74.74% | 0% |  | 74.74%
|  | back fill | m3 | 296 | 210 | 0 | 210 | 70.95% |  | #REF! | 0 | -210 |  | 210 | 0% | 70.95% | 0% | 77.7% | -6.757% |  | 70.95%
|  | Final Certificate | % | 100 | 55 | 21 | 76 | 76% |  | #REF! | 35 | -41 |  | 55 | 3% | 55% | 21% | 65% | 11% |  | 73%
|  | East LP |  |  | 0 | 0 | 0 | 10.6% |  | #REF! |  | 0 |  | 0 | -0.15% | 10.75% | -0.15% | 10.75% | -0.15% |  | 10.75%
|  | excavation | m3 | 397 | 397 | 0 | 397 | 100% |  | #REF! |  | -397 |  | 397 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | level&compact | m2 | 218 | 218 | 0 | 218 | 100% |  | #REF! |  | -218 |  | 218 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | lean | m3 | 7 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | footing rebar | Kg | 7260 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | footing form | m2 | 102 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | foting concrete | m3 | 65 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | ped rebar | Kg | 4840 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | ped form | m2 | 107 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | anchor | NO. | 120 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | ped concrete | m3 | 35 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | curing | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | coating | m2 | 384 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | back fill | m3 | 296 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 15 | -3 | 12 | 12% |  | #REF! |  | -12 |  | 15 | -3% | 15% | -3% | 15% | -3% |  | 15%
|  | Retaining wall |  |  | 0 | 0 | 0 | 30.94% |  | #REF! |  | 0 |  | 0 | -9.593% | 30.22% | 0.7159% | 33.61% | -2.675% |  | 40.53%
|  | Retaining wall 7 |  |  | 0 | 0 | 0 | 10.6% |  | #REF! |  | 0 |  | 0 | -12.77% | 10.2% | 0.4% | 12.88% | -2.28% |  | 23.37%
|  | excavation | m3 | 2750 | 2750 | 0 | 2750 | 100% |  | #REF! |  | -2750 |  | 1375 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | level&compact | m2 | 275 | 275 | 0 | 275 | 100% |  | #REF! |  | -275 |  | 0 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | lean | m3 | 46 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | footing rebar | Kg | 54855 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -63.8% | 0% | 0% | 19.14% | -19.14% |  | 63.8%
|  | footing form | m2 | 200 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | foting concrete | m3 | 400 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Wall rebar | Kg | 18285 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -65.63% | 0% | 0% | 0% | 0% |  | 65.63%
|  | Wall form | m2 | 760 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Wall concrete | m3 | 370 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | curing | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | coating | m2 | 1206 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | back fill | m3 | 4000 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 4 | 8 | 12 | 12% |  | #REF! |  | -12 |  | 4 | 2% | 4% | 8% | 4% | 8% |  | 10%
|  | Retaining wall 9 |  |  | 0 | 0 | 0 | 94.75% |  | #REF! |  | 0 |  | 0 | 0.25% | 93.25% | 1.5% | 100% | -5.25% |  | 94.5%
|  | excavation | m3 | 316 | 316 | 0 | 316 | 100% |  | #REF! | 316 | 0 |  | 316 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | level&compact | m2 | 128 | 128 | 0 | 128 | 100% |  | #REF! | 128 | 0 |  | 128 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | lean | m3 | 4 | 4 | 0 | 4 | 100% |  | #REF! | 4 | 0 |  | 4 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | footing rebar | Kg | 10025 | 10025 | 0 | 10025 | 100% |  | #REF! | 10025 | 0 |  | 10025 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | footing form | m2 | 45 | 45 | 0 | 45 | 100% |  |  | 45 | 0 |  | 45 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | foting concrete | m3 | 58 | 58 | 0 | 58 | 100% |  |  |  | -58 |  | 58 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Wall rebar | Kg | 10100 | 10100 | 0 | 10100 | 100% |  |  |  | -10100 |  | 10100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Wall form | m2 | 195 | 195 | 0 | 195 | 100% |  |  |  | -195 |  | 195 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Wall concrete | m3 | 56 | 56 | 0 | 56 | 100% |  | #REF! |  | -56 |  | 56 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | curing | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  | -100 |  | 65 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | coating | m2 | 145 | 145 | 0 | 145 | 100% |  | #REF! |  | -145 |  | 87 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | back fill | m3 | 166 | 83 | 0 | 83 | 50% |  | #REF! |  | -83 |  | 83 | 0% | 50% | 0% | 100% | -50% |  | 50%
|  | Final Certificate | % | 100 | 65 | 30 | 95 | 95% |  | #REF! | 20 | -75 |  | 60 | 0% | 65% | 30% | 100% | -5% |  | 95%
|  | Retaining wall 11 |  |  | 0 | 0 | 0 | 10.6% |  | #REF! |  | 0 |  | 0 | -12.9% | 10.3% | 0.3% | 14.47% | -3.867% |  | 23.5%
|  | excavation | m3 | 850 | 850 | 0 | 850 | 100% |  | #REF! |  | -850 |  | 340 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | level&compact | m2 | 55 | 55 | 0 | 55 | 100% |  | #REF! |  | -55 |  | 0 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | lean | m3 | 3.4 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | footing rebar | Kg | 8400 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -65.48% | 0% | 0% | 29.76% | -29.76% |  | 65.48%
|  | footing form | m2 | 50 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | foting concrete | m3 | 73 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Wall rebar | Kg | 2800 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | -63.93% | 0% | 0% | 0% | 0% |  | 63.93%
|  | Wall form | m2 | 159 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Wall concrete | m3 | 76 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | curing | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | coating | m2 | 251 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | back fill | m3 | 1500 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 6 | 6 | 12 | 12% |  | #REF! |  | -12 |  | 6 | 2% | 6% | 6% | 6% | 6% |  | 10%
|  | Retaining wall 12 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 98.3% | 1.7% | 100% | 0% |  | 100%
|  | excavation | m3 | 316 | 316 | 0 | 316 | 100% |  | #REF! | 316 | 0 |  | 316 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | level&compact | m2 | 128 | 128 | 0 | 128 | 100% |  | #REF! | 128 | 0 |  | 128 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | lean | m3 | 5 | 5 | 0 | 5 | 100% |  |  |  | -5 |  | 5 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | footing rebar | Kg | 10025 | 10025 | 0 | 10025 | 100% |  |  |  | -10025 |  | 10025 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | footing form | m2 | 45 | 45 | 0 | 45 | 100% |  |  |  | -45 |  | 45 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | foting concrete | m3 | 50 | 50 | 0 | 50 | 100% |  |  |  | -50 |  | 50 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Wall rebar | Kg | 10100 | 10100 | 0 | 10100 | 100% |  | #REF! |  | -10100 |  | 10100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Wall form | m2 | 195 | 195 | 0 | 195 | 100% |  | #REF! |  | -195 |  | 195 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Wall concrete | m3 | 64 | 64 | 0 | 64 | 100% |  | #REF! |  | -64 |  | 64 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | curing | % | 100 | 100 | 0 | 100 | 100% |  | #REF! |  | -100 |  | 100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | coating | m2 | 145 | 145 | 0 | 145 | 100% |  | #REF! |  | -145 |  | 145 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | back fill | m3 | 166 | 166 | 0 | 166 | 100% |  | #REF! |  | -166 |  | 166 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final Certificate | % | 100 | 66 | 34 | 100 | 100% |  | #REF! | 8 | -92 |  | 56 | 0% | 66% | 34% | 100% | 0% |  | 100%
|  | Retaining wall 13 |  |  | 0 | 0 | 0 | 65.42% |  | #REF! |  | 0 |  | 0 | -0.9368% | 63.47% | 1.95% | 73.69% | -8.265% |  | 66.36%
|  | excavation | m3 | 600 | 600 | 0 | 600 | 100% |  | #REF! |  | -600 |  | 600 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | level&compact | m2 | 58 | 58 | 0 | 58 | 100% |  | #REF! |  | -58 |  | 58 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | lean | m3 | 2.6 | 2.6 | 0 | 2.6 | 100% |  |  |  | -2.6 |  | 2.6 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | footing rebar | Kg | 6826 | 6826 | 0 | 6826 | 100% |  |  |  | -6826 |  | 6826 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | footing form | m2 | 29 | 29 | 0 | 29 | 100% |  |  |  | -29 |  | 29 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | foting concrete | m3 | 35 | 35 | 0 | 35 | 100% |  |  |  | -35 |  | 35 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Wall rebar | Kg | 2275 | 1100 | 0 | 1100 | 48.35% |  | #REF! |  | -1100 |  | 682.5 | -19.78% | 48.35% | 0% | 61.54% | -13.19% |  | 68.13%
|  | Wall form | m2 | 103 | 52 | 0 | 52 | 50.49% |  | #REF! |  | -52 |  | 30.9 | 0% | 50.49% | 0% | 62.14% | -11.65% |  | 50.49%
|  | Wall concrete | m3 | 28 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 60.71% | -60.71% |  | 0%
|  | curing | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | -50% | 0% | 0% | 20% | -20% |  | 50%
|  | coating | m2 | 150 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | back fill | m3 | 1000 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 36 | 39 | 75 | 75% |  | #REF! |  | -75 |  | 34 | 15% | 36% | 39% | 40% | 35% |  | 60%
|  | Base |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Base | m3 | 560 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Piping | pip |  | 0 | 0 | 0 | 23.03% |  | #REF! |  | 0 |  | 0 | -1.853% | 22.89% | 0.1395% | 22.81% | 0.2138% |  | 24.88%
|  | AG Piping |  |  | 0 | 0 | 0 | 22.97% |  | #REF! |  | 0 |  | 0 | -1.725% | 22.97% | 0% | 22.61% | 0.3624% |  | 24.7%
|  | Shop |  |  | 0 | 0 | 0 | 23.83% |  | #REF! |  | 0 |  | 0 | -3.432% | 23.83% | 0% | 25.06% | -1.231% |  | 27.26%
|  | Carbon Steel |  |  | 0 | 0 | 0 | 41.33% |  | #REF! |  | 0 |  | 0 | -4.375% | 44.74% | -3.411% | 42.16% | -0.8348% |  | 45.7%
|  | Material Handling From Lay down To Shop | ID | 42944 | 25598 | 0 | 25598 | 59.61% |  | #REF! | 3390 | -22208 |  | 25598 | 0% | 59.61% | 0% | 59.61% | 0% |  | 59.61%
|  | Cutting & Bevelling & Fit Up | ID | 12883 | 6933 | 0 | 6933 | 53.82% |  | #REF! |  | -6933 |  | 6933 | 0% | 53.82% | 0% | 53.82% | 0% |  | 53.82%
|  | Welding | ID | 12883 | 5800 | 0 | 5800 | 45.02% |  | #REF! |  | -5800 |  | 2280 | -5.69% | 45.02% | 0% | 47.41% | -2.391% |  | 50.71%
|  | NDT | ID | 2576.6 | 17 | -13.6 | 3.4 | 0.132% |  | #REF! |  | -3.4 |  | 0 | -2.662% | 0.132% | 0% | 0.09315% | 0.03881% |  | 2.794%
|  | PWHT | ID | 12883 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 20 | -5 |  | 20 | -15% | 25% | 0% | 25% | 0% |  | 40%
|  | Low Temperature CS |  |  | 0 | 0 | 0 | 5.165% |  | #REF! |  | 0 |  | 0 | 0% | 5.165% | 0% | 9.314% | -4.15% |  | 5.165%
|  | Material Handling From Lay down To Shop | ID | 27889 | 1248 | 0 | 1248 | 4.475% |  | #REF! |  | -1248 |  | 1248 | 0% | 4.475% | 0% | 4.475% | 0% |  | 4.475%
|  | Cutting & Bevelling & Fit Up | ID | 8367 | 232 | 0 | 232 | 2.773% |  | #REF! |  | -232 |  | 0 | 0% | 2.773% | 0% | 8.988% | -6.215% |  | 2.773%
|  | Welding | ID | 8367 | 232 | 0 | 232 | 2.773% |  | #REF! |  | -232 |  | 0 | 0% | 2.773% | 0% | 8.414% | -5.641% |  | 2.773%
|  | NDT | ID | 8367 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 20 | 0 | 20 | 20% |  | #REF! | 20 | 0 |  | 20 | 0% | 20% | 0% | 20% | 0% |  | 20%
|  | Stainless Steel |  |  | 0 | 0 | 0 | 3% |  | #REF! |  | 0 |  | 0 | 0% | 3% | 0% | 3% | 0% |  | 3%
|  | Material Handling From Lay down To Shop | ID | 13845 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & Bevelling & Fit Up | ID | 4154 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 4154 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 4154 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 4154 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 20 | 0 | 20 | 20% |  | #REF! | 20 | 0 |  | 20 | 0% | 20% | 0% | 20% | 0% |  | 20%
|  | Galva |  |  | 0 | 0 | 0 | 27.83% |  | #REF! |  | 0 |  | 0 | -69.17% | 27.83% | 0% | 3% | 24.83% |  | 97%
|  | Material Handling From Lay down To Shop | ID | 2645 | 2645 | 0 | 2645 | 100% |  | #REF! |  | -2645 |  | 0 | 0% | 100% | 0% | 0% | 100% |  | 100%
|  | Cutting & Bevelling & Fit Up | ID | 794 | 794 | -612.0417 | 181.9583 | 22.92% |  | #REF! |  | -181.9583 |  | 0 | -77.08% | 22.92% | 0% | 0% | 22.92% |  | 100%
|  | Welding | ID | 794 | 794 | -612.0417 | 181.9583 | 22.92% |  | #REF! |  | -181.9583 |  | 0 | -77.08% | 22.92% | 0% | 0% | 22.92% |  | 100%
|  | NDT | ID | 794 | 794 | -612.0417 | 181.9583 | 22.92% |  | #REF! |  | -181.9583 |  | 0 | -77.08% | 22.92% | 0% | 0% | 22.92% |  | 100%
|  | PWHT | ID | 794 | 794 | -612.0417 | 181.9583 | 22.92% |  | #REF! |  | -181.9583 |  | 0 | -77.08% | 22.92% | 0% | 0% | 22.92% |  | 100%
|  | Final Certificate | % | 100 | 80 | -50 | 30 | 30% |  | #REF! | 20 | -10 |  | 20 | -50% | 30% | 0% | 20% | 10% |  | 80%
|  | Field |  |  | 0 | 0 | 0 | 22.51% |  | #REF! |  | 0 |  | 0 | -0.8062% | 22.51% | 0% | 21.29% | 1.221% |  | 23.32%
|  | Carbon Steel |  |  | 0 | 0 | 0 | 24.11% |  | #REF! |  | 0 |  | 0 | -0.8642% | 24.11% | 0% | 23.08% | 1.033% |  | 24.98%
|  | Material Handling From Shop To Field | ID | 42944 | 22000 | 0 | 22000 | 51.23% |  | #REF! | 452 | -21548 |  | 6007 | 0% | 51.23% | 0% | 13.99% | 37.24% |  | 51.23%
|  | Scaffolding | m2 | 8000 | 7349 | 0 | 7349 | 91.86% |  | #REF! | 2350 | -4999 |  | 7349 | 0% | 91.86% | 0% | 91.86% | 0% |  | 91.86%
|  | Erection & Fit Up | ID | 30060 | 3619 | 0 | 3619 | 12.04% | 91.86% | #REF! | 452 | -3167 |  | 3619 | 0% | 12.04% | 0% | 12.32% | -0.2761% |  | 12.04%
|  | Valve Installation | ID | 280 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 30060 | 2970 | 0 | 2970 | 9.88% |  | #REF! | 408 | -2562 |  | 1842 | -1.261% | 9.88% | 0% | 12.22% | -2.342% |  | 11.14%
|  | NDT | ID | 6012 | 722 | -577.6 | 144.4 | 2.402% |  | #REF! |  | -144.4 |  | 0 | -17.92% | 2.402% | 0% | 2.562% | -0.1597% |  | 20.33%
|  | PWHT | ID | 30060 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 30060 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Low Temperature CS |  |  | 0 | 0 | 0 | 22.83% |  | #REF! |  | 0 |  | 0 | -0.03739% | 22.83% | 0% | 21.61% | 1.219% |  | 22.87%
|  | Material Handling From Shop To Field | ID | 27889 | 10000 | 0 | 10000 | 35.86% |  | #REF! |  | -10000 |  | 496 | 0% | 35.86% | 0% | 11.47% | 24.38% |  | 35.86%
|  | Scaffolding | m2 | 8000 | 7349 | 0 | 7349 | 91.86% |  | #REF! | 2350 | -4999 |  | 7349 | 0% | 91.86% | 0% | 91.86% | 0% |  | 91.86%
|  | Erection & Fit Up | ID | 19522 | 1864 | 0 | 1864 | 9.548% |  | #REF! |  | -1864 |  | 384 | 0% | 9.548% | 0% | 9.548% | 0% |  | 9.548%
|  | Valve Installation | ID | 280 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 19522 | 1864 | 0 | 1864 | 9.548% |  | #REF! |  | -1864 |  | 44 | 0% | 9.548% | 0% | 9.548% | 0% |  | 9.548%
|  | NDT | ID | 19522 | 1008 | 0 | 1008 | 5.163% |  | #REF! |  | -1008 |  | 0 | -1.496% | 5.163% | 0% | 5.163% | 0% |  | 6.659%
|  | PWHT | ID | 19522 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 19522 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Stainless Steel |  |  | 0 | 0 | 0 | 15.94% |  | #REF! |  | 0 |  | 0 | 0% | 15.94% | 0% | 15.94% | 0% |  | 15.94%
|  | Material Handling From Shop To Field | ID | 13845 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Scaffolding | m2 | 8000 | 7349 | 0 | 7349 | 91.86% |  | #REF! | 2350 | -4999 |  | 7349 | 0% | 91.86% | 0% | 91.86% | 0% |  | 91.86%
|  | Erection & Fit Up | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 280 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 9692 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Galva |  |  | 0 | 0 | 0 | 35.27% |  | #REF! |  | 0 |  | 0 | -20.55% | 35.27% | 0% | 15.94% | 19.32% |  | 55.82%
|  | Material Handling From Shop To Field | ID | 2645 | 2645 | 0 | 2645 | 100% |  | #REF! |  | -2645 |  | 0 | 0% | 100% | 0% | 0% | 100% |  | 100%
|  | Scaffolding | m2 | 8000 | 7349 | 0 | 7349 | 91.86% |  | #REF! | 2350 | -4999 |  | 7349 | 0% | 91.86% | 0% | 91.86% | 0% |  | 91.86%
|  | Erection & Fit Up | ID | 1852 | 1000 | -575.5833 | 424.4167 | 22.92% |  | #REF! |  | -424.4167 |  | 0 | -31.08% | 22.92% | 0% | 0% | 22.92% |  | 54%
|  | Valve Installation | ID | 280 | 280 | -215.8333 | 64.1667 | 22.92% |  | #REF! |  | -64.1667 |  | 0 | -77.08% | 22.92% | 0% | 0% | 22.92% |  | 100%
|  | Welding | ID | 1852 | 1000 | -575.5833 | 424.4167 | 22.92% |  | #REF! |  | -424.4167 |  | 0 | -31.08% | 22.92% | 0% | 0% | 22.92% |  | 54%
|  | NDT | ID | 1852 | 100 | 324.4167 | 424.4167 | 22.92% |  | #REF! |  | -424.4167 |  | 0 | 17.52% | 22.92% | 0% | 0% | 22.92% |  | 5.4%
|  | PWHT | ID | 1852 | 100 | 324.4167 | 424.4167 | 22.92% |  | #REF! |  | -424.4167 |  | 0 | 17.52% | 22.92% | 0% | 0% | 22.92% |  | 5.4%
|  | Hydro test | ID | 1852 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 55 | -15 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | -15% | 40% | 0% | 40% | 0% |  | 55%
|  | Pipe Support |  |  | 0 | 0 | 0 | 27.97% |  | #REF! |  | 0 |  | 0 | -14.18% | 14.32% | 13.65% | 42.15% | -14.18% |  | 42.15%
|  | Shop |  |  | 0 | 0 | 0 | 69.05% |  | #REF! |  | 0 |  | 0 | -30.95% | 20.48% | 48.57% | 100% | -30.95% |  | 100%
|  | Handling | Kg | 60354.4 | 43200 | 0 | 43200 | 71.58% |  | #REF! |  | -43200 |  | 43200 | -28.42% | 20.71% | 50.86% | 100% | -28.42% |  | 100%
|  | shop drawing | Kg | 60354.4 | 43200 | 0 | 43200 | 71.58% |  | #REF! |  | -43200 |  | 0 | -28.42% | 20.71% | 50.86% | 100% | -28.42% |  | 100%
|  | Cutting & assembling | Kg | 60354.4 | 43200 | 0 | 43200 | 71.58% |  | #REF! |  | -43200 |  | 0 | -28.42% | 20.71% | 50.86% | 100% | -28.42% |  | 100%
|  | Welding | Kg | 60354.4 | 43200 | 0 | 43200 | 71.58% |  | #REF! |  | -43200 |  | 0 | -28.42% | 20.71% | 50.86% | 100% | -28.42% |  | 100%
|  | Final Certificate | % | 100 | 16 | 5 | 21 | 21% |  | #REF! |  | -21 |  | 0 | -79% | 16% | 5% | 100% | -79% |  | 100%
|  | Field |  |  | 0 | 0 | 0 | 5.849% |  | #REF! |  | 0 |  | 0 | -5.151% | 11% | -5.151% | 11% | -5.151% |  | 11%
|  | Material Handling From Shop To Field | Kg | 90531.6 | 43200 | 0 | 43200 | 47.72% |  | #REF! |  | -43200 |  | 8500 | -52.28% | 100% | -52.28% | 100% | -52.28% |  | 100%
|  | Erection | Kg | 90531.6 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | Kg | 90531.6 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | Kg | 90531.6 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 12 | 12 | 12% |  | #REF! |  | -12 |  | 0 | 12% | 0% | 12% | 0% | 12% |  | 0%
|  | Painting & Sandblasting | pan |  | 0 | 0 | 0 | 19.52% |  |  |  | 0 |  | 0 | 0.7215% | 17.12% | 2.402% | 16.02% | 3.501% |  | 18.8%
|  | Pipe |  |  | 0 | 0 | 0 | 19.73% |  |  |  | 0 |  | 0 | 1% | 17.3% | 2.427% | 16.19% | 3.537% |  | 18.73%
|  | Sand Blast | m2 | 39250 | 21000 | 0 | 21000 | 53.5% |  |  | 1886 | -19114 |  | 8635 | 0% | 49.43% | 4.076% | 46.25% | 7.248% |  | 53.5%
|  | Primer | m2 | 39250 | 21000 | 0 | 21000 | 53.5% |  |  | 1886 | -19114 |  | 8635 | 0% | 49.43% | 4.076% | 46.25% | 7.248% |  | 53.5%
|  | Middle Paint | m2 | 39250 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Paint | m2 | 39250 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Touch Up & Punch | m2 | 39250 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 20 | 20 | 20% |  |  |  | -20 |  | 0 | 20% | 0% | 20% | 0% | 20% |  | 0%
|  | Support |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -26.25% | 0% | 0% | 0% | 0% |  | 26.25%
|  | Sand Blast | m2 | 800 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -75% | 0% | 0% | 0% | 0% |  | 75%
|  | Primer | m2 | 800 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -75% | 0% | 0% | 0% | 0% |  | 75%
|  | Middle Paint | m2 | 800 | 0 | 0 |  | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Paint | m2 | 800 | 0 | 0 |  | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Touch Up & Punch | m2 | 800 | 0 | 0 |  | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 0 |  | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Steel Structure | str |  | 0 | 0 | 0 | 86.6% |  | #REF! |  | 0 |  | 0 | -1.851% | 81.81% | 4.793% | 85% | 1.602% |  | 88.45%
|  | Installation Steel Structure |  |  | 0 | 0 | 0 | 87.38% |  | #REF! |  | 0 |  | 0 | -1.868% | 82.55% | 4.836% | 85.77% | 1.617% |  | 89.25%
|  | 140-IM-A1 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 93233 | 93233 | 0 | 93233 | 100% |  | #REF! | 94004 | 771 |  | 94004 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! | 14 | 0 |  | 14 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 93233 | 93233 | 0 | 93233 | 100% |  | #REF! | 94004 | 771 |  | 94004 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 93233 | 93233 | 0 | 93233 | 100% |  | #REF! | 94004 | 771 |  | 94004 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 93233 | 93233 | 0 | 93233 | 100% |  | #REF! | 94004 | 771 |  | 94004 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! | 14 | 0 |  | 14 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 50 | -50 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-A2 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 135196 | 135196 | 0 | 135196 | 100% |  | #REF! | 136607 | 1411 |  | 136607 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! | 16 | 2 |  | 16 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 135196 | 135196 | 0 | 135196 | 100% |  | #REF! | 136607 | 1411 |  | 136607 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 135196 | 135196 | 0 | 135196 | 100% |  | #REF! | 136607 | 1411 |  | 136607 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 135196 | 135196 | 0 | 135196 | 100% |  | #REF! | 136607 | 1411 |  | 136607 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! | 16 | 2 |  | 16 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 62 | -38 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-A3 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 83004 | 83004 | 0 | 83004 | 100% |  | #REF! | 80800 | -2204 |  | 80800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! | 16 | 0 |  | 16 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 83004 | 83004 | 0 | 83004 | 100% |  | #REF! | 80800 | -2204 |  | 80800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 83004 | 83004 | 0 | 83004 | 100% |  | #REF! | 80800 | -2204 |  | 80800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 83004 | 83004 | 0 | 83004 | 100% |  | #REF! | 80800 | -2204 |  | 80800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! | 16 | 0 |  | 16 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 62 | -38 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-A4 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 62652 | 62652 | 0 | 62652 | 100% |  | #REF! | 62652 | 0 |  | 62652 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! | 14 | 0 |  | 14 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 62652 | 62652 | 0 | 62652 | 100% |  | #REF! | 62652 | 0 |  | 62652 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 62652 | 62652 | 0 | 62652 | 100% |  | #REF! | 62652 | 0 |  | 62652 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 62652 | 62652 | 0 | 62652 | 100% |  | #REF! | 62652 | 0 |  | 62652 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! | 14 | 0 |  | 14 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 55 | -45 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-A5 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 179726 | 179726 | 0 | 179726 | 100% |  | #REF! | 179726 | 0 |  | 179726 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 32 | 32 | 0 | 32 | 100% |  | #REF! | 32 | 0 |  | 32 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 179726 | 179726 | 0 | 179726 | 100% |  | #REF! | 179726 | 0 |  | 179726 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 179726 | 179726 | 0 | 179726 | 100% |  | #REF! | 179726 | 0 |  | 179726 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 179726 | 179726 | 0 | 179726 | 100% |  | #REF! | 179726 | 0 |  | 179726 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 32 | 32 | 0 | 32 | 100% |  | #REF! | 32 | 0 |  | 32 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 62 | -38 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-A6 & A6-1 |  |  | 0 | 0 | 0 | 99.66% |  | #REF! |  | 0 |  | 0 | 0% | 94.86% | 4.8% | 94.86% | 4.8% |  | 99.66%
|  | Handling | Kg | 160153 | 159708.8393 | 0 | 159708.8393 | 99.72% |  | #REF! | 135200 | -24508.8393 |  | 135200 | 0% | 99.72% | 0% | 99.72% | 0% |  | 99.72%
|  | Chip&Padding | NO | 85 | 85 | 0 | 85 | 100% |  | #REF! | 33 | -52 |  | 33 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 160153 | 159708.8393 | 0 | 159708.8393 | 99.72% |  | #REF! | 135199 | -24509.8393 |  | 135200 | 0% | 99.72% | 0% | 99.72% | 0% |  | 99.72%
|  | Alignment | Kg | 160153 | 159708.8393 | 0 | 159708.8393 | 99.72% |  | #REF! | 135199 | -24509.8393 |  | 135200 | 0% | 99.72% | 0% | 99.72% | 0% |  | 99.72%
|  | Bolt Tightening & Test | Kg | 160153 | 159708.8393 | 0 | 159708.8393 | 99.72% |  | #REF! | 135199 | -24509.8393 |  | 135200 | 0% | 99.72% | 0% | 99.72% | 0% |  | 99.72%
|  | Grouting | NO | 85 | 85 | 0 | 85 | 100% |  | #REF! | 33 | -52 |  | 33 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 32 | 99 | 99% |  | #REF! | 63 | -36 |  | 67 | 0% | 67% | 32% | 67% | 32% |  | 99%
|  | 140-IM-A7 |  |  | 0 | 0 | 0 | 16.25% |  | #REF! |  | 0 |  | 0 | 1.65% | 14% | 2.25% | 14% | 2.25% |  | 14.6%
|  | Handling | Kg | 58446 | 58446 | 0 | 58446 | 100% |  | #REF! | 58446 | 0 |  | 58446 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 16 | 8 | 0 | 8 | 50% |  | #REF! | 8 | 0 |  | 8 | 0% | 50% | 0% | 50% | 0% |  | 50%
|  | Erection | Kg | 58446 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 58446 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Bolt Tightening & Test | Kg | 58446 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | NO | 16 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final test & Documents | % | 100 | 10 | 15 | 25 | 14% |  | #REF! | 9 | -16 |  | 10 | 0% | 10% | 4% | 10% | 4% |  | 14%
|  | 140-IM-B1 |  |  | 0 | 0 | 0 | 12.6% |  | #REF! |  | 0 |  | 0 | 1.35% | 9.6% | 3% | 9.6% | 3% |  | 11.25%
|  | Handling | Kg | 65946 | 63311.1216 | 0 | 63311.1216 | 96% |  | #REF! | 64131 | 819.8784 |  | 64131 | 0% | 96% | 0% | 96% | 0% |  | 96%
|  | Chip&Padding | NO | 10 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection | Kg | 65946 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 65946 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Bolt Tightening & Test | Kg | 65946 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | NO | 10 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final test & Documents | % | 100 | 0 | 20 | 20 | 20% |  | #REF! | 7 | -13 |  | 0 | 9% | 0% | 20% | 0% | 20% |  | 11%
|  | 140-IM-B2 |  |  | 0 | 0 | 0 | 12.94% |  | #REF! |  | 0 |  | 0 | 1.5% | 9.944% | 3% | 9.944% | 3% |  | 11.44%
|  | Handling | Kg | 171694 | 170741 | 0 | 170741 | 99.44% |  | #REF! | 170741 | 0 |  | 170741 | 0% | 99.44% | 0% | 99.44% | 0% |  | 99.44%
|  | Chip&Padding | NO | 12 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection | Kg | 171694 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 171694 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Bolt Tightening & Test | Kg | 171694 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | NO | 12 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final test & Documents | % | 100 | 0 | 20 | 20 | 20% |  | #REF! | 7 | -13 |  | 0 | 10% | 0% | 20% | 0% | 20% |  | 10%
|  | 140-IM-B3 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 169239 | 169239 | 0 | 169239 | 100% |  | #REF! | 167795 | -1444 |  | 169239 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 28 | 28 | 0 | 28 | 100% |  | #REF! | 28 | 0 |  | 28 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 169239 | 169239 | 0 | 169239 | 100% |  | #REF! | 167795 | -1444 |  | 169238.6 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 169239 | 169239 | 0 | 169239 | 100% |  | #REF! | 167795 | -1444 |  | 169239 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 169239 | 169239 | 0 | 169239 | 100% |  | #REF! | 0 | -169239 |  | 169239 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 28 | 28 | 0 | 28 | 100% |  | #REF! | 0 | -28 |  | 28 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 40 | -60 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-B4 |  |  | 0 | 0 | 0 | 99.79% |  | #REF! |  | 0 |  | 0 | 0% | 94.99% | 4.8% | 99.19% | 0.6% |  | 99.79%
|  | Handling | Kg | 115066 | 115066 | 0 | 115066 | 100% |  | #REF! | 115066 | 0 |  | 115066 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 20 | 20 | 0 | 20 | 100% |  | #REF! | 20 | 0 |  | 20 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 115066 | 114950.6 | 0 | 114950.6 | 99.9% |  | #REF! | 113646 | -1304.6 |  | 114950.6 | 0% | 99.9% | 0% | 99.9% | 0% |  | 99.9%
|  | Alignment | Kg | 115066 | 114951 | 0 | 114951 | 99.9% |  | #REF! | 113646 | -1305 |  | 114951 | 0% | 99.9% | 0% | 99.9% | 0% |  | 99.9%
|  | Bolt Tightening & Test | Kg | 115066 | 114951 | 0 | 114951 | 99.9% |  | #REF! | 113646 | -1305 |  | 114951 | 0% | 99.9% | 0% | 99.9% | 0% |  | 99.9%
|  | Grouting | NO | 20 | 20 | 0 | 20 | 100% |  | #REF! | 20 | 0 |  | 20 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 32 | 99 | 99% |  | #REF! | 54 | -45 |  | 67 | 0% | 67% | 32% | 95% | 4% |  | 99%
|  | 140-IM-B5 |  |  | 0 | 0 | 0 | 99.79% |  | #REF! |  | 0 |  | 0 | 0% | 94.99% | 4.8% | 99.19% | 0.6% |  | 99.79%
|  | Handling | Kg | 72007 | 72007 | 0 | 72007 | 100% |  | #REF! | 72293 | 286 |  | 72807 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 10 | 10 | 0 | 10 | 100% |  | #REF! | 10 | 0 |  | 10 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 72007 | 71935 | 0 | 71935 | 99.9% |  | #REF! | 72293 | 358 |  | 72407 | 0% | 99.9% | 0% | 99.9% | 0% |  | 99.9%
|  | Alignment | Kg | 72007 | 71935 | 0 | 71935 | 99.9% |  | #REF! | 72293 | 358 |  | 72407 | 0% | 99.9% | 0% | 99.9% | 0% |  | 99.9%
|  | Bolt Tightening & Test | Kg | 72007 | 71935 | 0 | 71935 | 99.9% |  | #REF! | 72293 | 358 |  | 72407 | 0% | 99.9% | 0% | 99.9% | 0% |  | 99.9%
|  | Grouting | NO | 10 | 10 | 0 | 10 | 100% |  | #REF! | 10 | 0 |  | 10 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 32 | 99 | 99% |  | #REF! | 55 | -44 |  | 67 | 0% | 67% | 32% | 95% | 4% |  | 99%
|  | 140-IM-B6 |  |  | 0 | 0 | 0 | 99.77% |  | #REF! |  | 0 |  | 0 | 0% | 94.97% | 4.8% | 98.42% | 1.35% |  | 99.77%
|  | Handling | Kg | 161771 | 161771 | 0 | 161771 | 100% |  | #REF! | 161544 | -227 |  | 161771 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! | 26 | 0 |  | 26 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 161771 | 161544.3 | 0 | 161544.3 | 99.86% |  | #REF! | 161544 | -0.3 |  | 161544.3 | 0% | 99.86% | 0% | 99.86% | 0% |  | 99.86%
|  | Alignment | Kg | 161771 | 161544 | 0 | 161544 | 99.86% |  | #REF! | 161544 | 0 |  | 161544 | 0% | 99.86% | 0% | 99.86% | 0% |  | 99.86%
|  | Bolt Tightening & Test | Kg | 161771 | 161544 | 0 | 161544 | 99.86% |  | #REF! | 161544 | 0 |  | 161544 | 0% | 99.86% | 0% | 99.86% | 0% |  | 99.86%
|  | Grouting | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! | 26 | 0 |  | 26 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 32 | 99 | 99% |  | #REF! | 55 | -44 |  | 67 | 0% | 67% | 32% | 90% | 9% |  | 99%
|  | 140-IM-B7 |  |  | 0 | 0 | 0 | 99.78% |  | #REF! |  | 0 |  | 0 | 0% | 94.98% | 4.8% | 98.43% | 1.35% |  | 99.78%
|  | Handling | Kg | 85977 | 85977 | 0 | 85977 | 100% |  | #REF! | 85857 | -120 |  | 85977 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 12 | 0 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 85977 | 85876.7 | 0 | 85876.7 | 99.88% |  | #REF! | 83375 | -2501.7 |  | 85876.7 | 0% | 99.88% | 0% | 99.88% | 0% |  | 99.88%
|  | Alignment | Kg | 85977 | 85877 | 0 | 85877 | 99.88% |  | #REF! | 83375 | -2502 |  | 85877 | 0% | 99.88% | 0% | 99.88% | 0% |  | 99.88%
|  | Bolt Tightening & Test | Kg | 85977 | 85877 | 0 | 85877 | 99.88% |  | #REF! | 83375 | -2502 |  | 85877 | 0% | 99.88% | 0% | 99.88% | 0% |  | 99.88%
|  | Grouting | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 12 | 0 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 32 | 99 | 99% |  | #REF! | 52 | -47 |  | 67 | 0% | 67% | 32% | 90% | 9% |  | 99%
|  | 140-IM-B8 |  |  | 0 | 0 | 0 | 99.67% |  | #REF! |  | 0 |  | 0 | 0.6% | 94.87% | 4.8% | 98.32% | 1.35% |  | 99.07%
|  | Handling | Kg | 98013 | 98013 | 0 | 98013 | 100% |  | #REF! | 97681 | -332 |  | 98013 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 12 | 0 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 98013 | 97714 | 0 | 97714 | 99.69% |  | #REF! | 97320 | -394 |  | 97714 | 0% | 99.69% | 0% | 99.69% | 0% |  | 99.69%
|  | Alignment | Kg | 98013 | 97714 | 0 | 97714 | 99.69% |  | #REF! | 97320 | -394 |  | 97714 | 0% | 99.69% | 0% | 99.69% | 0% |  | 99.69%
|  | Bolt Tightening & Test | Kg | 98013 | 97714 | 0 | 97714 | 99.69% |  | #REF! | 97320 | -394 |  | 97714 | 0% | 99.69% | 0% | 99.69% | 0% |  | 99.69%
|  | Grouting | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 12 | 0 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 32 | 99 | 99% |  | #REF! | 54 | -45 |  | 67 | 4% | 67% | 32% | 90% | 9% |  | 95%
|  | 140-IM-B9 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 59041 | 59041 | 0 | 59041 | 100% |  | #REF! | 59500 | 459 |  | 59500 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 8 | 8 | 0 | 8 | 100% |  | #REF! | 8 | 0 |  | 8 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 59041 | 59041 | 0 | 59041 | 100% |  | #REF! | 59500 | 459 |  | 59500 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 59041 | 59041 | 0 | 59041 | 100% |  | #REF! | 59500 | 459 |  | 59500 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 59041 | 59041 | 0 | 59041 | 100% |  | #REF! | 59500 | 459 |  | 59500 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 8 | 8 | 0 | 8 | 100% |  | #REF! | 8 | 0 |  | 8 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 48 | -52 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-B10 |  |  | 0 | 0 | 0 | 80.49% |  | #REF! |  | 0 |  | 0 | 2.25% | 74.79% | 5.7% | 74.79% | 5.7% |  | 78.24%
|  | Handling | Kg | 101233 | 101233 | 0 | 101233 | 100% |  | #REF! | 101700 | 467 |  | 101700 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 12 | 0 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 101233 | 80030.8083 | 0 | 80030.8083 | 79.06% |  | #REF! | 80400 | 369.1917 |  | 80400 | 0% | 79.06% | 0% | 79.06% | 0% |  | 79.06%
|  | Alignment | Kg | 101233 | 80030.8083 | 0 | 80030.8083 | 79.06% |  | #REF! | 80400 | 369.1917 |  | 80400 | 0% | 79.06% | 0% | 79.06% | 0% |  | 79.06%
|  | Bolt Tightening & Test | Kg | 101233 | 63898.2298 | 0 | 63898.2298 | 63.12% |  | #REF! | 0 | -63898.2298 |  | 64193 | 0% | 63.12% | 0% | 63.12% | 0% |  | 63.12%
|  | Grouting | NO | 12 | 7 | 0 | 7 | 58.33% |  | #REF! | 0 | -7 |  | 7 | 0% | 58.33% | 0% | 58.33% | 0% |  | 58.33%
|  | Final test & Documents | % | 100 | 52 | 38 | 90 | 90% |  | #REF! | 38 | -52 |  | 52 | 15% | 52% | 38% | 52% | 38% |  | 75%
|  | 140-IM-B11 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 142969 | 142969 | 0 | 142969 | 100% |  | #REF! | 142783 | -186 |  | 142783 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 24 | 24 | 0 | 24 | 100% |  | #REF! | 24 | 0 |  | 24 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 142969 | 142969 | 0 | 142969 | 100% |  | #REF! | 142783 | -186 |  | 142783 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 142969 | 142969 | 0 | 142969 | 100% |  | #REF! | 142783 | -186 |  | 142783 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 142969 | 142969 | 0 | 142969 | 100% |  | #REF! | 142783 | -186 |  | 142783 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 24 | 24 | 0 | 24 | 100% |  | #REF! | 24 | 0 |  | 24 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 50 | -50 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-B12 |  |  | 0 | 0 | 0 | 70% |  | #REF! |  | 0 |  | 0 | -78% | 62.5% | 7.5% | 62.5% | 7.5% |  | 148%
|  | Handling | Kg | 81227 | 81227 | 0 | 81227 | 100% |  | #REF! | 81169 | -58 |  | 81227 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 6 | 6 | 0 | 6 | 100% |  | #REF! | 6 | 0 |  | 6 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 81227 | 81227 | 0 | 81227 | 100% |  | #REF! | 81000 | -227 |  | 81227 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 81227 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Bolt Tightening & Test | Kg | 81227 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | NO | 6 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final test & Documents | % | 100 | 50 | 50 | 100 | 100% |  | #REF! | 40 | -60 |  | 50 | -520% | 50% | 50% | 50% | 50% |  | 620%
|  | 140-IM-B13 |  |  | 0 | 0 | 0 | 73.18% |  | #REF! |  | 0 |  | 0 | 1.95% | 67.18% | 6% | 71.68% | 1.5% |  | 71.23%
|  | Handling | Kg | 115037 | 115037 | 0 | 115037 | 100% |  | #REF! | 114739 | -298 |  | 115037 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 14 | 14 | 0 | 14 | 100% |  | #REF! | 14 | 0 |  | 14 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 115037 | 77582 | 0 | 77582 | 67.44% |  | #REF! | 75656 | -1926 |  | 75808 | 0% | 67.44% | 0% | 67.44% | 0% |  | 67.44%
|  | Alignment | Kg | 115037 | 77582 | 0 | 77582 | 67.44% |  | #REF! | 0 | -77582 |  | 0 | 0% | 67.44% | 0% | 67.44% | 0% |  | 67.44%
|  | Bolt Tightening & Test | Kg | 115037 | 77582 | 0 | 77582 | 67.44% |  | #REF! | 0 | -77582 |  | 0 | 0% | 67.44% | 0% | 67.44% | 0% |  | 67.44%
|  | Grouting | NO | 14 | 8 | 0 | 8 | 57.14% |  | #REF! | 0 | -8 |  | 0 | 0% | 57.14% | 0% | 57.14% | 0% |  | 57.14%
|  | Final test & Documents | % | 100 | 40 | 40 | 80 | 80% |  | #REF! | 31 | -49 |  | 40 | 13% | 40% | 40% | 70% | 10% |  | 67%
|  | 140-IM-C1 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 34919 | 34919 | 0 | 34919 | 100% |  | #REF! | 33400 | -1519 |  | 33400 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 12 | 0 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 34919 | 34919 | 0 | 34919 | 100% |  | #REF! | 33400 | -1519 |  | 33399.6 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 34919 | 34919 | 0 | 34919 | 100% |  | #REF! | 0 | -34919 |  | 33400 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 34919 | 34919 | 0 | 34919 | 100% |  | #REF! | 0 | -34919 |  | 33400 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 0 | -12 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 40 | -60 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-C2 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 63237 | 63237 | 0 | 63237 | 100% |  | #REF! | 63000 | -237 |  | 63000 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 22 | 22 | 0 | 22 | 100% |  | #REF! | 22 | 0 |  | 22 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 63237 | 63237 | 0 | 63237 | 100% |  | #REF! | 61847 | -1390 |  | 63000 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 63237 | 63237 | 0 | 63237 | 100% |  | #REF! | 0 | -63237 |  | 63000 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 63237 | 63237 | 0 | 63237 | 100% |  | #REF! | 0 | -63237 |  | 63000 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 22 | 22 | 0 | 22 | 100% |  | #REF! | 0 | -22 |  | 22 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 40 | -60 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-C3 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 32631 | 32631 | 0 | 32631 | 100% |  | #REF! | 31800 | -831 |  | 31800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 12 | 0 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 32631 | 32631 | 0 | 32631 | 100% |  | #REF! | 31800 | -831 |  | 31800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 32631 | 32631 | 0 | 32631 | 100% |  | #REF! | 0 | -32631 |  | 31800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 32631 | 32631 | 0 | 32631 | 100% |  | #REF! | 0 | -32631 |  | 31800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 12 | 12 | 0 | 12 | 100% |  | #REF! | 0 | -12 |  | 12 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 41 | -59 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-D1 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 57553 | 57553 | 0 | 57553 | 100% |  | #REF! | 57553 | 0 |  | 57553 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! | 18 | 0 |  | 18 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 57553 | 57553 | 0 | 57553 | 100% |  | #REF! | 57553 | 0 |  | 57553 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 57553 | 57553 | 0 | 57553 | 100% |  | #REF! | 57553 | 0 |  | 57553 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 57553 | 57553 | 0 | 57553 | 100% |  | #REF! | 57533 | -20 |  | 57553 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! | 18 | 0 |  | 18 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 41 | -59 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-D2 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 51015 | 51015 | 0 | 51015 | 100% |  | #REF! | 50938 | -77 |  | 51015 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! | 16 | 0 |  | 16 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 51015 | 51015 | 0 | 51015 | 100% |  | #REF! | 50588 | -427 |  | 51015 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 51015 | 51015 | 0 | 51015 | 100% |  | #REF! | 50588 | -427 |  | 51015 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 51015 | 51015 | 0 | 51015 | 100% |  | #REF! | 50588 | -427 |  | 51015 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! | 16 | 0 |  | 16 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 49 | -51 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-D3 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 67658 | 67658 | 0 | 67658 | 100% |  | #REF! | 67658 | 0 |  | 67658 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! | 26 | 0 |  | 26 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 67658 | 67658 | 0 | 67658 | 100% |  | #REF! | 67658 | 0 |  | 67658 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 67658 | 67658 | 0 | 67658 | 100% |  | #REF! | 67658 | 0 |  | 67658 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 67658 | 67658 | 0 | 67658 | 100% |  | #REF! | 67658 | 0 |  | 67658 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! | 26 | 0 |  | 26 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 41 | -59 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-D4 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 58695 | 58695 | 0 | 58695 | 100% |  | #REF! | 58695 | 0 |  | 58695 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! | 18 | 0 |  | 18 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 58695 | 58695 | 0 | 58695 | 100% |  | #REF! | 58695 | 0 |  | 58695 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 58695 | 58695 | 0 | 58695 | 100% |  | #REF! | 0 | -58695 |  | 58695 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 58695 | 58695 | 0 | 58695 | 100% |  | #REF! | 0 | -58695 |  | 58695 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! | 0 | -18 |  | 18 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 41 | -59 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-E1 |  |  | 0 | 0 | 0 | 82.5% |  | #REF! |  | 0 |  | 0 | 1.95% | 77.25% | 5.25% | 80.25% | 2.25% |  | 80.55%
|  | Handling | Kg | 53769 | 53769 | 0 | 53769 | 100% |  | #REF! | 50500 | -3269 |  | 50500 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 20 | 20 | 0 | 20 | 100% |  | #REF! | 20 | 0 |  | 20 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 53769 | 43069.5014 | 0 | 43069.5014 | 80.1% |  | #REF! | 35264 | -7805.5014 |  | 40451 | 0% | 80.1% | 0% | 80.1% | 0% |  | 80.1%
|  | Alignment | Kg | 53769 | 40221 | 0 | 40221 | 74.8% |  | #REF! | 0 | -40221 |  | 30000 | 0% | 74.8% | 0% | 74.8% | 0% |  | 74.8%
|  | Bolt Tightening & Test | Kg | 53769 | 40221 | 0 | 40221 | 74.8% |  | #REF! | 0 | -40221 |  | 30000 | 0% | 74.8% | 0% | 74.8% | 0% |  | 74.8%
|  | Grouting | NO | 20 | 14 | 0 | 14 | 70% |  | #REF! | 0 | -14 |  | 12 | 0% | 70% | 0% | 70% | 0% |  | 70%
|  | Final test & Documents | % | 100 | 55 | 35 | 90 | 90% |  | #REF! | 40 | -50 |  | 55 | 13% | 55% | 35% | 75% | 15% |  | 77%
|  | 140-IM-E2 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 64679 | 64679 | 0 | 64679 | 100% |  | #REF! | 64431 | -248 |  | 64679 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! | 26 | 0 |  | 26 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 64679 | 64679 | 0 | 64679 | 100% |  | #REF! | 63845 | -834 |  | 64679 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 64679 | 64679 | 0 | 64679 | 100% |  | #REF! | 63845 | -834 |  | 64679 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 64679 | 64679 | 0 | 64679 | 100% |  | #REF! | 63845 | -834 |  | 64679 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 26 | 26 | 0 | 26 | 100% |  | #REF! | 26 | 0 |  | 26 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 55 | -45 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | 140-IM-E3 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 94% | 6% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 38933 | 38933 | 0 | 38933 | 100% |  | #REF! | 38834 | -99 |  | 40000 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! | 16 | 0 |  | 16 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 38933 | 38933 | 0 | 38933 | 100% |  | #REF! | 37088 | -1845 |  | 39525 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 38933 | 38933 | 0 | 38933 | 100% |  | #REF! | 37088 | -1845 |  | 39525 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 38933 | 38933 | 0 | 38933 | 100% |  | #REF! | 37088 | -1845 |  | 25000 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 16 | 16 | 0 | 16 | 100% |  | #REF! | 0 | -16 |  | 0 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 60 | 40 | 100 | 100% |  | #REF! | 45 | -55 |  | 60 | 0% | 60% | 40% | 95% | 5% |  | 100%
|  | 140-IM-E4 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 94.3% | 5.7% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 14165 | 14165 | 0 | 14165 | 100% |  | #REF! | 14200 | 35 |  | 14165 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 6 | 6 | 0 | 6 | 100% |  | #REF! | 6 | 0 |  | 6 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 14165 | 14165 | 0 | 14165 | 100% |  | #REF! | 14200 | 35 |  | 14200.4 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 14165 | 14165 | 0 | 14165 | 100% |  | #REF! | 14200 | 35 |  | 14165 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 14165 | 14165 | 0 | 14165 | 100% |  | #REF! | 14200 | 35 |  | 14165 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 6 | 6 | 0 | 6 | 100% |  | #REF! | 0 | -6 |  | 0 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 62 | 38 | 100 | 100% |  | #REF! | 38 | -62 |  | 62 | 0% | 62% | 38% | 95% | 5% |  | 100%
|  | 140-IM-F1 |  |  | 0 | 0 | 0 | 66.25% |  | #REF! |  | 0 |  | 0 | 2.25% | 63.25% | 3% | 69.25% | -3% |  | 64%
|  | Handling | Kg | 36958 | 36958 | 0 | 36958 | 100% |  | #REF! | 35800 | -1158 |  | 35800 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 18 | 18 | 0 | 18 | 100% |  | #REF! | 20 | 2 |  | 20 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 36958 | 36958 | 0 | 36958 | 100% |  | #REF! | 34945 | -2013 |  | 35800.2 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 36958 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Bolt Tightening & Test | Kg | 36958 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | NO | 18 | 0 | 0 | 0 | 0% |  | #REF! | 0 | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final test & Documents | % | 100 | 55 | 20 | 75 | 75% |  | #REF! | 48 | -27 |  | 55 | 15% | 55% | 20% | 95% | -20% |  | 60%
|  | 140-IM-F2 |  |  | 0 | 0 | 0 | 100% |  | #REF! |  | 0 |  | 0 | 0% | 95.05% | 4.95% | 99.25% | 0.75% |  | 100%
|  | Handling | Kg | 57287 | 57287 | 0 | 57287 | 100% |  | #REF! | 54300 | -2987 |  | 54300 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Chip&Padding | NO | 22 | 22 | 0 | 22 | 100% |  | #REF! | 22 | 0 |  | 22 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Erection | Kg | 57287 | 57287 | 0 | 57287 | 100% |  | #REF! | 54300 | -2987 |  | 54300 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment | Kg | 57287 | 57287 | 0 | 57287 | 100% |  | #REF! | 0 | -57287 |  | 54300 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Bolt Tightening & Test | Kg | 57287 | 57287 | 0 | 57287 | 100% |  | #REF! | 0 | -57287 |  | 54300 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Grouting | NO | 22 | 22 | 0 | 22 | 100% |  | #REF! | 0 | -22 |  | 22 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Final test & Documents | % | 100 | 67 | 33 | 100 | 100% |  | #REF! | 55 | -45 |  | 67 | 0% | 67% | 33% | 95% | 5% |  | 100%
|  | Fireproofing |  |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Fireproofing | m2 | 200 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Insulation | ins |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cold Insulation | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hot Insulation | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Equipment Packages | equ |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Static Equipment |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP FLARE 140-X-101 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP FLARE 140-X-201 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LP FLARE 140-X-102 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LP FLARE 140-X-202 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | MP FLARE 140-X-103 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | MP FLARE 140-X-203 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Wet Flare K.O. Drum Heater 140-DH-101 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Wet Flare K.O. Drum Heater 140-DH-103 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Cold Flare K.O. Drum Heater 140-DH-104 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Wet Flare K.O. Drum Heater 140-DH-201 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | MP Flare K.O. Drum Heater 140-DH-203 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Cold Flare K.O. Drum Heater 140-DH-204 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Flare Stack K.O. Drum Heater 140-DH-105 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Flare Stack K.O. Drum Heater 140-DH-106 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Flare Stack K.O. Drum Heater 140-DH-205 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP Flare Stack K.O. Drum Heater 140-DH-206 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Rotary Equipment |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP FLARE STACKS PUMPS, 140-P-104A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP FLARE STACKS PUMPS, 140-P-104B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LP FLARE STACKS PUMPS, 140-P-105A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LP FLARE STACKS PUMPS, 140-P-105B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | MP FLARE STACKS PUMPS, 140-P-106A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | MP FLARE STACKS PUMPS, 140-P-106B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP FLARE STACKS PUMPS, 140-P-204A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HP FLARE STACKS PUMPS, 140-P-204B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LP FLARE STACKS PUMPS, 140-P-205A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LP FLARE STACKS PUMPS, 140-P-205B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | MP FLARE STACKS PUMPS, 140-P-206A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | MP FLARE STACKS PUMPS, 140-P-206B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation | Kg | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Unit 143 |  |  | 0 | 0 | 0 | 13.45% |  | #REF! |  | 0 |  | 0 | -9.454% | 18.81% | -5.359% | 19.06% | -5.606% |  | 22.91%
|  | Welding & NDT Procedures | pip |  | 0 | 0 | 0 | 29.6% |  | #REF! |  | 0 |  | 0 | -70.4% | 50.9% | -21.3% | 86.62% | -57.02% |  | 100%
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100% | 100% | -74% | 26% | 26% |  | #REF! | 100 | 99.74 |  | 100 | -74% | 100% | -74% | 100% | -74% |  | 100%
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100% | 100% | -74% | 26% | 26% |  | #REF! | 100 | 99.74 |  | 100 | -74% | 100% | -74% | 100% | -74% |  | 100%
|  | Qualification of Welding Equipments | % | 100% | 100% | -74% | 26% | 26% |  | #REF! | 100 | 99.74 |  | 100 | -74% | 100% | -74% | 100% | -74% |  | 100%
|  | Maintaining Welder Qualification Records | % | 100% | 100% | -74% | 26% | 26% |  | #REF! | 100 | 99.74 |  | 100 | -74% | 100% | -74% | 100% | -74% |  | 100%
|  | Monitoring Welder Performance | % | 100% | 100% | -74% | 26% | 26% |  | #REF! | 100 | 99.74 |  | 100 | -74% | 100% | -74% | 100% | -74% |  | 100%
|  | Prepare NDT Procedures & Obtain Certification | % | 100% | 50% | -12% | 38% | 38% |  | #REF! |  | -0.38 |  | 100 | -62% | 100% | -62% | 100% | -62% |  | 100%
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100% | 24% | 2% | 26% | 26% |  | #REF! |  | -0.26 |  | 20 | -74% | 20% | 6% | 45% | -19% |  | 100%
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100% | 24% | 2% | 26% | 26% |  | #REF! |  | -0.26 |  | 20 | -74% | 20% | 6% | 100% | -74% |  | 100%
|  | Perform NDT as per the Procedures | % | 100% | 24% | 2% | 26% | 26% |  | #REF! |  | -0.26 |  | 20 | -74% | 20% | 6% | 100% | -74% |  | 100%
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100% | 100% | -74% | 26% | 26% |  | #REF! | 100 | 99.74 |  | 100 | -74% | 100% | -74% | 100% | -74% |  | 100%
|  | Prepare PWHT Procedures & Obtain Certification | % | 100% | 0% | 26% | 26% | 26% |  | #REF! |  | -0.26 |  | 0 | -74% | 15% | 11% | 100% | -74% |  | 100%
|  | Perform PWHT Testing | % | 100% | 0% | 26% | 26% | 26% |  | #REF! |  | -0.26 |  | 0 | -74% | 15% | 11% | 50% | -24% |  | 100%
|  | Provide and maintain secure storage for radioactive sources | % | 100% | 24% | 2% | 26% | 26% |  | #REF! |  | -0.26 |  | 20 | -74% | 20% | 6% | 45% | -19% |  | 100%
|  | Implement specific safety procedures relating to radioactive sources | % | 100% | 100% | -74% | 26% | 26% |  | #REF! | 100 | 99.74 |  | 100 | -74% | 100% | -74% | 100% | -74% |  | 100%
|  | Piping | pip |  | 0 | 0 | 0 | 16.92% |  | #REF! |  | 0 |  | 0 | -7.146% | 23.46% | -6.539% | 19.25% | -2.335% |  | 24.06%
|  | AG Piping |  |  | 0 | 0 | 0 | 17.09% |  | #REF! |  | 0 |  | 0 | -7.22% | 23.7% | -6.607% | 19.45% | -2.359% |  | 24.31%
|  | Shop |  |  | 0 | 0 | 0 | 32.49% |  | #REF! |  | 0 |  | 0 | 2.03% | 30.46% | 2.03% | 32.64% | -0.1554% |  | 30.46%
|  | Carbon Steel |  |  | 0 | 0 | 0 | 46.22% |  | #REF! |  | 0 |  | 0 | 3% | 43.22% | 3% | 46.45% | -0.2297% |  | 43.22%
|  | Material Handling From Lay down To Shop | ID | 26984 | 17000 | 0 | 17000 | 63% |  | #REF! | 2000 | -15000 |  | 13966 | 0% | 63% | 0% | 51.76% | 11.24% |  | 63%
|  | Cutting & Bevelling & Fit Up | ID | 8095 | 4200 | 0 | 4200 | 51.88% |  | #REF! |  | -4200 |  | 4071 | 0% | 51.88% | 0% | 58.94% | -7.054% |  | 51.88%
|  | Welding | ID | 8095 | 4200 | 0 | 4200 | 51.88% |  | #REF! |  | -4200 |  | 2268 | 0% | 51.88% | 0% | 55.66% | -3.78% |  | 51.88%
|  | NDT | ID | 1619 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 8095 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 20 | 45 | 45% |  | #REF! | 25 | -20 |  | 25 | 20% | 25% | 20% | 25% | 20% |  | 25%
|  | Low Temperature CS |  |  | 0 | 0 | 0 | 3.75% |  | #REF! |  | 0 |  | 0 | 0% | 3.75% | 0% | 3.75% | 0% |  | 3.75%
|  | Material Handling From Lay down To Shop | ID | 93 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & Bevelling & Fit Up | ID | 28 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 28 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 28 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 28 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | Stainless Steel |  |  | 0 | 0 | 0 | 3.75% |  | #REF! |  | 0 |  | 0 | 0% | 3.75% | 0% | 3.75% | 0% |  | 3.75%
|  | Material Handling From Lay down To Shop | ID | 41 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & Bevelling & Fit Up | ID | 12 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 12 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 12 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 12 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | Galva |  |  | 0 | 0 | 0 | 3.75% |  | #REF! |  | 0 |  | 0 | 0% | 3.75% | 0% | 3.75% | 0% |  | 3.75%
|  | Material Handling From Lay down To Shop | ID | 1971 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & Bevelling & Fit Up | ID | 591 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 591 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 591 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 591 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | CU-NI |  |  | 0 | 0 | 0 | 3.75% |  | #REF! |  | 0 |  | 0 | 0% | 3.75% | 0% | 3.75% | 0% |  | 3.75%
|  | Material Handling From Lay down To Shop | ID | 5256 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & Bevelling & Fit Up | ID | 1577 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 1577 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 1577 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 1577 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | Field |  |  | 0 | 0 | 0 | 8.803% |  | #REF! |  | 0 |  | 0 | -12.2% | 20.06% | -11.26% | 12.35% | -3.546% |  | 21%
|  | Carbon Steel |  |  | 0 | 0 | 0 | 11.64% |  | #REF! |  | 0 |  | 0 | -12% | 23.12% | -11.49% | 14.93% | -3.292% |  | 23.63%
|  | Material Handling From Shop To Field | ID | 26984 | 14000 | 0 | 14000 | 51.88% |  | #REF! | 1072 | -12928 |  | 2888 | 0% | 51.88% | 0% | 23.72% | 28.16% |  | 51.88%
|  | Erection & Fit Up | ID | 18889 | 1942 | 0 | 1942 | 10.28% |  | #REF! | 756 | -1186 |  | 1827 | 0% | 10.28% | 0% | 16.04% | -5.755% |  | 10.28%
|  | Valve Installation | ID | 380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 18889 | 1342 | 378 | 1720 | 9.106% |  | #REF! | 756 | -964 |  | 875 | -0.2753% | 9.106% | 0% | 18.71% | -9.603% |  | 9.381%
|  | NDT | ID | 3777.8 | 540 | -432 | 108 | 2.859% |  | #REF! |  | -108 |  | 540 | -16.73% | 2.859% | 0% | 2.859% | 0% |  | 19.59%
|  | PWHT | ID | 18889 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 18889 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | Low Temperature CS |  |  | 0 | 0 | 0 | 2.874% |  | #REF! |  | 0 |  | 0 | -12.63% | 15.5% | -12.63% | 15.5% | -12.63% |  | 15.5%
|  | Material Handling From Shop To Field | ID | 93 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection & Fit Up | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 65 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | Stainless Steel |  |  | 0 | 0 | 0 | 2.874% |  | #REF! |  | 0 |  | 0 | -12.63% | 15.5% | -12.63% | 15.5% | -12.63% |  | 15.5%
|  | Material Handling From Shop To Field | ID | 41 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection & Fit Up | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 29 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | Galva |  |  | 0 | 0 | 0 | 2.874% |  | #REF! |  | 0 |  | 0 | -12.63% | 15.5% | -12.63% | 2.5% | 0.3736% |  | 15.5%
|  | Material Handling From Shop To Field | ID | 1971 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection & Fit Up | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 1380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | CU-NI |  |  | 0 | 0 | 0 | 2.874% |  | #REF! |  | 0 |  | 0 | -12.63% | 11.6% | -8.726% | 2.5% | 0.3736% |  | 15.5%
|  | Material Handling From Shop To Field | ID | 5256 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection & Fit Up | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 380 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 3679 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 25 | 0 | 25 | 25% |  | #REF! | 25 | 0 |  | 25 | 0% | 25% | 0% | 25% | 0% |  | 25%
|  | Pipe Support |  |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Shop |  |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Handling | Kg | 26579 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | shop drawing | Kg | 26579 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & assembling | Kg | 26579 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | Kg | 26579 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Field |  |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling From Shop To Field | Kg | 39869 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection | Kg | 39869 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | Kg | 39869 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | Kg | 39869 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Painting & Sandblasting | pan |  | 0 | 0 | 0 | 16.64% |  |  |  | 0 |  | 0 | 1.103% | 15.4% | 1.237% | 15.4% | 1.237% |  | 15.54%
|  | Pipe |  |  | 0 | 0 | 0 | 16.81% |  |  |  | 0 |  | 0 | 1.25% | 15.56% | 1.25% | 15.56% | 1.25% |  | 15.56%
|  | Sand Blast | m2 | 11000 | 4891 | 0 | 4891 | 44.46% |  |  | 3480 | -1411 |  | 4891 | 0% | 44.46% | 0% | 44.46% | 0% |  | 44.46%
|  | Primer | m2 | 11000 | 4891 | 0 | 4891 | 44.46% |  |  | 3480 | -1411 |  | 4891 | 0% | 44.46% | 0% | 44.46% | 0% |  | 44.46%
|  | Middle Paint | m2 | 11000 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Paint | m2 | 11000 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Touch Up & Punch | m2 | 11000 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 25 | 25 | 25% |  |  |  | -25 |  | 0 | 25% | 0% | 25% | 0% | 25% |  | 0%
|  | Support |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -13.12% | 0% | 0% | 0% | 0% |  | 13.12%
|  | Sand Blast | m2 | 400 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -37.5% | 0% | 0% | 0% | 0% |  | 37.5%
|  | Primer | m2 | 400 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | -37.5% | 0% | 0% | 0% | 0% |  | 37.5%
|  | Middle Paint | m2 | 400 | 0 | 0 |  | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Paint | m2 | 400 | 0 | 0 |  | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Touch Up & Punch | m2 | 400 | 0 | 0 |  | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 400 | 0 | 0 |  | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Insulation | ins |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cold Insulation | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hot Insulation | M2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Equipment Packages | equ |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Static Equipment |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Sump Drum 143-D-101 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Degassing Boot 143-D-102 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Rotary Equipment |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 143-P-101 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 143-P-102 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 143-P-103 A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 143-P-103 B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 143-P-103 C |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 143-P-104 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Unit 147/148 |  |  | 0 | 0 | 0 | 6.148% |  | #REF! |  | 0 |  | 0 | -8.42% | 7.898% | -1.75% | 10.4% | -4.253% |  | 14.57%
|  | Welding & NDT Procedures | pip |  | 0 | 0 | 0 | 20.1% |  | #REF! |  | 0 |  | 0 | -79.9% | 50.14% | -30.04% | 86.63% | -66.53% |  | 100%
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100% | 100% | -85% | 15% | 15% |  | #REF! | 100 | 99.85 |  | 100 | -85% | 100% | -85% | 100% | -85% |  | 100%
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100% | 100% | -85% | 15% | 15% |  | #REF! | 100 | 99.85 |  | 100 | -85% | 100% | -85% | 100% | -85% |  | 100%
|  | Qualification of Welding Equipments | % | 100% | 100% | -85% | 15% | 15% |  | #REF! | 100 | 99.85 |  | 100 | -85% | 100% | -85% | 100% | -85% |  | 100%
|  | Maintaining Welder Qualification Records | % | 100% | 100% | -85% | 15% | 15% |  | #REF! | 100 | 99.85 |  | 100 | -85% | 100% | -85% | 100% | -85% |  | 100%
|  | Monitoring Welder Performance | % | 100% | 100% | -85% | 15% | 15% |  | #REF! | 100 | 99.85 |  | 100 | -85% | 100% | -85% | 100% | -85% |  | 100%
|  | Prepare NDT Procedures & Obtain Certification | % | 100% | 50% | -18% | 32% | 32% |  | #REF! |  | -0.32 |  | 100 | -68% | 100% | -68% | 100% | -68% |  | 100%
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100% | 24% | -9% | 15% | 15% |  | #REF! |  | -0.15 |  | 20 | -85% | 20% | -5% | 45% | -30% |  | 100%
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100% | 24% | -9% | 15% | 15% |  | #REF! |  | -0.15 |  | 20 | -85% | 20% | -5% | 100% | -85% |  | 100%
|  | Perform NDT as per the Procedures | % | 100% | 24% | -9% | 15% | 15% |  | #REF! |  | -0.15 |  | 20 | -85% | 20% | -5% | 100% | -85% |  | 100%
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100% | 100% | -85% | 15% | 15% |  | #REF! | 100 | 99.85 |  | 100 | -85% | 100% | -85% | 100% | -85% |  | 100%
|  | Prepare PWHT Procedures & Obtain Certification | % | 100% | 0% | 15% | 15% | 15% |  | #REF! |  | -0.15 |  | 0 | -85% | 13% | 2% | 100% | -85% |  | 100%
|  | Perform PWHT Testing | % | 100% | 0% | 15% | 15% | 15% |  | #REF! |  | -0.15 |  | 0 | -85% | 13% | 2% | 50% | -35% |  | 100%
|  | Provide and maintain secure storage for radioactive sources | % | 100% | 24% | -9% | 15% | 15% |  | #REF! |  | -0.15 |  | 20 | -85% | 20% | -5% | 45% | -30% |  | 100%
|  | Implement specific safety procedures relating to radioactive sources | % | 100% | 100% | -85% | 15% | 15% |  | #REF! | 100 | 99.85 |  | 100.0001 | -85% | 100% | -85% | 100% | -85% |  | 100%
|  | Piping | pip |  | 0 | 0 | 0 | 8.691% |  | #REF! |  | 0 |  | 0 | -5.203% | 8.691% | 0% | 9.325% | -0.6348% |  | 13.89%
|  | AG Piping |  |  | 0 | 0 | 0 | 8.78% |  | #REF! |  | 0 |  | 0 | -5.257% | 8.78% | 0% | 9.422% | -0.6414% |  | 14.04%
|  | Shop |  |  | 0 | 0 | 0 | 17.66% |  | #REF! |  | 0 |  | 0 | -15.02% | 17.66% | 0% | 18.25% | -0.5892% |  | 32.68%
|  | Carbon Steel |  |  | 0 | 0 | 0 | 38.04% |  | #REF! |  | 0 |  | 0 | -161% | 38.04% | 0% | 81.33% | -43.3% |  | 199%
|  | Material Handling From Lay down To Shop | ID | 4934 | 2450 | 0 | 2450 | 49.66% |  | #REF! | 600 | -1850 |  | 1136.3002 | 0% | 49.66% | 0% | 45.32% | 4.337% |  | 49.66%
|  | Cutting & Bevelling & Fit Up | ID | 1480 | 4000 | -3375.625 | 624.375 | 42.19% |  | #REF! |  | -624.375 |  | 216.82 | -228.1% | 42.19% | 0% | 100% | -57.81% |  | 270.3%
|  | Welding | ID | 1480 | 4000 | -3375.625 | 624.375 | 42.19% |  | #REF! |  | -624.375 |  | 187 | -228.1% | 42.19% | 0% | 100% | -57.81% |  | 270.3%
|  | NDT | ID | 296 | 20 | -18.6786 | 1.3214 | 0.4464% |  | #REF! |  | -1.3214 |  | 0 | -26.58% | 0.4464% | 0% | 1.351% | -0.9049% |  | 27.03%
|  | PWHT | ID | 1480 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 60% | -20% |  | 40%
|  | Low Temperature CS |  |  | 0 | 0 | 0 | 16.02% |  | #REF! |  | 0 |  | 0 | 3.276% | 16.02% | 0% | 10.89% | 5.13% |  | 12.75%
|  | Material Handling From Lay down To Shop | ID | 36676 | 15000 | 0 | 15000 | 40.9% |  | #REF! |  | -15000 |  | 0 | 0% | 40.9% | 0% | 3.817% | 37.08% |  | 40.9%
|  | Cutting & Bevelling & Fit Up | ID | 11003 | 850 | 390 | 1240 | 11.27% |  | #REF! |  | -1240 |  | 0 | 3.544% | 11.27% | 0% | 7.725% | 3.544% |  | 7.725%
|  | Welding | ID | 11003 | 600 | 640 | 1240 | 11.27% |  | #REF! |  | -1240 |  | 0 | 5.817% | 11.27% | 0% | 5.453% | 5.817% |  | 5.453%
|  | NDT | ID | 11003 | 200 | 0 | 200 | 1.818% |  | #REF! |  | -200 |  | 0 | 0% | 1.818% | 0% | 1.818% | 0% |  | 1.818%
|  | PWHT | ID | 11003 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Galva |  |  | 0 | 0 | 0 | 6% |  | #REF! |  | 0 |  | 0 | 0% | 6% | 0% | 6% | 0% |  | 6%
|  | Material Handling From Lay down To Shop | ID | 544 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & Bevelling & Fit Up | ID | 163 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 163 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 163 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 163 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | GRE & Stainless Steel |  |  | 0 | 0 | 0 | 6% |  | #REF! |  | 0 |  | 0 | 0% | 6% | 0% | 6% | 0% |  | 6%
|  | Material Handling From Lay down To Shop | ID | 578 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & Bevelling & Fit Up | ID | 173 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 173 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 173 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 173 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Field |  |  | 0 | 0 | 0 | 4% |  | #REF! |  | 0 |  | 0 | 0% | 4% | 0% | 4.669% | -0.6695% |  | 4%
|  | Carbon Steel |  |  | 0 | 0 | 0 | 4% |  | #REF! |  | 0 |  | 0 | 0% | 4% | 0% | 4.52% | -0.52% |  | 4%
|  | Material Handling From Shop To Field | ID | 4934 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Scaffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 4% | -4% |  | 0%
|  | Erection & Fit Up | ID | 3454 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 611 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 4045 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 809 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 4045 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 4045 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Low Temperature CS |  |  | 0 | 0 | 0 | 4% |  | #REF! |  | 0 |  | 0 | 0% | 4% | 0% | 4.52% | -0.52% |  | 4%
|  | Material Handling From Shop To Field | ID | 36676 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Scaffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 4% | -4% |  | 0%
|  | Erection & Fit Up | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 611 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 25673 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Galva |  |  | 0 | 0 | 0 | 4% |  | #REF! |  | 0 |  | 0 | 0% | 4% | 0% | 4.52% | -0.52% |  | 4%
|  | Material Handling From Shop To Field | ID | 544 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Scaffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 4% | -4% |  | 0%
|  | Erection & Fit Up | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 611 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 381 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | GRE |  |  | 0 | 0 | 0 | 4% |  | #REF! |  | 0 |  | 0 | 0% | 4% | 0% | 17% | -13% |  | 4%
|  | Scoffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 100% | -100% |  | 0%
|  | Material Handling To Field | ID | 386 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection & Fittup | ID | 270 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Bonding | ID | 270 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 270 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Stainless Steel |  |  | 0 | 0 | 0 | 4% |  | #REF! |  | 0 |  | 0 | 0% | 4% | 0% | 4.52% | -0.52% |  | 4%
|  | Material Handling From Shop To Field | ID | 192 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Scaffolding | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 4% | -4% |  | 0%
|  | Erection & Fit Up | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Valve Installation | ID | 611 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PWHT | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hydro test | ID | 134 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 40 | 0 | 40 | 40% |  | #REF! | 40 | 0 |  | 40 | 0% | 40% | 0% | 40% | 0% |  | 40%
|  | Pipe Support |  |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Shop |  |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Handling | Kg | 37124 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | shop drawing | Kg | 37124 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cutting & assembling | Kg | 37124 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | Kg | 37124 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Field |  |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling From Shop To Field | Kg | 55687 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Erection | Kg | 55687 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Welding | Kg | 55687 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | NDT | Kg | 55687 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Painting & Sandblasting | pan |  | 0 | 0 | 0 | 13.41% |  |  |  | 0 |  | 0 | -18.89% | 12.32% | 1.09% | 12.32% | 1.09% |  | 32.31%
|  | Pipe |  |  | 0 | 0 | 0 | 13.55% |  |  |  | 0 |  | 0 | -19.09% | 12.45% | 1.101% | 12.45% | 1.101% |  | 32.64%
|  | Sand Blast | m2 | 5200 | 4850 | -3000 | 1850 | 35.58% |  |  | 415 | -1435 | 24 | 429 | -57.69% | 35.58% | 0% | 35.58% | 0% |  | 93.27%
|  | Primer | m2 | 5200 | 4850 | -3000 | 1850 | 35.58% |  |  | 415 | -1435 | 288 | 429 | -57.67% | 35.57% | 0.00684% | 35.57% | 0.00684% |  | 93.25%
|  | Middle Paint | m2 | 5200 | 0 | 0 | 0 | 0% |  |  |  | 0 | 414.72 | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Paint | m2 | 5200 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Touch Up & Punch | m2 | 5200 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 100 | 0 | 22 | 22 | 22% |  |  |  | -22 |  | 0 | 22% | 0% | 22% | 0% | 22% |  | 0%
|  | Support |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Sand Blast | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Primer | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Middle Paint | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Paint | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Touch Up & Punch | m2 | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Certificate | % | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Insulation | ins |  | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Cold Insulation | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Hot Insulation | m2 | 1 | 0 | 0 | 0 | 0% |  | #REF! |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Equipment Packages | equ |  | 0 | 0 | 0 | 0.1244% |  |  |  | 0 |  | 0 | 0% | 0.1244% | 0% | 0.1244% | 0% |  | 0.1244%
|  | Static Equipment |  |  | 0 | 0 | 0 | 0.9081% |  |  |  | 0 |  | 0 | 0% | 0.9081% | 0% | 0.9081% | 0% |  | 0.9081%
|  | Air cooler 147-A-101 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Vert.) 147-D-101 A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Vert.) 147-D-101 B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Vert.) 147-D-102 A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Vert.) 147-D-102 B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Vert.) 147-D-103 A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Vert.) 147-D-103 B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Hori) 147-D-104 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Vert.) 147-D-105 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Hori) 147-D-106 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Hori) 147-D-107 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Hori) 147-D-108 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Hori.) in Sump 147-D-109 |  |  | 0 | 0 | 0 | 44.88% |  |  |  | 0 |  | 0 | 0% | 44.88% | 0% | 44.88% | 0% |  | 44.88%
|  | Material Handling | Kg | 16440 | 16060 | 0 | 16060 | 97.69% |  |  |  | -16060 |  | 16060 | 0% | 97.69% | 0% | 97.69% | 0% |  | 97.69%
|  | Chipping & Padding | % | 100 | 100 | 0 | 100 | 100% |  |  |  | -100 |  | 100 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Installation |  | 16440 | 16440 | 0 | 16440 | 100% |  |  |  | -16440 |  | 16440 | 0% | 100% | 0% | 100% | 0% |  | 100%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Drum (Hori) on St. 147-D-110 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LP FLARE K.O. DRUM 147-D-111 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Electric Heater 147-DH-107 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Electric Heater 147-DH-108 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Electric Heater 147-DH-109 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Electric Heater 147-DH-110 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LPG TANK FLARE 147-X-101 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | LOW PRESSURE PROPANE CHILLER 147-E-101 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | MEDUIM PRESSURE PROPANE CHILLER 147-E-102 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | HIGH PRESSURE PROPANE CHILLER 147-E-103 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | PROPANE BOIL OFF GAS CONDENSER 147-E-104 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Rotary Equipment |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Compressor 147-K-101A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Compressor 147-K-101B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Compressor 147-K-102A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Compressor 147-K-102B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-101A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-101B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-101C |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-102 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-103A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-103B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-103C |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-104 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-106 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-107 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-108 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-109A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 147-P-109B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 148-P-101A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 148-P-101B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 148-P-101C |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 148-P-102 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 148-P-103A |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 148-P-103B |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 148-P-103C |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Pump 148-P-104 |  |  | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Material Handling |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Chipping & Padding |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Alignment |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Grouting |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | External Installation |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
|  | Final Inspection |  | 1 | 0 | 0 | 0 | 0% |  |  |  | 0 |  | 0 | 0% | 0% | 0% | 0% | 0% |  | 0%
[12 empty] | 0 |  |  | 0% |  | 0% |  | 0%
-203.2613
232049999999.9999
9825103953.4884
1761398233.3764
120317904475.3876
40837741910.0229
59307851427.7247

## QC (hidden)
South Pars Gas Field Development Phase 14 Package Number 2
|  | Cut Of Date : | 2014-05-01
Description |  |  | Quantity |  |  | FIN(Up To Last) |  | FIN(This Month) |  | Quantity Approved QC | Price
|  |  | Unit | Estimate | Work Performed | Date | No. | Date | No.
|  | Package NO.2 | [8 empty] | 273000000000
|  | Procurement | per | 0 | 0 | [5 empty] | #REF!
|  | fire proof | per | 0 | 0 | [5 empty] | #REF!
|  | PO Placement | m2 | 200 | 0
|  | Fabrication & Test | m2 | 200 | 0
|  | Delivery | m2 | 200 | 0
|  | Rebar | per | 0 | 0 | [5 empty] | #REF!
|  | PO Placement | Kg | 308693 | 308693
|  | Fabrication & Test | Kg | 308693 | 308693
|  | Delivery | Kg | 308693 | 308693
|  | Piping Support | per | 0 | 0 | [5 empty] | #REF!
|  | PO Placement | Kg | 80000 | 80000
|  | Fabrication & Test | Kg | 80000 | 80000
|  | Delivery | Kg | 80000 | 80000
|  | Cold Insulating | per | 0 | 0 | [5 empty] | #REF!
|  | PO Placement | m2 | 5862 | 0
|  | Fabrication & Test | m2 | 5862 | 0
|  | Delivery | m2 | 5862 | 0
|  | Warm Insulating | per | 0 | 0 | [5 empty] | #REF!
|  | PO Placement | m2 | 2937 | 2937
|  | Fabrication & Test | m2 | 2937 | 2937
|  | Delivery | m2 | 2937 | 2937
|  | Paint | per | 0 | 0 | [5 empty] | #REF!
|  | PO Placement | Kg | 57000 | 57000
|  | Delivery | Kg | 57000 | 57000
|  | Electrode | per | 0 | 0 | [5 empty] | #REF!
|  | PO Placement | Kg | 27000 | 27000
|  | Fabrication & Test | Kg | 27000 | 27000
|  | Delivery | Kg | 27000 | 27000
|  | Plant Construction |  | 0 | 0 | [5 empty] | #REF!
|  | General |  | 0 | 0 | [5 empty] | #REF!
|  | mobolization |  | 0 | 0 | [5 empty] | #REF!
|  | primary mobilozation | % | 100 | 100 | [5 empty] | #REF! |  | 100
|  | countiuse mobilization | % | 100 | 35 | [5 empty] | #REF! |  | 20
|  | Demobilizaton |  | 0 | 0 | [5 empty] | #REF!
|  | Demobilizaton | % | 100 | 50 | [5 empty] | #REF!
|  | Gate House | civ | 0 | 0 | [5 empty] | #REF!
|  | civil | civ | 0 | 0 | [5 empty] | #REF!
| ` | Foundation | % | 100 | 100 | [5 empty] | #REF! |  | 100
|  | columns | % | 100 | 100 | [5 empty] | #REF! |  | 100
|  | Wall | % | 100 | 100 | [5 empty] | #REF!
|  | Floor | % | 100 | 100 | [5 empty] | #REF!
|  | Roof | % | 100 | 100 | [5 empty] | #REF! |  | 75
|  | Mechanical | civ | 0 | 0 | [5 empty] | #REF!
|  | Piping | % | 100 | 0 | [5 empty] | #REF!
|  | Installation | % | 100 | 0 | [5 empty] | #REF!
|  | electrical | civ | 0 | 0 | [5 empty] | #REF!
|  | Cabling | % | 100 | 0 | [5 empty] | #REF!
|  | Installation | % | 100 | 0 | [5 empty] | #REF!
|  | telecom | civ | 0 | 0 | [5 empty] | #REF!
|  | telecom | % | 100 | 0 | [5 empty] | #REF!
|  | architect | civ | 0 | 0 | [5 empty] | #REF!
|  | architect | % | 100 | 0 | [5 empty] | #REF!
|  | final works | civ | 0 | 0 | [5 empty] | #REF!
|  | final works | % | 100 | 0 | [5 empty] | #REF!
|  | Unit 140 |  | 0 | 0 | [5 empty] | #REF!
|  | Welding & NDT Procedures | pip | 0 | 0 | [5 empty] | #REF!
|  | Prepare and qualify welding procedures (welding procedures qualfication tests (WPQT) including lab. Tests) for structural and pipe welding | % | 1 | 0.28 | [5 empty] | #REF! |  | 100
|  | Qualification of welders including lab testing for structural and pipe welding | % | 1 | 0.28 | [5 empty] | #REF! |  | 100
|  | Qualification of welding equipment | % | 1 | 0.28 | [5 empty] | #REF! |  | 100
|  | Maintaining welder qualification records | % | 1 | 0.28 | [5 empty] | #REF! |  | 100
|  | Monitoring welder performance | % | 1 | 0.28 | [5 empty] | #REF! |  | 100
|  | Prepare and NDT Procedures and obtain certification | % | 1 | 0.36 | [5 empty] | #REF!
|  | Qualification of NDT equipment and dimensional control (UT, RT, MT,...) | % | 1 | 0.28 | [5 empty] | #REF!
|  | Qualification of equipment operators for NDT and dimensional control | % | 1 | 0.28 | [5 empty] | #REF!
|  | Perform NDT as per the procedures | % | 1 | 0.28 | [5 empty] | #REF!
|  | Supply of associated Elec. Power, consumables, Materials construction equipments | % | 1 | 0.28 | [5 empty] | #REF! |  | 100
|  | Prepare PWHT procedure and obtain certification | % | 1 | 0.28 | [5 empty] | #REF!
|  | Perform PWHT testing | % | 1 | 0.28 | [5 empty] | #REF!
|  | Provide and maintain secure storage for radioactive sources | % | 1 | 0.28 | [5 empty] | #REF!
|  | Implement specific safety procedures relating to radioactive sources | % | 1 | 0.28 | [5 empty] | #REF! |  | 100
|  | Civil | civ | 0 | 0 | [5 empty] | #REF!
|  | Plat Form |  | 0 | 0 | [5 empty] | #REF!
|  | West HP |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 1983 | 1765 | [5 empty] | #REF! |  | 1385
|  | level&compact | m2 | 851 | 705 | [5 empty] | #REF! |  | 588
|  | lean | m3 | 36.57 | 32 | [5 empty] | #REF! |  | 40
|  | footing rebar | Kg | 33778 | 29400 | [5 empty] | #REF! |  | 25188
|  | footing form | m2 | 309 | 246 | [5 empty] | #REF! |  | 195
|  | foting concrete | m3 | 448 | 390 | 2/8/13 , 2/17/13 , 2/17/13 2/17/13 , 2/27/13 , 2/27/13,3/8/13 , 3/7/13 , 4/20/13 , 4/22/13 | 40002 , 40010 ,40012 40014 , 40024 , 40036 , 40042 , 40044 , 40068 , 40070 | 2/11/2013,29/10/2013, | 40083,40085,40125,40129,40131 |  | #REF! |  | 343
|  | ped rebar | Kg | 22520 | 20892 | [5 empty] | #REF! |  | 11666
|  | ped form | m2 | 376 | 306 | [5 empty] | #REF! |  | 225
|  | anchor | NO. | 418 | 335 | [5 empty] | #REF! |  | 98
|  | ped concrete | m3 | 146 | 130 | 3/7/13 , 3/7/13 , 3/7/13 , 3/7/13 , 4/27/13 , 4/27/13,7/9/2013 | 40046 , 40048 , 40050 40052 , 40082 , 40084,40092-2 |  |  |  | #REF! |  | 12
|  | curing | % | 100 | 60 | [5 empty] | #REF! |  | 75
|  | coating | m2 | 1174 | 864 | 9/12/2013 ,9/07/2013 | 60022-1,60023 |  |  |  | #REF! |  | 90
|  | back fill | m3 | 1402 | 1240 | 1/10/2013,07/10/2013,12/10/2013,17/10/2013, | 05070-1,05072-2,05073-2,05074-2,05075-2,05076-1,05077-2,05078-2,05084,05086-1,05089,05090,05091,05092,05093,05094,05095, |  |  |  | #REF! |  | 0
|  | Final Certificate | % | 100 | 86 | [5 empty] | #REF! |  | 45
|  | East HP |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 1983 | 1765 | [5 empty] | #REF! |  | 1358
|  | level&compact | m2 | 845 | 705 | [5 empty] | #REF! |  | 575
|  | lean | m3 | 36 | 32 | 2013-09-09 | 10044,10045 |  |  |  | #REF! |  | 39
|  | footing rebar | Kg | 33471 | 29750 | [5 empty] | #REF! |  | 26445
|  | footing form | m2 | 298 | 246 | [5 empty] | #REF! |  | 200
|  | foting concrete | m3 | 444 | 390 | 2/12/13 , 2/12/13 , 2/21/13,2/10/2013,06/10/2013 2/27/13 , 2/21/13 , 2/27/13 2/27/13 , 2/27/13 , 2/27/13 , 3/3/13 , 3/5/13 , 3/12/13 | 40004 , 40006 , 40016,40156-1,40156-2 40020 , 40022 , 40028 40030 , 40032 , 40034 , 40020-1 , 40040 , 40054 |  |  |  | #REF! |  | 358
|  | ped rebar | Kg | 21315 | 20892 | [5 empty] | #REF! |  | 12103
|  | ped form | m2 | 389 | 306 | [5 empty] | #REF! |  | 235
|  | anchor | NO. | 420 | 324 | [5 empty] | #REF! |  | 132
|  | ped concrete | m3 | 146 | 130 | 4/10/13 , 4/22/13 , 4/20/13 , 4/20/13 , 4/20/13 4/25/13,9/28/2013 | 40054 , 40058 , 40060 , 40062 , 40064 , 40076,40156 |  |  |  | #REF! |  | 60
|  | curing | % | 100 | 80 | [5 empty] | #REF! |  | 60
|  | coating | m2 | 1173 | 932 | [5 empty] | #REF! |  | 250
|  | back fill | m3 | 1406 | 1240 | 9/10/2013,9/02/2013,9/03/2013, 9/07/2013, 9/08/2013,9/19/2013, 9/27/2013 , 9/10/1513,02/10/2013,12/10/2013,03/10/2013,07/10/2013,19/10/2013,26/10/2013, 30/10/2013, | 05000,05002-3,05003, 05004-3, 05007-1,05008, 05010,05011 ,5012, 5013 ,5015 ,5019~5032, 5040~5048,5059~5066,,05111,05129,05130,05131,05132,05133,05134,05135,05136 ,05129,05130,05131,05132,05133,05134,05135,05136 |  |  |  | #REF! |  | 0
|  | Final Certificate | % | 100 | 88 | [5 empty] | #REF! |  | 45
|  | West LP |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 397 | 325 | [5 empty] | #REF! |  | 145
|  | level&compact | m2 | 218 | 175 | [5 empty] | #REF! |  | 99
|  | lean | m3 | 7 | 5 | [5 empty] | #REF! |  | 5
|  | footing rebar | Kg | 7260 | 6154 | [5 empty] | #REF! |  | 6702
|  | footing form | m2 | 100 | 65 | [5 empty] | #REF! |  | 71
|  | foting concrete | m3 | 65 | 45 | 2/28/2013 , 4/20/2013 | 40024 , 40066 |  |  |  | #REF! |  | 18
|  | ped rebar | Kg | 4840 | 3389 | [5 empty] | #REF! |  | 2300
|  | ped form | m2 | 107 | 85 | [5 empty] | #REF! |  | 41
|  | anchor | NO. | 120 | 95 | [5 empty] | #REF! |  | 29
|  | ped concrete | m3 | 35 | 28 | 4/25/13 , 4/25/13 | 40078 , 40080 |  |  |  | #REF! |  | 21
|  | curing | % | 100 | 60 | [5 empty] | #REF! |  | 40
|  | coating | m2 | 384 | 287 | 2013-09-07 | 60024 |  |  |  | #REF! |  | 0
|  | back fill | m3 | 296 | 210 | 17/10/2013,09/10/2013, | 05079-2,05080-2,05081-2,05083-1, | may13, | 05121,05122,05123,05124,05125,05126,05127,05128,05137,05138,05139 |  | #REF! |  | 0
|  | Final Certificate | % | 100 | 76 | [5 empty] | #REF! |  | 39
|  | East LP |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 397 | 397 | [5 empty] | #REF! |  | 214
|  | level&compact | m2 | 218 | 218 | [5 empty] | #REF! |  | 138
|  | lean | m3 | 7 | 0 | [5 empty] | #REF!
|  | footing rebar | Kg | 7260 | 0 | [5 empty] | #REF!
|  | footing form | m2 | 102 | 0 | [5 empty] | #REF!
|  | foting concrete | m3 | 65 | 0 | [5 empty] | #REF!
|  | ped rebar | Kg | 4840 | 0 | [5 empty] | #REF!
|  | ped form | m2 | 107 | 0 | [5 empty] | #REF!
|  | anchor | NO. | 120 | 0 | [5 empty] | #REF!
|  | ped concrete | m3 | 35 | 0 | [5 empty] | #REF!
|  | curing | % | 100 | 0 | [5 empty] | #REF!
|  | coating | m2 | 384 | 0 | [5 empty] | #REF!
|  | back fill | m3 | 296 | 0 | 9/5/2013,9/16/2013,9/11/2013,9/20/2013,9/21/2013, 9/24/2013,15/10/2013,31/10/2013,05/11/2013,10/11/2013 | 5005,5006,5016,5017,5018,5034,5035,5048,5049,5050,5056,5057,5058,05088-2,05112-1,05115,05118 |  |  |  | #REF!
|  | Final Certificate | % | 100 | 12 | [5 empty] | #REF! |  | 10
|  | Retaining wall |  | 0 | 0 | [5 empty] | #REF!
|  | Retaining wall 7 |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 2750 | 2750 | [5 empty] | #REF!
|  | level&compact | m2 | 275 | 275 | [5 empty] | #REF!
|  | lean | m3 | 46 | 0 | [5 empty] | #REF!
|  | footing rebar | Kg | 54855 | 0
|  | footing form | m2 | 200 | 0
|  | foting concrete | m3 | 400 | 0
|  | Wall rebar | Kg | 18285 | 0
|  | Wall form | m2 | 760 | 0 | [5 empty] | #REF!
|  | Wall concrete | m3 | 370 | 0 | [5 empty] | #REF!
|  | curing | % | 100 | 0 | [5 empty] | #REF!
|  | coating | m2 | 1206 | 0 | [5 empty] | #REF!
|  | back fill | m3 | 4000 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 12 | [5 empty] | #REF!
|  | Retaining wall 9 |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 316 | 316 | [5 empty] | #REF! |  | 316
|  | level&compact | m2 | 128 | 128 | [5 empty] | #REF! |  | 128
|  | lean | m3 | 4 | 4 | [5 empty] | #REF! |  | 4
|  | footing rebar | Kg | 10025 | 10025 | [5 empty] | #REF! |  | 10025
|  | footing form | m2 | 45 | 45 | [7 empty] | 20
|  | foting concrete | m3 | 58 | 58 | 6/13/2013,7/20/2013 | 40074,40072-2
|  | Wall rebar | Kg | 10100 | 10100
|  | Wall form | m2 | 195 | 195
|  | Wall concrete | m3 | 56 | 56 | 7/10/2013 , 7/21/2013,29/10/2013 7/25/2013 , 7/31/2013 | 40102 , 40108 , 40414,40119,40123 40118 |  |  |  | #REF!
|  | curing | % | 100 | 100 | [5 empty] | #REF!
|  | coating | m2 | 145 | 145 | 2013-09-03 | 60012-2,60013-2 |  |  |  | #REF!
|  | back fill | m3 | 166 | 83 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 95 | [5 empty] | #REF! |  | 20
|  | Retaining wall 11 |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 850 | 850 | [5 empty] | #REF!
|  | level&compact | m2 | 55 | 55 | [5 empty] | #REF!
|  | lean | m3 | 3.4 | 0
|  | footing rebar | Kg | 8400 | 0
|  | footing form | m2 | 50 | 0
|  | foting concrete | m3 | 73 | 0
|  | Wall rebar | Kg | 2800 | 0 | [5 empty] | #REF!
|  | Wall form | m2 | 159 | 0 | [5 empty] | #REF!
|  | Wall concrete | m3 | 76 | 0 | [5 empty] | #REF!
|  | curing | % | 100 | 0 | [5 empty] | #REF!
|  | coating | m2 | 251 | 0 | [5 empty] | #REF!
|  | back fill | m3 | 1500 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 12 | [5 empty] | #REF!
|  | Retaining wall 12 |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 316 | 316 | [5 empty] | #REF! |  | 316
|  | level&compact | m2 | 128 | 128 | [5 empty] | #REF! |  | 128
|  | lean | m3 | 5 | 5
|  | footing rebar | Kg | 10025 | 10025
|  | footing form | m2 | 45 | 45
|  | foting concrete | m3 | 50 | 50 | 2013-07-01 | 40098,40100
|  | Wall rebar | Kg | 10100 | 10100 | [5 empty] | #REF!
|  | Wall form | m2 | 195 | 195 | [5 empty] | #REF!
|  | Wall concrete | m3 | 64 | 64 | 7/16/13 , 7/21/13 ,7/23/13 7/25/13 , 7/31/13,29/10/2013 | 40104 , 40110 , 40112,40113,40121, 40116 , 40120 |  |  |  | #REF!
|  | curing | % | 100 | 100 | [5 empty] | #REF!
|  | coating | m2 | 145 | 145 | 2013-09-03 | 60010-2,60011-2 |  |  |  | #REF!
|  | back fill | m3 | 166 | 166 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 100 | [5 empty] | #REF! |  | 8
|  | Retaining wall 13 |  | 0 | 0 | [5 empty] | #REF!
|  | excavation | m3 | 600 | 600 | [5 empty] | #REF!
|  | level&compact | m2 | 58 | 58 | [5 empty] | #REF!
|  | lean | m3 | 2.6 | 2.6
|  | footing rebar | Kg | 6826 | 6826
|  | footing form | m2 | 29 | 29
|  | foting concrete | m3 | 35 | 35 | 2/10/2013,23/10/2013 | 40162-40170-1&2,
|  | Wall rebar | Kg | 2275 | 1100 | [5 empty] | #REF!
|  | Wall form | m2 | 103 | 52 | [5 empty] | #REF!
|  | Wall concrete | m3 | 28 | 0 | [5 empty] | #REF!
|  | curing | % | 100 | 0 | [5 empty] | #REF!
|  | coating | m2 | 150 | 0 | [5 empty] | #REF!
|  | back fill | m3 | 1000 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 75 | [5 empty] | #REF!
|  | Base |  | 0 | 0
|  | Base | m3 | 560 | 0
|  | Piping | pip | 0 | 0 | [5 empty] | #REF!
|  | AG Piping |  | 0 | 0 | [5 empty] | #REF!
|  | Shop |  | 0 | 0 | [5 empty] | #REF!
|  | Carbon Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 42944 | 25598 | [5 empty] | #REF! |  | 3390
|  | Cutting & Bevelling & Fit Up | ID | 12883 | 6933 | 7/10/13 , 7/16/13 , 7/23/13,09/11/2013,05/11/2013,28/10/2013,20/10/2013,12/10/2013,05/10/2013, 7/29/13,09/04/13 ,09/28/13 ,09/25/13 ,09/21/13 ,09/18/13 ,09/10/13 , | 00025 , 00026 , 00028 ,,00086,00080,00077,00071,00064,00059,0096,00096 00030,00043,00055,00053,00049,00047,00045,00043 |  |  |  | #REF!
|  | Welding | ID | 12883 | 5800 | 7/10/13 , 7/16/13 , 7/23/13,2/10/2013,12/10/2013,20/10/2013,28/10/2013,9/11/2013,05/11/2013,05/11/2013,28/10/2013,20/10/2013,05/10/2013, 7/29/13,09/04/13 ,09/28/13 ,09/25/13 ,09/21/13 ,09/18/13 ,09/10/13 , | 00024 , 00027 , 00029,00058,00067,00070,00076,00089,00083,00081,00074,00068,00065,00060,00054,00048,00105 00031,00056-00054-00050-00048-00046-00044 |  |  |  | #REF!
|  | NDT | ID | 2576.6 | 3.4 | 22/09/2013,3/09/2013,27/08/2013,9/10/2013,6/10/2013,13/10/2013,28/10/2013,29/10/2013,20/10/2013,07/10/2013 | 00051,00042,00039,00090,00084,000,00078~85,00079,,00073,,00072,,00063 |  |  |  | #REF!
|  | PWHT | ID | 12883 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 20
|  | Low Temperature CS |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 27889 | 1248 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 8367 | 232 | [5 empty] | #REF!
|  | Welding | ID | 8367 | 232 | 7/10/13 , 7/16/13 , 7/23/13 7/29/13,09/04/13 ,09/28/13 ,09/25/13 ,09/21/13 ,09/18/13 ,09/10/13 , | 00024 , 00027 , 00029 00031,00056-00054-00050-00048-00046-00044 | 5/10/2013,9/10/2013,28/10/2013,20/10/2013,12/10/2013,2/10/2013,5/10/2013, | 00083,00089,00076,00070,00067,00062,00058,00 |  | #REF!
|  | NDT | ID | 8367 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 1 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 20 | [5 empty] | #REF! |  | 20
|  | Stainless Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 13845 | 0 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 4154 | 0 | [5 empty] | #REF!
|  | Welding | ID | 4154 | 0 | [5 empty] | #REF!
|  | NDT | ID | 4154 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 4154 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 20 | [5 empty] | #REF! |  | 20
|  | Galva |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 2645 | 2645 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 794 | 181.9583 | [5 empty] | #REF!
|  | Welding | ID | 794 | 181.9583 | [5 empty] | #REF!
|  | NDT | ID | 794 | 181.9583 | [5 empty] | #REF!
|  | PWHT | ID | 794 | 181.9583 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 30 | [5 empty] | #REF! |  | 20
|  | Field |  | 0 | 0 | [5 empty] | #REF!
|  | Carbon Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 42944 | 22000 | [5 empty] | #REF! |  | 452
|  | Scaffolding | m2 | 8000 | 7349 | [5 empty] | #REF! |  | 2350
|  | Erection & Fit Up | ID | 30060 | 3619 | 5/26/13 , 5/19/13 , 6/5/13 , 6/12/13 , 6/23/13 , 6/30/13 , 7/10/13 , 7/16/13 , 7/23/13 7/29/13 | 00014 , 00009 , 00015 , 00017 , 00019, 00021 , 00025 , 00026 , 00028 ,00057,00061,00066,,00069,00075,00082,00088,09/11/2013,05/11/2013,28/10/2013,20/10/2013,12/10/2013,05/10/2013,02/10/2013, 00030 | 19/04/2014 | ,0096 |  | #REF! |  | 452
|  | Valve Installation | ID | 280 | 0 | [5 empty] | #REF!
|  | Welding | ID | 30060 | 2970 | 7/10/13 , 7/16/13 , 7/23/13,5/10/2013 7/29/13,09/04/13 ,09/28/13 ,09/25/13 ,09/21/13 ,09/18/13 ,09/10/13 , | 00024 , 00027 , 00029,00062, 00031,00056-00054-00050-00048-00046-00044 | 26/04/2014 | 105 |  | #REF! |  | 408
|  | NDT | ID | 6012 | 144.4 | 22/09/2013,3/09/2013,27/08/2013,9/10/2013,6/10/2013,13/10/2013,28/10/2013,29/10/2013,20/10/2013,07/10/2013 | 00051,00042,00039,00090,00084,000,00078~85,00079,,00073,,00072,,00063, | 26/04/2014 | 00101 |  | #REF!
|  | PWHT | ID | 30060 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 30060 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Low Temperature CS |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 27889 | 10000 | [5 empty] | #REF!
|  | Scaffolding | m2 | 8000 | 7349 | [5 empty] | #REF! |  | 2350
|  | Erection & Fit Up | ID | 19522 | 1864 | [5 empty] | #REF!
|  | Valve Installation | ID | 280 | 0 | [5 empty] | #REF!
|  | Welding | ID | 19522 | 1864 | 2013-05-10 | 00062 |  |  |  | #REF!
|  | NDT | ID | 19522 | 1008 | 22/09/2013,3/09/2013,27/08/2013,9/10/2013,6/10/2013,13/10/2013,28/10/2013,29/10/2013,20/10/2013,07/10/2013 | 00051,00042,00039,00090,00084,000,00078~85,00079,,00073,,00072,,00063 |  |  |  | #REF!
|  | PWHT | ID | 19522 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 19522 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Stainless Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 13845 | 0 | [5 empty] | #REF!
|  | Scaffolding | m2 | 8000 | 7349 | [5 empty] | #REF! |  | 2350
|  | Erection & Fit Up | ID | 9692 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 280 | 0 | [5 empty] | #REF!
|  | Welding | ID | 9692 | 0 | [5 empty] | #REF!
|  | NDT | ID | 9692 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 9692 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 9692 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Galva |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 2645 | 2645 | [5 empty] | #REF!
|  | Scaffolding | m2 | 8000 | 7349 | [5 empty] | #REF! |  | 2350
|  | Erection & Fit Up | ID | 1852 | 424.4167 | [5 empty] | #REF!
|  | Valve Installation | ID | 280 | 64.1667 | [5 empty] | #REF!
|  | Welding | ID | 1852 | 424.4167 | [5 empty] | #REF!
|  | NDT | ID | 1852 | 424.4167 | [5 empty] | #REF!
|  | PWHT | ID | 1852 | 424.4167 | [5 empty] | #REF!
|  | Hydro test | ID | 1852 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Pipe Support |  | 0 | 0 | [5 empty] | #REF!
|  | Shop |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 60354.4 | 43200 | [5 empty] | #REF!
|  | shop drawing | Kg | 60354.4 | 43200 | [5 empty] | #REF!
|  | Cutting & assembling | Kg | 60354.4 | 43200 | [5 empty] | #REF!
|  | Welding | Kg | 60354.4 | 43200 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 21 | [5 empty] | #REF!
|  | Field |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | Kg | 90531.6 | 43200 | [5 empty] | #REF!
|  | Erection | Kg | 90531.6 | 0 | [5 empty] | #REF!
|  | Welding | Kg | 90531.6 | 0 | [5 empty] | #REF!
|  | NDT | Kg | 90531.6 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 12 | [5 empty] | #REF!
|  | Painting & Sandblasting | pan | 0 | 0
|  | Pipe |  | 0 | 0
|  | Sand Blast | m2 | 39250 | 21000 | 2013-05-08 | 00003 | [5 empty] | 0
|  | Primer | m2 | 39250 | 21000 | 5/8/2013 , 7/5/13 , 7/12/13 , 7/19/13,9/7/13 , 9/13/13 , 9/20/13 ,9/27/13,9/04/2014,26/04/2014 | 00003, 00013 , 00014 , 00016,00021~00025,00043~00046 | [5 empty] | 0
|  | Middle Paint | m2 | 39250 | 0
|  | Final Paint | m2 | 39250 | 0
|  | Touch Up & Punch | m2 | 39250 | 0
|  | Final Certificate | % | 100 | 20
|  | Support |  | 0 | 0
|  | Sand Blast | m2 | 800 | 0
|  | Primer | m2 | 800 | 0
|  | Middle Paint | m2 | 800 | 0
|  | Final Paint | m2 | 800 | 0
|  | Touch Up & Punch | m2 | 800 | 0
|  | Final Certificate | % | 100 | 0
|  | Steel Structure | str | 0 | 0 | [5 empty] | #REF!
|  | Installation Steel Structure |  | 0 | 0 | [5 empty] | #REF!
|  | 140-IM-A1 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 93233 | 93233 | [5 empty] | #REF! | 94004 | 94004
|  | Chip&Padding | NO | 14 | 14 | 2012-12-05 | 00001 |  |  |  | #REF! | 14 | 14
|  | Erection | Kg | 93233 | 93233 | [5 empty] | #REF! | 94004 | 94004
|  | Alignment | Kg | 93233 | 93233 | 2013-05-08 | 00041 |  |  |  | #REF! | 94004 | 94004
|  | Bolt Tightening & Test | Kg | 93233 | 93233 | 2013-05-27 | 00047-4 |  |  |  | #REF! | 94004 | 94004
|  | Grouting | NO | 14 | 14 | 2013-05-30 | 00035 |  |  |  | #REF! | 14 | 14
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 62 | 62
|  | 140-IM-A2 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 135196 | 135196 | [5 empty] | #REF! | 136607 | 136607
|  | Chip&Padding | NO | 14 | 14 | 2012-12-07 | 00002 |  |  |  | #REF! | 16 | 16
|  | Erection | Kg | 135196 | 135196 | [5 empty] | #REF! | 136607 | 136607
|  | Alignment | Kg | 135196 | 135196 | 2013-03-02 | 00040 |  |  |  | #REF! | 136607 | 136607
|  | Bolt Tightening & Test | Kg | 135196 | 135196 | 2013-03-05 | 00047 |  |  |  | #REF! | 136607 | 136607
|  | Grouting | NO | 14 | 14 | 2013-03-06 | 00049 |  |  |  | #REF! | 16 | 16
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 63 | 63
|  | 140-IM-A3 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 83004 | 83004 | [5 empty] | #REF! | 80800 | 80800
|  | Chip&Padding | NO | 16 | 16 | 2012-12-10 | 00003 |  |  |  | #REF! | 16 | 16
|  | Erection | Kg | 83004 | 83004 | [5 empty] | #REF! | 80800 | 80800
|  | Alignment | Kg | 83004 | 83004 | 2013-03-03 | 00019 |  |  |  | #REF! | 80800 | 80800
|  | Bolt Tightening & Test | Kg | 83004 | 83004 | 2013-03-06 | 00048 |  |  |  | #REF! | 80800 | 80800
|  | Grouting | NO | 16 | 16 | 2013-03-07 | 00050 |  |  |  | #REF! | 16 | 16
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 63 | 63
|  | 140-IM-A4 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 62652 | 62652 | [5 empty] | #REF! | 62652 | 62652
|  | Chip&Padding | NO | 14 | 14 | 2012-12-10 | 00004 |  |  |  | #REF! | 14 | 14
|  | Erection | Kg | 62652 | 62652 | [5 empty] | #REF! | 62652 | 62652
|  | Alignment | Kg | 62652 | 62652 | 2013-04-09 | 00032 |  |  |  | #REF! | 62652 | 62652
|  | Bolt Tightening & Test | Kg | 62652 | 62652 | 2013-05-20 | 00082-1 |  |  |  | #REF! | 62652 | 62652
|  | Grouting | NO | 14 | 14 | 2013-05-22 | 00083-1 |  |  |  | #REF! | 14 | 14
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 62 | 62
|  | 140-IM-A5 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 179726 | 179726 | [5 empty] | #REF! | 179726 | 179726
|  | Chip&Padding | NO | 32 | 32 | 2012-12-12 | 00005 |  |  |  | #REF! | 32 | 32
|  | Erection | Kg | 179726 | 179726 | [5 empty] | #REF! | 179726 | 179726
|  | Alignment | Kg | 179726 | 179726 | 2013-02-06 | 00033 |  |  |  | #REF! | 179726 | 179726
|  | Bolt Tightening & Test | Kg | 179726 | 179726 | 2013-03-19 | 00037 |  |  |  | #REF! | 179726 | 179726
|  | Grouting | NO | 32 | 32 | 2013-02-21 | 00038 |  |  |  | #REF! | 32 | 32
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 64 | 64
|  | 140-IM-A6 & A6-1 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 160153 | 159708.8393 | [5 empty] | #REF! | 135200 | 135200
|  | Chip&Padding | NO | 85 | 85 | 2012-12-14 | 00006 |  |  |  | #REF! | 33 | 33
|  | Erection | Kg | 160153 | 159708.8393 | [5 empty] | #REF! | 135199 | 135199
|  | Alignment | Kg | 160153 | 159708.8393 |  | 00034 |  |  |  | #REF! | 135199 | 135199
|  | Bolt Tightening & Test | Kg | 160153 | 159708.8393 | 2013-02-20 | 00039 |  |  |  | #REF! | 135199 | 135199
|  | Grouting | NO | 85 | 85 | 2013-02-28 | 00040 |  |  |  | #REF! | 33 | 33
|  | Final test & Documents | % | 100 | 99 | [5 empty] | #REF! | 64 | 64
|  | 140-IM-A7 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 58446 | 58446 | [5 empty] | #REF! | 58446 | 58446
|  | Chip&Padding | NO | 16 | 8 | [5 empty] | #REF! | 8 | 8
|  | Erection | Kg | 58446 | 0 | [5 empty] | #REF! | 0 | 0
|  | Alignment | Kg | 58446 | 0 | [5 empty] | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 58446 | 0 | [5 empty] | #REF! | 0 | 0
|  | Grouting | NO | 16 | 0 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 25 | [5 empty] | #REF! | 10 | 10
|  | 140-IM-B1 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 65946 | 63311.1216 | [5 empty] | #REF! | 64131 | 64131
|  | Chip&Padding | NO | 10 | 0 | [5 empty] | #REF! | 0 | 0
|  | Erection | Kg | 65946 | 0 | [5 empty] | #REF! | 0 | 0
|  | Alignment | Kg | 65946 | 0 | [5 empty] | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 65946 | 0 | [5 empty] | #REF! | 0 | 0
|  | Grouting | NO | 10 | 0 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 20 | [5 empty] | #REF! | 7 | 7
|  | 140-IM-B2 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 171694 | 170741 | [5 empty] | #REF! | 170741 | 170741
|  | Chip&Padding | NO | 12 | 0 | [5 empty] | #REF! | 0 | 0
|  | Erection | Kg | 171694 | 0 | [5 empty] | #REF! | 0 | 0
|  | Alignment | Kg | 171694 | 0 | [5 empty] | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 171694 | 0 | [5 empty] | #REF! | 0 | 0
|  | Grouting | NO | 12 | 0 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 20 | [5 empty] | #REF! | 7 | 7
|  | 140-IM-B3 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 169239 | 169239 | [5 empty] | #REF! | 167795 | 167795
|  | Chip&Padding | NO | 28 | 28 | 2013-01-08 | 00025 |  |  |  | #REF! | 28 | 28
|  | Erection | Kg | 169239 | 169239 | [5 empty] | #REF! | 165941 | 165941
|  | Alignment | Kg | 169239 | 169239 | 2013-05-28 | 00059 |  |  |  | #REF! | 167795 | 167795
|  | Bolt Tightening & Test | Kg | 169239 | 169239 | 2013-06-01 | 00096 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 28 | 28 | 2013-06-13 | 00102 |  |  |  | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 48 | 48
|  | 140-IM-B4 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 115066 | 115066 | [5 empty] | #REF! | 115066 | 115066
|  | Chip&Padding | NO | 20 | 20 | 2012-12-16 | 00007 |  |  |  | #REF! | 20 | 20
|  | Erection | Kg | 115066 | 114950.6 | [5 empty] | #REF! | 113646 | 113646
|  | Alignment | Kg | 115066 | 114951 | 2013-04-30 | 00056 |  |  |  | #REF! | 113646 | 113646
|  | Bolt Tightening & Test | Kg | 115066 | 114951 | 2013-05-09 | 00076 |  |  |  | #REF! | 113646 | 113646
|  | Grouting | NO | 20 | 20 | 2013-05-09 | 00078 |  |  |  | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 99 | [5 empty] | #REF! | 54 | 54
|  | 140-IM-B5 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 72007 | 72007 | [5 empty] | #REF! | 72293 | 72293
|  | Chip&Padding | NO | 10 | 10 | 2012-12-18 | 00008 |  |  |  | #REF! | 10 | 10
|  | Erection | Kg | 72007 | 71935 | [5 empty] | #REF! | 72293 | 72293
|  | Alignment | Kg | 72007 | 71935 | 2013-04-17 | 00057 |  |  |  | #REF! | 72293 | 72293
|  | Bolt Tightening & Test | Kg | 72007 | 71935 | 2013-04-27 | 00067 |  |  |  | #REF! | 72293 | 72293
|  | Grouting | NO | 10 | 10 | 2013-05-02 | 00070 |  |  |  | #REF! | 10 | 10
|  | Final test & Documents | % | 100 | 99 | [5 empty] | #REF! | 55 | 55
|  | 140-IM-B6 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 161771 | 161771 | [5 empty] | #REF! | 161544 | 161544
|  | Chip&Padding | NO | 26 | 26 | 2012-12-18 | 00009 |  |  |  | #REF! | 26 | 26
|  | Erection | Kg | 161771 | 161544.3 | [5 empty] | #REF! | 161544 | 161544
|  | Alignment | Kg | 161771 | 161544 | 2013-04-20 | 00058 |  |  |  | #REF! | 161544 | 161544
|  | Bolt Tightening & Test | Kg | 161771 | 161544 | 2013-04-27 | 00068 |  |  |  | #REF! | 161544 | 161544
|  | Grouting | NO | 26 | 26 | 2013-05-02 | 00071 |  |  |  | #REF! | 26 | 26
|  | Final test & Documents | % | 100 | 99 | [5 empty] | #REF! | 62 | 62
|  | 140-IM-B7 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 85977 | 85977 | [5 empty] | #REF! | 85857 | 85857
|  | Chip&Padding | NO | 12 | 12 | 2012-12-20 | 00010 |  |  |  | #REF! | 12 | 12
|  | Erection | Kg | 85977 | 85876.7 | [5 empty] | #REF! | 83375 | 83375
|  | Alignment | Kg | 85977 | 85877 | 2013-04-14 | 00054 |  |  |  | #REF! | 83375 | 83375
|  | Bolt Tightening & Test | Kg | 85977 | 85877 | 2013-04-23 | 00061 |  |  |  | #REF! | 83375 | 83375
|  | Grouting | NO | 12 | 12 | 2013-04-27 | 00063 |  |  |  | #REF! | 12 | 12
|  | Final test & Documents | % | 100 | 99 | [5 empty] | #REF! | 61 | 61
|  | 140-IM-B8 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 98013 | 98013 | [5 empty] | #REF! | 97681 | 97681
|  | Chip&Padding | NO | 12 | 12 | 2012-12-20 | 00011 |  |  |  | #REF! | 12 | 12
|  | Erection | Kg | 98013 | 97714 | [5 empty] | #REF! | 97320 | 97320
|  | Alignment | Kg | 98013 | 97714 | 2013-04-19 | 00055 |  |  |  | #REF! | 97320 | 97320
|  | Bolt Tightening & Test | Kg | 98013 | 97714 | 2013-04-22 | 00062 |  |  |  | #REF! | 97320 | 97320
|  | Grouting | NO | 12 | 12 | 2013-04-27 | 00064 |  |  |  | #REF! | 12 | 12
|  | Final test & Documents | % | 100 | 99 | [5 empty] | #REF! | 62 | 62
|  | 140-IM-B9 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 59041 | 59041 | [5 empty] | #REF! | 59500 | 59500
|  | Chip&Padding | NO | 8 | 8 | 2012-12-20 | 00012 |  |  |  | #REF! | 8 | 8
|  | Erection | Kg | 59041 | 59041 | [5 empty] | #REF! | 59500 | 59500
|  | Alignment | Kg | 59041 | 59041 | 2013-04-30 | 00060 |  |  |  | #REF! | 59500 | 59500
|  | Bolt Tightening & Test | Kg | 59041 | 59041 | 2013-05-10 | 00077 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 8 | 8 | 2013-05-12 | 00080 |  |  |  | #REF! | 8 | 8
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 62 | 62
|  | 140-IM-B10 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 101233 | 101233 | [5 empty] | #REF! | 101700 | 101700
|  | Chip&Padding | NO | 12 | 12 | 2013-01-03 | 00017 |  |  |  | #REF! | 12 | 12
|  | Erection | Kg | 101233 | 80030.8083 | [5 empty] | #REF! | 80400 | 80400
|  | Alignment | Kg | 101233 | 80030.8083 | 2013-05-29 | 00066 |  |  |  | #REF! | 80400 | 80400
|  | Bolt Tightening & Test | Kg | 101233 | 63898.2298 | 2013-07-02 | 00110 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 12 | 7 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 90 | [5 empty] | #REF! | 42 | 42
|  | 140-IM-B11 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 142969 | 142969 | [5 empty] | #REF! | 142783 | 142783
|  | Chip&Padding | NO | 24 | 24 | 2013-01-03 | 00018 |  |  |  | #REF! | 24 | 24
|  | Erection | Kg | 142969 | 142969 | [5 empty] | #REF! | 142783 | 142783
|  | Alignment | Kg | 142969 | 142969 | 2013-04-27 | 00051 |  |  |  | #REF! | 142783 | 142783
|  | Bolt Tightening & Test | Kg | 142969 | 142969 | 2013-05-02 | 00072 |  |  |  | #REF! | 142783 | 142783
|  | Grouting | NO | 24 | 24 | 2013-05-05 | 00073 |  |  |  | #REF! | 24 | 24
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 57 | 57
|  | 140-IM-B12 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 81227 | 81227 | [5 empty] | #REF! | 81169 | 81169
|  | Chip&Padding | NO | 6 | 6 | 2013-01-04 | 00019 |  |  |  | #REF! | 6 | 6
|  | Erection | Kg | 81227 | 81227 | [5 empty] | #REF! | 81000 | 81000
|  | Alignment | Kg | 81227 | 0 | 2013-05-07 | 00075 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 81227 | 0 | [5 empty] | #REF! | 0 | 0
|  | Grouting | NO | 6 | 0 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 41 | 41
|  | 140-IM-B13 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 115037 | 115037 | [5 empty] | #REF! | 114739 | 114739
|  | Chip&Padding | NO | 14 | 14 | 1/4/2013,01/13/2013 | 00020,00031-1 |  |  |  | #REF! | 14 | 14
|  | Erection | Kg | 115037 | 77582 | [5 empty] | #REF! | 75656 | 75656
|  | Alignment | Kg | 115037 | 77582 | 2013-07-16 | 00115 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 115037 | 77582 | [5 empty] | #REF! | 0 | 0
|  | Grouting | NO | 14 | 8 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 80 | [5 empty] | #REF! | 31 | 31
|  | 140-IM-C1 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 34919 | 34919 | [5 empty] | #REF! | 33400 | 33400
|  | Chip&Padding | NO | 12 | 12 | 2013-01-13 | 00026-1 |  |  |  | #REF! | 12 | 12
|  | Erection | Kg | 34919 | 34919 | [5 empty] | #REF! | 33400 | 33400
|  | Alignment | Kg | 34919 | 34919 | 2013-06-16 | 00103 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 34919 | 34919 | 2013-06-21 | 00108 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 12 | 12 | 2013-06-29 | 00112 |  |  |  | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 41 | 41
|  | 140-IM-C2 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 63237 | 63237 | [5 empty] | #REF! | 63000 | 63000
|  | Chip&Padding | NO | 22 | 22 | 2013-01-13 | 00027-1 |  |  |  | #REF! | 22 | 22
|  | Erection | Kg | 63237 | 63237 | [5 empty] | #REF! | 61847 | 61847
|  | Alignment | Kg | 63237 | 63237 | 2013-06-02 | 00100 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 63237 | 63237 | 2013-06-17 | 00105 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 22 | 22 | 2013-06-13 | 00107 |  |  |  | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 41 | 41
|  | 140-IM-C3 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 32631 | 32631 | [5 empty] | #REF! | 31800 | 31800
|  | Chip&Padding | NO | 12 | 12 | 2013-01-13 | 00028-1 |  |  |  | #REF! | 12 | 12
|  | Erection | Kg | 32631 | 32631 | [5 empty] | #REF! | 31800 | 31800
|  | Alignment | Kg | 32631 | 32631 | 2013-06-16 | 00104 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 32631 | 32631 | 2013-06-18 | 00106 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 12 | 12 | 2013-06-26 | 00111 |  |  |  | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 41 | 41
|  | 140-IM-D1 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 57553 | 57553 | [5 empty] | #REF! | 57553 | 57553
|  | Chip&Padding | NO | 18 | 18 | 2013-01-03 | 00013-1 |  |  |  | #REF! | 18 | 18
|  | Erection | Kg | 57553 | 57553 | [5 empty] | #REF! | 57553 | 57553
|  | Alignment | Kg | 57553 | 57553 | 2013-05-01 | 00042 |  |  |  | #REF! | 57553 | 57553
|  | Bolt Tightening & Test | Kg | 57553 | 57553 | 2013-05-18 | 00085 |  |  |  | #REF! | 57533 | 57533
|  | Grouting | NO | 18 | 18 | 2013-05-24 | 00089 |  |  |  | #REF! | 18 | 18
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 61 | 61
|  | 140-IM-D2 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 51015 | 51015 | [5 empty] | #REF! | 50938 | 50938
|  | Chip&Padding | NO | 16 | 16 | 2013-01-03 | 00014-1 |  |  |  | #REF! | 16 | 16
|  | Erection | Kg | 51015 | 51015 | [5 empty] | #REF! | 50588 | 50588
|  | Alignment | Kg | 51015 | 51015 | 2013-05-06 | 00069 |  |  |  | #REF! | 50588 | 50588
|  | Bolt Tightening & Test | Kg | 51015 | 51015 | 2013-05-21 | 00087 |  |  |  | #REF! | 50588 | 50588
|  | Grouting | NO | 16 | 16 | 2013-05-23 | 00090 |  |  |  | #REF! | 16 | 16
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 62 | 62
|  | 140-IM-D3 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 67658 | 67658 | [5 empty] | #REF! | 67658 | 67658
|  | Chip&Padding | NO | 26 | 26 | 2013-07-01 | 00015-2 |  |  |  | #REF! | 26 | 26
|  | Erection | Kg | 67658 | 67658 | [5 empty] | #REF! | 67658 | 67658
|  | Alignment | Kg | 67658 | 67658 | 2013-05-15 | 00074 |  |  |  | #REF! | 67658 | 67658
|  | Bolt Tightening & Test | Kg | 67658 | 67658 | 2013-05-21 | 00088 |  |  |  | #REF! | 67658 | 67658
|  | Grouting | NO | 26 | 26 | 2013-05-26 | 00093 |  |  |  | #REF! | 26 | 26
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 61 | 61
|  | 140-IM-D4 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 58695 | 58695 | [5 empty] | #REF! | 58695 | 58695
|  | Chip&Padding | NO | 18 | 18 | 2013-07-01 | 00016-2 |  |  |  | #REF! | 18 | 18
|  | Erection | Kg | 58695 | 58695 | [5 empty] | #REF! | 58695 | 58695
|  | Alignment | Kg | 58695 | 58695 | 2013-06-09 | 00081 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 58695 | 58695 | 2013-06-23 | 00109 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 18 | 18 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 41 | 41
|  | 140-IM-E1 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 53769 | 53769 | [5 empty] | #REF! | 50500 | 50500
|  | Chip&Padding | NO | 20 | 20 | 2013-02-17 | 00036 |  |  |  | #REF! | 20 | 20
|  | Erection | Kg | 53769 | 43069.5014 | [5 empty] | #REF! | 35264 | 35264
|  | Alignment | Kg | 53769 | 40221 | 2013-06-26 | 00095-1 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 53769 | 40221 | 2013-07-19 | 00116 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 20 | 14 | 2013-07-20 | 00117 |  |  |  | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 90 | [5 empty] | #REF! | 40 | 40
|  | 140-IM-E2 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 64679 | 64679 | [5 empty] | #REF! | 64431 | 64431
|  | Chip&Padding | NO | 26 | 26 | 2013-01-06 | 00022 |  |  |  | #REF! | 26 | 26
|  | Erection | Kg | 64679 | 64679 | [5 empty] | #REF! | 63845 | 63845
|  | Alignment | Kg | 64679 | 64679 | 2013-04-27 | 00053 |  |  |  | #REF! | 63845 | 63845
|  | Bolt Tightening & Test | Kg | 64679 | 64679 | 2013-05-17 | 00084 |  |  |  | #REF! | 63845 | 63845
|  | Grouting | NO | 26 | 26 | 2013-05-19 | 00086 |  |  |  | #REF! | 26 | 26
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 62 | 62
|  | 140-IM-E3 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 38933 | 38933 | [5 empty] | #REF! | 38834 | 38834
|  | Chip&Padding | NO | 16 | 16 | 2013-04-09 | 00023-4 |  |  |  | #REF! | 16 | 16
|  | Erection | Kg | 38933 | 38933 | [5 empty] | #REF! | 37088 | 37088
|  | Alignment | Kg | 38933 | 38933 | 2013-05-17 | 00065 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 38933 | 38933 | 2013-05-24 | 00091 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 16 | 16 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 52 | 52
|  | 140-IM-E4 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 14165 | 14165 | [5 empty] | #REF! | 14200 | 14200
|  | Chip&Padding | NO | 6 | 6 | 2013-04-07 | 00024-4 |  |  |  | #REF! | 6 | 6
|  | Erection | Kg | 14165 | 14165 | [5 empty] | #REF! | 14200 | 14200
|  | Alignment | Kg | 14165 | 14165 | 2013-05-17 | 00079 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 14165 | 14165 | 2013-05-24 | 00092 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 6 | 6 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 54 | 54
|  | 140-IM-F1 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 36958 | 36958 | [5 empty] | #REF! | 35800 | 35800
|  | Chip&Padding | NO | 18 | 18 | 2013-01-10 | 00029 |  |  |  | #REF! | 20 | 20
|  | Erection | Kg | 36958 | 36958 | [5 empty] | #REF! | 34945 | 34945
|  | Alignment | Kg | 36958 | 0 | [5 empty] | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 36958 | 0 | [5 empty] | #REF! | 0 | 0
|  | Grouting | NO | 18 | 0 | [5 empty] | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 75 | [5 empty] | #REF! | 48 | 48
|  | 140-IM-F2 |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 57287 | 57287 | [5 empty] | #REF! | 54300 | 54300
|  | Chip&Padding | NO | 22 | 22 | 2013-01-10 | 00030 |  |  |  | #REF! | 22 | 22
|  | Erection | Kg | 57287 | 57287 | [5 empty] | #REF! | 54300 | 54300
|  | Alignment | Kg | 57287 | 57287 | 2013-06-02 | 00097 |  |  |  | #REF! | 0 | 0
|  | Bolt Tightening & Test | Kg | 57287 | 57287 | 2013-06-08 | 00099 |  |  |  | #REF! | 0 | 0
|  | Grouting | NO | 22 | 22 | 2013-06-10 | 00101 |  |  |  | #REF! | 0 | 0
|  | Final test & Documents | % | 100 | 100 | [5 empty] | #REF! | 55 | 55
|  | Fireproofing |  | 0 | 0 | [5 empty] | #REF!
|  | Fireproofing | m2 | 200 | 0 | [5 empty] | #REF!
|  | Insulation | ins | 0 | 0 | [5 empty] | #REF!
|  | Cold Insulation | m2 | 1 | 0 | [5 empty] | #REF!
|  | Hot Insulation | m2 | 1 | 0 | [5 empty] | #REF!
|  | Equipment Packages | equ | 0 | 0
|  | Static Equipment |  | 0 | 0
|  | HP FLARE 140-X-101 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP FLARE 140-X-201 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | LP FLARE 140-X-102 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | LP FLARE 140-X-202 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | MP FLARE 140-X-103 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | MP FLARE 140-X-203 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-101 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-103 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Cold Flare K.O. Drum Heater 140-DH-104 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-201 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | MP Flare K.O. Drum Heater 140-DH-203 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Cold Flare K.O. Drum Heater 140-DH-204 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-105 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-106 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-205 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-206 |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | Rotary Equipment |  | 0 | 0
|  | HP FLARE STACKS PUMPS, 140-P-104A |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP FLARE STACKS PUMPS, 140-P-104B |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | LP FLARE STACKS PUMPS, 140-P-105A |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | LP FLARE STACKS PUMPS, 140-P-105B |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | MP FLARE STACKS PUMPS, 140-P-106A |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | MP FLARE STACKS PUMPS, 140-P-106B |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP FLARE STACKS PUMPS, 140-P-204A |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | HP FLARE STACKS PUMPS, 140-P-204B |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | LP FLARE STACKS PUMPS, 140-P-205A |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | LP FLARE STACKS PUMPS, 140-P-205B |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | MP FLARE STACKS PUMPS, 140-P-206A |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | MP FLARE STACKS PUMPS, 140-P-206B |  | 0 | 0
|  | Material Handling | Kg | 1 | 0
|  | Chipping & Padding | % | 1 | 0
|  | Installation | Kg | 1 | 0
|  | Alignment | Kg | 1 | 0
|  | Grouting | % | 1 | 0
|  | External Installation | Kg | 1 | 0
|  | Final Inspection | % | 1 | 0
|  | Unit 143 |  | 0 | 0 | [5 empty] | #REF!
|  | Welding & NDT Procedures | pip | 0 | 0 | [5 empty] | #REF!
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 1 | 0.26 | [5 empty] | #REF! |  | 100
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 1 | 0.26 | [5 empty] | #REF! |  | 100
|  | Qualification of Welding Equipments | % | 1 | 0.26 | [5 empty] | #REF! |  | 100
|  | Maintaining Welder Qualification Records | % | 1 | 0.26 | [5 empty] | #REF! |  | 100
|  | Monitoring Welder Performance | % | 1 | 0.26 | [5 empty] | #REF! |  | 100
|  | Prepare NDT Procedures & Obtain Certification | % | 1 | 0.38 | [5 empty] | #REF!
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 1 | 0.26 | [5 empty] | #REF!
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 1 | 0.26 | [5 empty] | #REF!
|  | Perform NDT as per the Procedures | % | 1 | 0.26 | [5 empty] | #REF!
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 1 | 0.26 | [5 empty] | #REF! |  | 100
|  | Prepare PWHT Procedures & Obtain Certification | % | 1 | 0.26 | [5 empty] | #REF!
|  | Perform PWHT Testing | % | 1 | 0.26 | [5 empty] | #REF!
|  | Provide and maintain secure storage for radioactive sources | % | 1 | 0.26 | [5 empty] | #REF!
|  | Implement specific safety procedures relating to radioactive sources | % | 1 | 0.26 | [5 empty] | #REF! |  | 100
|  | Piping | pip | 0 | 0 | [5 empty] | #REF!
|  | AG Piping |  | 0 | 0 | [5 empty] | #REF!
|  | Shop |  | 0 | 0 | [5 empty] | #REF!
|  | Carbon Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 26984 | 17000 | [5 empty] | #REF! |  | 2000
|  | Cutting & Bevelling & Fit Up | ID | 8095 | 4200 | 6/5/13 , 6/12/13 , 7/10/13 , 7/16/13 , 7/23/1309/11/2013,05/11/2013,28/10/2013,20/10/2013,12/10/2013,05/10/2013, 7/29/13,09/04/13 ,09/28/13 ,09/25/13 ,09/21/13 ,09/18/13 ,09/10/13 , | 00015 , 00017 , 00025 , 00026 , 00028 ,00086,00080,00077,00071,00064,00059, 00030,00043,00055,00053,00049,00047,00045,00043 |  |  |  | #REF!
|  | Welding | ID | 8095 | 4200 | 6/5/13 , 6/12/13 , 7/10/13 , 7/16/13 , 7/23/132/10/2013,12/10/2013,20/10/2013,28/10/2013,9/11/2013,05/11/2013,05/11/2013,28/10/2013,20/10/2013,05/10/2013, 7/29/13,09/04/13 ,09/28/13 ,09/25/13 ,09/21/13 ,09/18/13 ,09/10/13 , | 00016 , 00018 , 00024 , 00027 , 0002900058,00067,00070,00076,00089,00083,00081,00074,00068,00065,00060,00054,00048 00031,00056-00054-00050-00048-00046-00044 |  |  |  | #REF!
|  | NDT | ID | 1619 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 8095 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 45 | [5 empty] | #REF! |  | 25
|  | Low Temperature CS |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 93 | 0 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 28 | 0 | [5 empty] | #REF!
|  | Welding | ID | 28 | 0 | [5 empty] | #REF!
|  | NDT | ID | 28 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 28 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | Stainless Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 41 | 0 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 12 | 0 | [5 empty] | #REF!
|  | Welding | ID | 12 | 0 | [5 empty] | #REF!
|  | NDT | ID | 12 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 12 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | Galva |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 1971 | 0 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 591 | 0 | [5 empty] | #REF!
|  | Welding | ID | 591 | 0 | [5 empty] | #REF!
|  | NDT | ID | 591 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 591 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | CU-NI |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 5256 | 0 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 1577 | 0 | [5 empty] | #REF!
|  | Welding | ID | 1577 | 0 | [5 empty] | #REF!
|  | NDT | ID | 1577 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 1577 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | Field |  | 0 | 0 | [5 empty] | #REF!
|  | Carbon Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 26984 | 14000 | [5 empty] | #REF! |  | 1072
|  | Scaffolding | M2 | #REF! | #REF! | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 18889 | 1942 | 5/21/2013 , 5/17/2013 , 5/8/2013 , 6/5/13 , 6/12/13 , 7/10/13 , 7/16/13 , 7/23/1309/11/2013,05/11/2013,28/10/2013,20/10/2013,12/10/2013,05/10/2013,02/10/2013, 7/29/13,09/04/13 ,09/28/13 ,09/25/13 ,09/21/13 ,09/18/13 ,09/10/13 , | 00010 , 00007 , 00001,00057,00061,00066,,00069,00075,00082,00088 00015 , 00017 , 00025 , 00026 , 00028 00030,00043,00055,00053,00049,00047,00045,00043 | 19/04/2014,26/04/2014 | 0096,102 |  | #REF! |  | 550
|  | Valve Installation | ID | 380 | 0 | [5 empty] | #REF!
|  | Welding | ID | 18889 | 1720 | 5/21/2013 , 5/17/2013 , 5/13/2013 , 5/13/2013 5/10/2013 6/5/13 , 6/12/13 , 7/10/13 , 7/16/13 , 7/23/13 7/29/13,09/04/13 ,09/28/13 ,09/25/13 ,09/21/13 ,09/18/13 ,09/10/13 , | 00011 , 00006 , 00004 , 00003 , 00016 , 00018, 00024 , 00027 , 00029,00062 00031 ,00056-00054-00050-00048-00046-00044 | 19/04/2014,26/04/2014 | 99,105 |  | #REF! |  | 550
|  | NDT | ID | 3777.8 | 108 | 22/09/2013,3/09/2013,27/08/2013,9/10/2013,6/10/2013,13/10/2013,28/10/2013,29/10/2013,20/10/2013,07/10/2013 | 00051,00042,00039,00090,00084,000,00078~85,00079,,00073,,00072,,00063 |  |  |  | #REF!
|  | PWHT | ID | 18889 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 18889 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | Low Temperature CS |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 93 | 0 | [5 empty] | #REF!
|  | Scaffolding | M2 | #REF! | #REF! | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 65 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 380 | 0 | [5 empty] | #REF!
|  | Welding | ID | 65 | 0 | [5 empty] | #REF!
|  | NDT | ID | 65 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 65 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 65 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | Stainless Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 41 | 0 | [5 empty] | #REF!
|  | Scaffolding | M2 | #REF! | #REF! | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 29 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 380 | 0 | [5 empty] | #REF!
|  | Welding | ID | 29 | 0 | [5 empty] | #REF!
|  | NDT | ID | 29 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 29 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 29 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | Galva |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 1971 | 0 | [5 empty] | #REF!
|  | Scaffolding | M2 | #REF! | #REF! | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 1380 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 381 | 0 | [5 empty] | #REF!
|  | Welding | ID | 1380 | 0 | [5 empty] | #REF!
|  | NDT | ID | 1380 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 1380 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 1380 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | CU-NI |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 5256 | 0 | [5 empty] | #REF!
|  | Scaffolding | M2 | #REF! | #REF! | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 3679 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 380 | 0 | [5 empty] | #REF!
|  | Welding | ID | 3679 | 0 | [5 empty] | #REF!
|  | NDT | ID | 3679 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 3679 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 3679 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 25 | [5 empty] | #REF! |  | 25
|  | Pipe Support |  | 0 | 0 | [5 empty] | #REF!
|  | Shop |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 26579 | 0 | [5 empty] | #REF!
|  | shop drawing | Kg | 26579 | 0 | [5 empty] | #REF!
|  | Cutting & assembling | Kg | 26579 | 0 | [5 empty] | #REF!
|  | Welding | Kg | 26579 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 0 | [5 empty] | #REF!
|  | Field |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | Kg | 39869 | 0 | [5 empty] | #REF!
|  | Erection | Kg | 39869 | 0 | [5 empty] | #REF!
|  | Welding | Kg | 39869 | 0 | [5 empty] | #REF!
|  | NDT | Kg | 39869 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 0 | [5 empty] | #REF!
|  | Painting & Sandblasting | pan | 0 | 0
|  | Pipe |  | 0 | 0
|  | Sand Blast | m2 | 11000 | 4891 | 5/24/2013 , 5/8/2013 , 5/8/2013 | 00006 , 00004 , 00002 | [5 empty] | 3480
|  | Primer | m2 | 11000 | 4891 | 5/24/2013 , 5/8/2013 , 5/8/2013 , 7/5/13 , 7/12/13 , 7/19/13,9/7/13 , 9/13/13 , 9/20/13 ,9/27/13 | 00006 , 00004 , 00002, 00013 , 00014 , 00016 00016, 00021~00025 | [5 empty] | 3480
|  | Middle Paint | m2 | 11000 | 0
|  | Final Paint | m2 | 11000 | 0
|  | Touch Up & Punch | m2 | 11000 | 0
|  | Final Certificate | % | 100 | 25
|  | Support |  | 0 | 0
|  | Sand Blast | m2 | 400 | 0
|  | Primer | m2 | 400 | 0
|  | Middle Paint | m2 | 400 | 0
|  | Final Paint | m2 | 400 | 0
|  | Touch Up & Punch | m2 | 400 | 0
|  | Final Certificate | % | 400 | 0
|  | Insulation | ins | 0 | 0 | [5 empty] | #REF!
|  | Cold Insulation | M2 | 1 | 0 | [5 empty] | #REF!
|  | Hot Insulation | M2 | 1 | 0 | [5 empty] | #REF!
|  | Equipment Packages | equ | 0 | 0
|  | Static Equipment |  | 0 | 0
|  | Sump Drum 143-D-101 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Degassing Boot 143-D-102 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Rotary Equipment |  | 0 | 0
|  | Pump 143-P-101 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 143-P-102 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 143-P-103 A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 143-P-103 B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 143-P-103 C |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 143-P-104 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Unit 147/148 |  | 0 | 0 | [5 empty] | #REF!
|  | Welding & NDT Procedures | pip | 0 | 0 | [5 empty] | #REF!
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 1 | 0.15 | [5 empty] | #REF! |  | 100
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 1 | 0.15 | [5 empty] | #REF! |  | 100
|  | Qualification of Welding Equipments | % | 1 | 0.15 | [5 empty] | #REF! |  | 100
|  | Maintaining Welder Qualification Records | % | 1 | 0.15 | [5 empty] | #REF! |  | 100
|  | Monitoring Welder Performance | % | 1 | 0.15 | [5 empty] | #REF! |  | 100
|  | Prepare NDT Procedures & Obtain Certification | % | 1 | 0.32 | [5 empty] | #REF!
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 1 | 0.15 | [5 empty] | #REF!
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 1 | 0.15 | [5 empty] | #REF!
|  | Perform NDT as per the Procedures | % | 1 | 0.15 | [5 empty] | #REF!
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 1 | 0.15 | [5 empty] | #REF! |  | 100
|  | Prepare PWHT Procedures & Obtain Certification | % | 1 | 0.15 | [5 empty] | #REF!
|  | Perform PWHT Testing | % | 1 | 0.15 | [5 empty] | #REF!
|  | Provide and maintain secure storage for radioactive sources | % | 1 | 0.15 | [5 empty] | #REF!
|  | Implement specific safety procedures relating to radioactive sources | % | 1 | 0.15 | [5 empty] | #REF! |  | 100
|  | Piping | pip | 0 | 0 | [5 empty] | #REF!
|  | AG Piping |  | 0 | 0 | [5 empty] | #REF!
|  | Shop |  | 0 | 0 | [5 empty] | #REF!
|  | Carbon Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 4934 | 2450 | [5 empty] | #REF! |  | 600
|  | Cutting & Bevelling & Fit Up | ID | 1480 | 624.375 | 09/11/2013,05/11/2013,28/10/2013,20/10/2013,12/10/2013,05/10/2013, | ,00086,00080,00077,00071,00064,00059, | 12/4/2014,26/04/2014 | 0097,00103 |  | #REF!
|  | Welding | ID | 1480 | 624.375 | 2/10/2013,12/10/2013,20/10/2013,28/10/2013,9/11/2013,05/11/2013,05/11/2013,28/10/2013,20/10/2013,05/10/2013, | 00058,00067,00070,00076,00089,00083,00081,00074,00068,00065,00060,00054,00048 | 12/04/2014,26/04/2014,1904/2014 | 00094,00104,00099 |  | #REF!
|  | NDT | ID | 296 | 1.3214 | 22/09/2013,3/09/2013,27/08/2013,9/10/2013,6/10/2013,13/10/2013,28/10/2013,29/10/2013,20/10/2013,07/10/2013 | 00051,00042,00039,00090,00084,000,00078~85,00079,,00073,,00072,,00063 | 19/04/2014 | 00100 |  | #REF!
|  | PWHT | ID | 1480 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Low Temperature CS |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 36676 | 15000 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 11003 | 1240 | [5 empty] | #REF!
|  | Welding | ID | 11003 | 1240 | [5 empty] | #REF!
|  | NDT | ID | 11003 | 200 | [5 empty] | #REF!
|  | PWHT | ID | 11003 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Galva |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 544 | 0 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 163 | 0 | [5 empty] | #REF!
|  | Welding | ID | 163 | 0 | [5 empty] | #REF!
|  | NDT | ID | 163 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 163 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | GRE & Stainless Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Lay down To Shop | ID | 578 | 0 | [5 empty] | #REF!
|  | Cutting & Bevelling & Fit Up | ID | 173 | 0 | [5 empty] | #REF!
|  | Welding | ID | 173 | 0 | [5 empty] | #REF!
|  | NDT | ID | 173 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 173 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Field |  | 0 | 0 | [5 empty] | #REF!
|  | Carbon Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 4934 | 0 | [5 empty] | #REF!
|  | Scaffolding | m2 | 1 | 0 | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 3454 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 611 | 0 | [5 empty] | #REF!
|  | Welding | ID | 4045 | 0 | [5 empty] | #REF!
|  | NDT | ID | 809 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 4045 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 4045 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Low Temperature CS |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 36676 | 0 | [5 empty] | #REF!
|  | Scaffolding | m2 | 1 | 0 | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 25673 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 611 | 0 | [5 empty] | #REF!
|  | Welding | ID | 25673 | 0 | [5 empty] | #REF!
|  | NDT | ID | 25673 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 25673 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 25673 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Galva |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 544 | 0 | [5 empty] | #REF!
|  | Scaffolding | m2 | 1 | 0 | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 381 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 611 | 0 | [5 empty] | #REF!
|  | Welding | ID | 381 | 0 | [5 empty] | #REF!
|  | NDT | ID | 381 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 381 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 381 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | GRE |  | 0 | 0 | [5 empty] | #REF!
|  | Scoffolding | m2 | 1 | 0 | [5 empty] | #REF!
|  | Material Handling To Field | ID | 386 | 0 | [5 empty] | #REF!
|  | Erection & Fittup | ID | 270 | 0 | [5 empty] | #REF!
|  | Bonding | ID | 270 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 270 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Stainless Steel |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | ID | 192 | 0 | [5 empty] | #REF!
|  | Scaffolding | m2 | 1 | 0 | [5 empty] | #REF!
|  | Erection & Fit Up | ID | 134 | 0 | [5 empty] | #REF!
|  | Valve Installation | ID | 611 | 0 | [5 empty] | #REF!
|  | Welding | ID | 134 | 0 | [5 empty] | #REF!
|  | NDT | ID | 134 | 0 | [5 empty] | #REF!
|  | PWHT | ID | 134 | 0 | [5 empty] | #REF!
|  | Hydro test | ID | 134 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 40 | [5 empty] | #REF! |  | 40
|  | Pipe Support |  | 0 | 0 | [5 empty] | #REF!
|  | Shop |  | 0 | 0 | [5 empty] | #REF!
|  | Handling | Kg | 37124 | 0 | [5 empty] | #REF!
|  | shop drawing | Kg | 37124 | 0 | [5 empty] | #REF!
|  | Cutting & assembling | Kg | 37124 | 0 | [5 empty] | #REF!
|  | Welding | Kg | 37124 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 0 | [5 empty] | #REF!
|  | Field |  | 0 | 0 | [5 empty] | #REF!
|  | Material Handling From Shop To Field | Kg | 55687 | 0 | [5 empty] | #REF!
|  | Erection | Kg | 55687 | 0 | [5 empty] | #REF!
|  | Welding | Kg | 55687 | 0 | [5 empty] | #REF!
|  | NDT | Kg | 55687 | 0 | [5 empty] | #REF!
|  | Final Certificate | % | 100 | 0 | [5 empty] | #REF!
|  | Painting & Sandblasting | pan | 0 | 0
|  | Pipe |  | 0 | 0
|  | Sand Blast | m2 | 5200 | 1850 | [7 empty] | 415
|  | Primer | m2 | 5200 | 1850 | [7 empty] | 415
|  | Middle Paint | m2 | 5200 | 0
|  | Final Paint | m2 | 5200 | 0
|  | Touch Up & Punch | m2 | 5200 | 0
|  | Final Certificate | % | 100 | 22
|  | Support |  | 0 | 0
|  | Sand Blast | m2 | 1 | 0
|  | Primer | m2 | 1 | 0
|  | Middle Paint | m2 | 1 | 0
|  | Final Paint | m2 | 1 | 0
|  | Touch Up & Punch | m2 | 1 | 0
|  | Final Certificate | % | 1 | 0
|  | Insulation | ins | 0 | 0 | [5 empty] | #REF!
|  | Cold Insulation | m2 | 1 | 0 | [5 empty] | #REF!
|  | Hot Insulation | m2 | 1 | 0 | [5 empty] | #REF!
|  | Equipment Packages | equ | 0 | 0
|  | Static Equipment |  | 0 | 0
|  | Air cooler 147-A-101 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Vert.) 147-D-101 A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Vert.) 147-D-101 B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Vert.) 147-D-102 A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Vert.) 147-D-102 B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Vert.) 147-D-103 A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Vert.) 147-D-103 B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Hori) 147-D-104 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Vert.) 147-D-105 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Hori) 147-D-106 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Hori) 147-D-107 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Hori) 147-D-108 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Hori.) in Sump 147-D-109 |  | 0 | 0
|  | Material Handling | Kg | 16440 | 16060
|  | Chipping & Padding | % | 100 | 100
|  | Installation |  | 16440 | 16440
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Drum (Hori) on St. 147-D-110 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | LP FLARE K.O. DRUM 147-D-111 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Electric Heater 147-DH-107 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Electric Heater 147-DH-108 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Electric Heater 147-DH-109 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Electric Heater 147-DH-110 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | LPG TANK FLARE 147-X-101 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | LOW PRESSURE PROPANE CHILLER 147-E-101 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | MEDUIM PRESSURE PROPANE CHILLER 147-E-102 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | HIGH PRESSURE PROPANE CHILLER 147-E-103 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | PROPANE BOIL OFF GAS CONDENSER 147-E-104 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Rotary Equipment |  | 0 | 0
|  | Compressor 147-K-101A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Compressor 147-K-101B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Compressor 147-K-102A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Compressor 147-K-102B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-101A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-101B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-101C |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-102 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-103A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-103B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-103C |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-104 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-106 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-107 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-108 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-109A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 147-P-109B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 148-P-101A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 148-P-101B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 148-P-101C |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 148-P-102 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 148-P-103A |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 148-P-103B |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 148-P-103C |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
|  | Pump 148-P-104 |  | 0 | 0
|  | Material Handling |  | 1 | 0
|  | Chipping & Padding |  | 1 | 0
|  | Installation |  | 1 | 0
|  | Alignment |  | 1 | 0
|  | Grouting |  | 1 | 0
|  | External Installation |  | 1 | 0
|  | Final Inspection |  | 1 | 0
232049999999.9999
9825103953.4884
1761398233.3764
120317904475.3876
40837741910.0229
59307851427.7247

## checked (hidden)
South Pars Gas Field Development Phase 14 Invoice : No/08
|  | Date : | 2013-08-31
Description |  |  | Unit | Estimate | Work Performed | W.F | Activity Total Price | Up To Last |  | This Month |  | Up To Now
[8 empty] | % Actual | Cost | % Actual | Cost | % Actual | Cost | last
|  | Package NO.2 |  |  |  | 100% | 273000000000 | 27.47% | 74993032680.1713 | 0.8108% | 2213420619.9067 | 28.28% | 77206453300.078 | 27.47% |  | 0
|  | Procurement |  |  |  | 15% | 40950000000 | 76.07% | 31151734073.369 | 0% | 0 | 76.07% | 31151734073.369 | 76.07% |  | 0
|  | fire proof |  |  |  | 0.1987% | 542557717.1942 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PO Placement | m2 | 200 |  | 0.04968% | 135639429.2986 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Fabrication & Test | m2 | 200 |  | 0.1192% | 325534630.3165 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Delivery | m2 | 200 |  | 0.02981% | 81383657.5791 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Rebar |  |  |  | 4.373% | 11938255300.1542 | 100% | 11938255300.1542 | 0% | 0 | 100% | 11938255300.1542 | 100% | 308693 | 308693
|  | PO Placement | Kg | 308693 | 308693 | 1.093% | 2984563825.0386 | 100% | 2984563825.0386 | 0% | 0 | 100% | 2984563825.0386 | 100%
|  | Fabrication & Test | Kg | 308693 | 308693 | 2.624% | 7162953180.0925 | 100% | 7162953180.0925 | 0% | 0 | 100% | 7162953180.0925 | 100%
|  | Delivery | Kg | 308693 | 308693 | 0.6559% | 1790738295.0231 | 100% | 1790738295.0231 | 0% | 0 | 100% | 1790738295.0231 | 100%
|  | Piping Support |  |  |  | 0.934% | 2549740541.1546 | 85% | 2167279459.9814 | 0% | 0 | 85% | 2167279459.9814 | 85% |  | 0
|  | PO Placement | Kg | 72000 | 72000 | 0.2335% | 637435135.2886 | 100% | 637435135.2886 | 0% | 0 | 100% | 637435135.2886 | 100%
|  | Fabrication & Test | Kg | 72000 | 72000 | 0.5604% | 1529844324.6927 | 100% | 1529844324.6927 | 0% | 0 | 100% | 1529844324.6927 | 100%
|  | Delivery | Kg | 72000 |  | 0.1401% | 382461081.1732 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Cold Insulating |  |  |  | 0.7797% | 2128664224.832 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PO Placement | m2 | 5862 |  | 0.1949% | 532166056.208 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Fabrication & Test | m2 | 5862 |  | 0.4678% | 1277198534.8992 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Delivery | m2 | 5862 |  | 0.117% | 319299633.7248 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Warm Insulating |  |  |  | 0.5209% | 1422014517.9874 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PO Placement | m2 | 2937 |  | 0.1302% | 355503629.4968 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Fabrication & Test | m2 | 2937 |  | 0.3125% | 853208710.7924 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Delivery | m2 | 2937 |  | 0.07813% | 213302177.6981 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Paint |  |  |  | 5.56% | 15178806652.6741 | 80.58% | 12231588360.9466 | 0% | 0 | 80.58% | 12231588360.9466 | 80.58% | 13900 | 13900
|  | PO Placement | Kg | 57000 | 57000 | 4.17% | 11384104989.5056 | 100% | 11384104989.5056 | 0% | 0 | 100% | 11384104989.5056 | 100%
|  | Delivery | Kg | 57000 | 12730 | 1.39% | 3794701663.1685 | 22.33% | 847483371.441 | 0% | 0 | 22.33% | 847483371.441 | 22.33%
|  | Electrode |  |  |  | 2.634% | 7189961046.0035 | 66.96% | 4814610952.2868 | 0% | 0 | 66.96% | 4814610952.2868 | 66.96% | 18080 | 18080
|  | PO Placement | Kg | 27000 | 18080 | 0.6584% | 1797490261.5009 | 66.96% | 1203652738.0717 | 0% | 0 | 66.96% | 1203652738.0717 | 66.96%
|  | Fabrication & Test | Kg | 27000 | 18080 | 1.58% | 4313976627.6021 | 66.96% | 2888766571.3721 | 0% | 0 | 66.96% | 2888766571.3721 | 66.96%
|  | Delivery | Kg | 27000 | 18080 | 0.3951% | 1078494156.9005 | 66.96% | 722191642.843 | 0% | 0 | 66.96% | 722191642.843 | 66.96%
|  | Plant Construction |  |  |  | 85% | 232050000000 | 18.89% | 39867165559.1021 | 0.9539% | 6187553666.6069 | 19.85% | 46054719225.709 | 18.89% |  | 0
|  | General |  |  |  | 3.599% | 9825103953.4884 | 47.49% | 4666025117.8605 | 0% | 0 | 47.49% | 4666025117.8605 | 47.49% |  | 0
|  | mobolization |  |  |  | 3.249% | 8870770186.0465 | 52.6% | 4666025117.8605 | 0% | 0 | 52.6% | 4666025117.8605 | 52.6% |  | 0
|  | primary mobilozation | % | 100 | 100 | 1.3% | 3548308074.4186 | 100% | 3548308074.4186 | 0% | 0 | 100% | 3548308074.4186 | 100% | 100 | 0
|  | countiuse mobilization | % | 100 | 21 | 1.95% | 5322462111.6279 | 21% | 1117717043.4419 | 0% | 0 | 21% | 1117717043.4419 | 21% | 27 | 6
|  | Demobilizaton |  |  |  | 0.3496% | 954333767.4419 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Demobilizaton | % | 100 | 0 | 0.3496% | 954333767.4419 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Gate House |  |  |  | 0.6452% | 1761398233.3764 | 20% | 352279646.6753 | 0% | 0 | 20% | 352279646.6753 | 20% |  | 0
|  | civil |  |  |  | 0.1613% | 440349558.3441 | 80% | 352279646.6753 | 0% | 0 | 80% | 352279646.6753 | 80% |  | 0
| ` | Foundation | % | 100 | 100 | 0.04839% | 132104867.5032 | 100% | 132104867.5032 | 0% | 0 | 100% | 132104867.5032 | 100% | 100 | 0
|  | columns | % | 100 | 100 | 0.04839% | 132104867.5032 | 100% | 132104867.5032 | 0% | 0 | 100% | 132104867.5032 | 100% | 100 | 0
|  | Wall | % | 100 | 0 | 0.01613% | 44034955.8344 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Floor | % | 100 | 0 | 0.01613% | 44034955.8344 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Roof | % | 100 | 100 | 0.03226% | 88069911.6688 | 100% | 88069911.6688 | 0% | 0 | 100% | 88069911.6688 | 100% | 95 | -5
|  | Mechanical |  |  |  | 0.06452% | 176139823.3376 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Piping | % | 100 | 0 | 0.04516% | 123297876.3363 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | % | 100 | 0 | 0.01936% | 52841947.0013 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | electrical |  |  |  | 0.06452% | 176139823.3376 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cabling | % | 100 | 0 | 0.04516% | 123297876.3363 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | % | 100 | 0 | 0.01936% | 52841947.0013 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | telecom |  |  |  | 0.129% | 352279646.6753 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | telecom | % | 100 | 0 | 0.129% | 352279646.6753 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | architect |  |  |  | 0.1936% | 528419470.0129 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | architect | % | 100 | 0 | 0.1936% | 528419470.0129 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | final works |  |  |  | 0.03226% | 88069911.6688 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | final works | % | 100 | 0 | 0.03226% | 88069911.6688 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Unit 140 |  |  |  | 43.74% | 119404914507.985 | 27.04% | 30187668673.2316 | 1.819% | 4268427788.4261 | 28.86% | 34456096461.6577 | 27.04% |  | 0
|  | Welding & NDT Procedures |  |  |  | 2.527% | 6898699223.1414 | 30.2% | 1462524235.306 | 31.55% | 2797422534.9838 | 61.75% | 4259946770.2898 | 30.2% |  | 0
|  | Prepare and qualify welding procedures (welding procedures qualfication tests (WPQT) including lab. Tests) for structural and pipe welding | % | 100 | 100 | 0.01263% | 34493496.1157 | 100% | 34493496.1157 | 0% | 0 | 100% | 34493496.1157 | 100% | 100 | 0
|  | Qualification of welders including lab testing for structural and pipe welding | % | 100 | 100 | 0.01263% | 34493496.1157 | 100% | 34493496.1157 | 0% | 0 | 100% | 34493496.1157 | 100% | 100 | 0
|  | Qualification of welding equipment | % | 100 | 100 | 0.01263% | 34493496.1157 | 100% | 34493496.1157 | 0% | 0 | 100% | 34493496.1157 | 100% | 100 | 0
|  | Maintaining welder qualification records | % | 100 | 100 | 0.01263% | 34493496.1157 | 100% | 34493496.1157 | 0% | 0 | 100% | 34493496.1157 | 100% | 100 | 0
|  | Monitoring welder performance | % | 100 | 50 | 0.01263% | 34493496.1157 | 100% | 34493496.1157 | -50% | -17246748.0579 | 50% | 17246748.0579 | 100% | 100 | 50
|  | Prepare and NDT Procedures and obtain certification | % | 100 | 20 | 0.7581% | 2069609766.9424 | 50% | 413921953.3885 | 50% | 1655687813.5539 | 100% | 2069609766.9424 | 50% |  | -20
|  | Qualification of NDT equipment and dimensional control (UT, RT, MT,...) | % | 100 | 20 | 0.01263% | 34493496.1157 | 20% | 6898699.2231 | 80% | 27594796.8926 | 100% | 34493496.1157 | 20% |  | -20
|  | Qualification of equipment operators for NDT and dimensional control | % | 100 | 20 | 0.01263% | 34493496.1157 | 20% | 6898699.2231 | 80% | 27594796.8926 | 100% | 34493496.1157 | 20% |  | -20
|  | Perform NDT as per the procedures | % | 100 | 20 | 0.2022% | 551895937.8513 | 20% | 110379187.5703 | 80% | 441516750.2811 | 100% | 551895937.8513 | 20% |  | -20
|  | Supply of associated Elec. Power, consumables, Materials construction equipments | % | 100 | 100 | 0.2022% | 551895937.8513 | 100% | 551895937.8513 | 0% | 0 | 100% | 551895937.8513 | 100% | 100 | 0
|  | Prepare PWHT procedure and obtain certification | % | 100 | 0 | 0.6317% | 1724674805.7854 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Perform PWHT testing | % | 100 | 0 | 0.3285% | 896830899.0084 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 0.3032% | 827843906.777 | 20% | 165568781.3554 | 80% | 662275125.4216 | 100% | 827843906.777 | 20% |  | -20
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100 | 0.01263% | 34493496.1157 | 100% | 34493496.1157 | 0% | 0 | 100% | 34493496.1157 | 100% | 100 | 0
|  | Civil |  |  |  | 5.511% | 15046048929.3428 | 48.39% | 6645941968.1924 | -0.02985% | 629998479.9858 | 48.36% | 7275940448.1781 | 48.39% |  | 0
|  | Plat Form |  |  |  | 2.567% | 7008988843.7506 | 81.47% | 5393325934.1455 | -0.06407% | 312680917.5121 | 81.41% | 5706006851.6576 | 81.47% |  | 0
|  | West HP |  |  |  | 1.097% | 2993691729.3879 | 88.9% | 2606110987.0017 | -0.15% | 50901758.4729 | 88.75% | 2657012745.4746 | 88.9% |  | 0
|  | excavation | m3 | 1385 | 1385 | 0.08773% | 239495338.351 | 100% | 239495338.351 | 0% | 0 | 100% | 239495338.351 | 100% | 1385 | 0
|  | level&compact | m2 | 588 | 588 | 0.02193% | 59873834.5878 | 100% | 59873834.5878 | 0% | 0 | 100% | 59873834.5878 | 100% | 588 | 0
|  | lean | m3 | 40 | 40 | 0.01097% | 29936917.2939 | 100% | 29936917.2939 | 0% | 0 | 100% | 29936917.2939 | 100% | 40 | 0
|  | footing rebar | Kg | 27084 | 27084 | 0.1535% | 419116842.1143 | 100% | 419116842.1143 | 0% | 0 | 100% | 419116842.1143 | 100% | 25188 | -1896
|  | footing form | m2 | 210 | 210 | 0.1151% | 314337631.5857 | 100% | 314337631.5857 | 0% | 0 | 100% | 314337631.5857 | 100% | 195 | -15
|  | foting concrete | m3 | 369 | 369 | 0.2303% | 628675263.1715 | 100% | 628675263.1715 | 0% | 0 | 100% | 628675263.1715 | 100% | 343 | -26
|  | ped rebar | Kg | 14583 | 14583 | 0.0658% | 179621503.7633 | 100% | 179621503.7633 | 0% | 0 | 100% | 179621503.7633 | 100% | 11666 | -2917
|  | ped form | m2 | 259 | 259 | 0.04935% | 134716127.8225 | 100% | 134716127.8225 | 0% | 0 | 100% | 134716127.8225 | 100% | 225 | -34
|  | anchor | NO. | 274 | 274 | 0.05483% | 149684586.4694 | 100% | 149684586.4694 | 0% | 0 | 100% | 149684586.4694 | 100% | 98 | -176
|  | ped concrete | m3 | 121 | 115 | 0.09869% | 269432255.6449 | 95.04% | 256071978.5055 | 0% | 0 | 95.04% | 256071978.5055 | 95.04% | 12 | -103
|  | curing | % | 100 | 85 | 0.01097% | 29936917.2939 | 85% | 25446379.6998 | 0% | 0 | 85% | 25446379.6998 | 85% | 75 | -10
|  | coating | m2 | 850 | 680 | 0.0329% | 89810751.8816 | 85% | 35924300.7527 | -5% | 35924300.7527 | 80% | 71848601.5053 | 85% | 400 | -280
|  | back fill | m3 | 998 | 199.6 | 0.1097% | 299369172.9388 | 20% | 44896376.8675 | 0% | 14977457.7203 | 20% | 59873834.5878 | 20% | 0 | -199.6
|  | Final Certificate | % | 100 | 59 | 0.05483% | 149684586.4694 | 59% | 88313906.0169 | 0% | 0 | 59% | 88313906.0169 | 59% | 50 | -9
|  | East HP |  |  |  | 1.078% | 2941964874.4525 | 86.36% | 2411228103.2488 | 0% | 129355677.4875 | 86.36% | 2540583780.7363 | 86.36% |  | 0
|  | excavation | m3 | 1358 | 1358 | 0.08621% | 235357189.9562 | 100% | 235357189.9562 | 0% | 0 | 100% | 235357189.9562 | 100% | 1358 | 0
|  | level&compact | m2 | 575 | 575 | 0.02155% | 58839297.4891 | 100% | 58839297.4891 | 0% | 0 | 100% | 58839297.4891 | 100% | 575 | 0
|  | lean | m3 | 39 | 39 | 0.01078% | 29419648.7445 | 100% | 29419648.7445 | 0% | 0 | 100% | 29419648.7445 | 100% | 39 | 0
|  | footing rebar | Kg | 26445 | 26445 | 0.1509% | 411875082.4234 | 100% | 411875082.4234 | 0% | 0 | 100% | 411875082.4234 | 100% | 26445 | 0
|  | footing form | m2 | 200 | 200 | 0.1132% | 308906311.8175 | 100% | 308906311.8175 | 0% | 0 | 100% | 308906311.8175 | 100% | 200 | 0
|  | foting concrete | m3 | 362 | 362 | 0.2263% | 617812623.635 | 100% | 617812623.635 | 0% | 0 | 100% | 617812623.635 | 100% | 358 | -4
|  | ped rebar | Kg | 14239 | 14239 | 0.06466% | 176517892.4672 | 100% | 150038349.0786 | 0% | 26479543.3886 | 100% | 176517892.4672 | 100% | 12103 | -2136
|  | ped form | m2 | 255 | 255 | 0.04849% | 132388419.3504 | 100% | 119144385.7126 | 0% | 13244033.6378 | 100% | 132388419.3504 | 100% | 235 | -20
|  | anchor | NO. | 262 | 262 | 0.05388% | 147098243.7226 | 100% | 139743331.5365 | 0% | 7354912.1861 | 100% | 147098243.7226 | 100% | 132 | -130
|  | ped concrete | m3 | 120 | 84.996 | 0.09699% | 264776838.7007 | 70.83% | 176517892.4672 | 0% | 11023542.3846 | 70.83% | 187541434.8517 | 70.83% | 60 | -24.996
|  | curing | % | 100 | 85 | 0.01078% | 29419648.7445 | 85% | 25006701.4328 | 0% | 0 | 85% | 25006701.4328 | 85% | 60 | -25
|  | coating | m2 | 830 | 581 | 0.03233% | 88258946.2336 | 70% | 44143680.7867 | 0% | 17637581.5768 | 70% | 61781262.3635 | 70% | 500 | -81
|  | back fill | m3 | 976.7 | 217.9994 | 0.1078% | 294196487.4453 | 22.32% | 12048591.684 | 0% | 53616064.3137 | 22.32% | 65664655.9978 | 22.32% | 0 | -217.9994
|  | Final Certificate | % | 100 | 56 | 0.05388% | 147098243.7226 | 56% | 82375016.4847 | 0% | 0 | 56% | 82375016.4847 | 56% | 52 | -4
|  | West LP |  |  |  | 0.1705% | 465541694.4189 | 95.5% | 312168836.6184 | 0% | 132423481.5516 | 95.5% | 444592318.17 | 95.5% |  | 0
|  | excavation | m3 | 145 | 145 | 0.01364% | 37243335.5535 | 100% | 37243335.5535 | 0% | 0 | 100% | 37243335.5535 | 100% | 145 | 0
|  | level&compact | m2 | 99 | 99 | 0.003411% | 9310833.8884 | 100% | 9310833.8884 | 0% | 0 | 100% | 9310833.8884 | 100% | 99 | 0
|  | lean | m3 | 5 | 5 | 0.001705% | 4655416.9442 | 100% | 4655416.9442 | 0% | 0 | 100% | 4655416.9442 | 100% | 5 | 0
|  | footing rebar | Kg | 7978 | 7978 | 0.02387% | 65175837.2186 | 100% | 54751624.5976 | 0% | 10424212.6211 | 100% | 65175837.2186 | 100% | 6702 | -1276
|  | footing form | m2 | 77 | 77 | 0.01791% | 48881877.914 | 100% | 45072900.4142 | 0% | 3808977.4998 | 100% | 48881877.914 | 100% | 71 | -6
|  | foting concrete | m3 | 48 | 48 | 0.03581% | 97763755.828 | 100% | 61102347.3925 | 0% | 36661408.4355 | 100% | 97763755.828 | 100% | 18 | -30
|  | ped rebar | Kg | 4296 | 4296 | 0.01023% | 27932501.6651 | 100% | 14954551.6364 | 0% | 12977950.0288 | 100% | 27932501.6651 | 100% | 2300 | -1996
|  | ped form | m2 | 61 | 61 | 0.007674% | 20949376.2488 | 100% | 14080728.2984 | 0% | 6868647.9504 | 100% | 20949376.2488 | 100% | 41 | -20
|  | anchor | NO. | 72 | 72 | 0.008526% | 23277084.7209 | 100% | 18104399.2274 | 0% | 5172685.4935 | 100% | 23277084.7209 | 100% | 29 | -43
|  | ped concrete | m3 | 26 | 23.4 | 0.01535% | 41898752.4977 | 90% | 37064281.0557 | 0% | 644596.1923 | 90% | 37708877.2479 | 90% | 21 | -2.4
|  | curing | % | 100 | 65 | 0.001705% | 4655416.9442 | 65% | 3026021.0137 | 0% | 0 | 65% | 3026021.0137 | 65% | 40 | -25
|  | coating | m2 | 181 | 181 | 0.005116% | 13966250.8326 | 100% | 0 | 0% | 13966250.8326 | 100% | 13966250.8326 | 100% | 0 | -181
|  | back fill | m3 | 135.9 | 122.31 | 0.01705% | 46554169.4419 | 90% | 0 | 0% | 41898752.4977 | 90% | 41898752.4977 | 90% | 0 | -122.31
|  | Final Certificate | % | 100 | 55 | 0.008526% | 23277084.7209 | 55% | 12802396.5965 | 0% | 0 | 55% | 12802396.5965 | 55% | 39 | -16
|  | East LP |  |  |  | 0.2226% | 607790545.4913 | 10.5% | 63818007.2766 | 0% | 0 | 10.5% | 63818007.2766 | 10.5% |  | 0
|  | excavation | m3 | 214 | 214 | 0.01781% | 48623243.6393 | 100% | 48623243.6393 | 0% | 0 | 100% | 48623243.6393 | 100% | 214 | 0
|  | level&compact | m2 | 138 | 138 | 0.004453% | 12155810.9098 | 100% | 12155810.9098 | 0% | 0 | 100% | 12155810.9098 | 100% | 138 | 0
|  | lean | m3 | 7 | 0 | 0.002226% | 6077905.4549 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | footing rebar | Kg | 9287 | 0 | 0.03117% | 85090676.3688 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | footing form | m2 | 102 | 0 | 0.02338% | 63818007.2766 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | foting concrete | m3 | 65 | 0 | 0.04675% | 127636014.5532 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | ped rebar | Kg | 5000 | 0 | 0.01336% | 36467432.7295 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | ped form | m2 | 84 | 0 | 0.01002% | 27350574.5471 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | anchor | NO. | 72 | 0 | 0.01113% | 30389527.2746 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | ped concrete | m3 | 30 | 0 | 0.02004% | 54701149.0942 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | curing | % | 100 | 0 | 0.002226% | 6077905.4549 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | coating | m2 | 248.02 | 0 | 0.006679% | 18233716.3647 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | back fill | m3 | 195.4 | 0 | 0.02226% | 60779054.5491 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 10 | 0.01113% | 30389527.2746 | 10% | 3038952.7275 | 0% | 0 | 10% | 3038952.7275 | 10% | 10 | 0
|  | Retaining wall |  |  |  | 2.849% | 7777710085.5922 | 20.19% | 1252616034.0469 | 0% | 317317562.4737 | 20.19% | 1569933596.5206 | 20.19% |  | 0
|  | Retaining wall 7 |  |  |  | 1.902% | 5193483001.6425 | 4% | 0 | 0% | 207739320.0657 | 4% | 207739320.0657 | 4% |  | 0
|  | excavation | m3 | 1705 | 852.5 | 0.1522% | 415478640.1314 | 50% | 0 | 0% | 207739320.0657 | 50% | 207739320.0657 | 50% |  | -852.5
|  | level&compact | m2 | 472 | 0 | 0.03805% | 103869660.0328 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | lean | m3 | 21 | 0 | 0.01902% | 51934830.0164 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | footing rebar | Kg | 36150 | 0 | 0.2663% | 727087620.2299 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | footing form | m2 | 218 | 0 | 0.1997% | 545315715.1725 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | foting concrete | m3 | 444 | 0 | 0.3995% | 1090631430.3449 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall rebar | Kg | 36200 | 0 | 0.1141% | 311608980.0985 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall form | m2 | 780 | 0 | 0.08561% | 233706735.0739 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall concrete | m3 | 385 | 0 | 0.2663% | 727087620.2299 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | curing | % | 100 | 0 | 0.01902% | 51934830.0164 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | coating | m2 | 1263 | 0 | 0.05707% | 155804490.0493 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | back fill | m3 | 798 | 0 | 0.1902% | 519348300.1642 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.09512% | 259674150.0821 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Retaining wall 9 |  |  |  | 0.2292% | 625720843.5714 | 86% | 459984155.4529 | 0% | 78135770.0185 | 86% | 538119925.4714 | 86% |  | 0
|  | excavation | m3 | 316 | 316 | 0.01834% | 50057667.4857 | 100% | 50057667.4857 | 0% | 0 | 100% | 50057667.4857 | 100% | 316 | 0
|  | level&compact | m2 | 128 | 128 | 0.004584% | 12514416.8714 | 100% | 12514416.8714 | 0% | 0 | 100% | 12514416.8714 | 100% | 128 | 0
|  | lean | m3 | 4 | 4 | 0.002292% | 6257208.4357 | 100% | 6257208.4357 | 0% | 0 | 100% | 6257208.4357 | 100% | 4 | 0
|  | footing rebar | Kg | 10025 | 10025 | 0.03209% | 87600918.1 | 100% | 87600918.1 | 0% | 0 | 100% | 87600918.1 | 100% | 10025 | 0
|  | footing form | m2 | 45 | 45 | 0.02407% | 65700688.575 | 100% | 65700688.575 | 0% | 0 | 100% | 65700688.575 | 100% | 45 | 0
|  | foting concrete | m3 | 58 | 50 | 0.04813% | 131401377.15 | 100% | 113277049.2672 | 0% | 18124327.8828 | 100% | 131401377.15 | 100% |  | -50
|  | Wall rebar | Kg | 10100 | 10100 | 0.01375% | 37543250.6143 | 100% | 37543250.6143 | 0% | 0 | 100% | 37543250.6143 | 100% |  | -10100
|  | Wall form | m2 | 195 | 185 | 0.01031% | 28157437.9607 | 100% | 26713466.7832 | 0% | 1443971.1775 | 100% | 28157437.9607 | 100% |  | -185
|  | Wall concrete | m3 | 50 | 23 | 0.03209% | 87600918.1 | 100% | 40296422.326 | 0% | 47304495.774 | 100% | 87600918.1 | 100% |  | -23
|  | curing | % | 100 | 65 | 0.002292% | 6257208.4357 | 65% | 4067185.4832 | 0% | 0 | 65% | 4067185.4832 | 65% |  | -65
|  | coating | m2 | 145 | 0 | 0.006876% | 18771625.3071 | 60% | 0 | 0% | 11262975.1843 | 60% | 11262975.1843 | 60% |  | 0
|  | back fill | m3 | 166 | 0 | 0.02292% | 62572084.3571 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 51 | 0.01146% | 31286042.1786 | 51% | 15955881.5111 | 0% | 0 | 51% | 15955881.5111 | 51% | 20 | -31
|  | Retaining wall 11 |  |  |  | 0.2292% | 625720843.5714 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | excavation | m3 | 336 | 0 | 0.01834% | 50057667.4857 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | level&compact | m2 | 88 | 0 | 0.004584% | 12514416.8714 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | lean | m3 | 4 | 0 | 0.002292% | 6257208.4357 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | footing rebar | Kg | 5610 | 0 | 0.03209% | 87600918.1 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | footing form | m2 | 50 | 0 | 0.02407% | 65700688.575 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | foting concrete | m3 | 73 | 0 | 0.04813% | 131401377.15 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall rebar | Kg | 5240 | 0 | 0.01375% | 37543250.6143 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall form | m2 | 167 | 0 | 0.01031% | 28157437.9607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall concrete | m3 | 76 | 0 | 0.03209% | 87600918.1 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | curing | % | 100 | 0 | 0.002292% | 6257208.4357 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | coating | m2 | 263 | 0 | 0.006876% | 18771625.3071 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | back fill | m3 | 166 | 0 | 0.02292% | 62572084.3571 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.01146% | 31286042.1786 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Retaining wall 12 |  |  |  | 0.3438% | 938581265.3571 | 87.8% | 792631878.594 | 0% | 31442472.3895 | 87.8% | 824074350.9835 | 87.8% |  | 0
|  | excavation | m3 | 316 | 316 | 0.0275% | 75086501.2286 | 100% | 75086501.2286 | 0% | 0 | 100% | 75086501.2286 | 100% | 316 | 0
|  | level&compact | m2 | 128 | 128 | 0.006876% | 18771625.3071 | 100% | 18771625.3071 | 0% | 0 | 100% | 18771625.3071 | 100% | 128 | 0
|  | lean | m3 | 4 | 4 | 0.003438% | 9385812.6536 | 100% | 9385812.6536 | 0% | 0 | 100% | 9385812.6536 | 100% |  | -4
|  | footing rebar | Kg | 10025 | 10025 | 0.04813% | 131401377.15 | 100% | 131401377.15 | 0% | 0 | 100% | 131401377.15 | 100% |  | -10025
|  | footing form | m2 | 45 | 45 | 0.0361% | 98551032.8625 | 100% | 98551032.8625 | 0% | 0 | 100% | 98551032.8625 | 100% |  | -45
|  | foting concrete | m3 | 50 | 50 | 0.0722% | 197102065.725 | 100% | 197102065.725 | 0% | 0 | 100% | 197102065.725 | 100% |  | -50
|  | Wall rebar | Kg | 10100 | 10100 | 0.02063% | 56314875.9214 | 100% | 56314875.9214 | 0% | 0 | 100% | 56314875.9214 | 100% |  | -10100
|  | Wall form | m2 | 195 | 195 | 0.01547% | 42236156.9411 | 100% | 42236156.9411 | 0% | 0 | 100% | 42236156.9411 | 100% |  | -195
|  | Wall concrete | m3 | 50 | 50 | 0.04813% | 131401377.15 | 100% | 131401377.15 | 0% | 0 | 100% | 131401377.15 | 100% |  | -50
|  | curing | % | 100 | 100 | 0.003438% | 9385812.6536 | 100% | 6100778.2248 | 0% | 3285034.4287 | 100% | 9385812.6536 | 100% |  | -100
|  | coating | m2 | 145 | 145 | 0.01031% | 28157437.9607 | 100% | 0 | 0% | 28157437.9607 | 100% | 28157437.9607 | 100% |  | -145
|  | back fill | m3 | 166 | 0 | 0.03438% | 93858126.5357 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 56 | 0.01719% | 46929063.2679 | 56% | 26280275.43 | 0% | 0 | 56% | 26280275.43 | 56% | 8 | -48
|  | Retaining wall 13 |  |  |  | 0.1444% | 394204131.45 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | excavation | m3 | 180 | 0 | 0.01155% | 31536330.516 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | level&compact | m2 | 72 | 0 | 0.002888% | 7884082.629 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | lean | m3 | 3 | 0 | 0.001444% | 3942041.3145 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | footing rebar | Kg | 4520 | 0 | 0.02022% | 55188578.403 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | footing form | m2 | 30 | 0 | 0.01516% | 41391433.8022 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | foting concrete | m3 | 35 | 0 | 0.03032% | 82782867.6045 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall rebar | Kg | 4280 | 0 | 0.008664% | 23652247.887 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall form | m2 | 103 | 0 | 0.006498% | 17739185.9152 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Wall concrete | m3 | 28 | 0 | 0.02022% | 55188578.403 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | curing | % | 100 | 0 | 0.001444% | 3942041.3145 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | coating | m2 | 170 | 0 | 0.004332% | 11826123.9435 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | back fill | m3 | 95 | 0 | 0.01444% | 39420413.145 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.00722% | 19710206.5725 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Base |  |  |  | 0.095% | 259350000 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Base | m3 | 560 | 0 | 0.095% | 259350000 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Piping |  |  |  | 19.52% | 53299063883.461 | 11.33% | 5272513442.4227 | 0% | 768914696.2579 | 11.33% | 6041428138.6807 | 11.33% |  | 0
|  | AG Piping |  |  |  | 19.32% | 52754434410.9095 | 11.45% | 5272513442.4227 | 0% | 768914696.2579 | 11.45% | 6041428138.6807 | 11.45% |  | 0
|  | Shop |  |  |  | 6.763% | 18464052043.8183 | 4.93% | 691691624.4658 | 0% | 218650873.4031 | 4.93% | 910342497.8689 | 4.93% |  | 0
|  | Carbon Steel |  |  |  | 3.489% | 9523605519.1553 | 6.743% | 423478228.726 | 0% | 218650873.4031 | 6.743% | 642129102.129 | 6.743% |  | 0
|  | Material Handling From Lay down To Shop | ID | 56511 | 9850 | 0.1744% | 476180275.9578 | 34.25% | 82999340.2733 | 0% | 80092404.2422 | 34.25% | 163091744.5155 | 34.25% | 3390 | -6460
|  | Cutting & Bevelling & Fit Up | ID | 19779 | 226 | 1.221% | 3333261931.7044 | 4.06% | 38086718.0629 | 0% | 97243716.3643 | 4.06% | 135330434.4272 | 4.06% |  | -226
|  | Welding | ID | 19779 | 99 | 1.221% | 3333261931.7044 | 1.74% | 16684004.8151 | 0% | 41314752.7965 | 1.74% | 57998757.6117 | 1.74% |  | -99
|  | NDT | ID | 19779 | 0 | 0.1744% | 476180275.9578 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 19779 | 0 | 0.1744% | 476180275.9578 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 20 | 0.5233% | 1428540827.8733 | 20% | 285708165.5747 | 0% | 0 | 20% | 285708165.5747 | 20% | 20 | 0
|  | Low Temperature CS |  |  |  | 1.993% | 5441886032.4206 | 3% | 163256580.9726 | 0% | 0 | 3% | 163256580.9726 | 3% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.09967% | 272094301.621 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 0.6977% | 1904660111.3472 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.6977% | 1904660111.3472 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.09967% | 272094301.621 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.09967% | 272094301.621 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 20 | 0.299% | 816282904.8631 | 20% | 163256580.9726 | 0% | 0 | 20% | 163256580.9726 | 20% | 20 | 0
|  | Stainless Steel |  |  |  | 1.167% | 3184615197.5497 | 3% | 95538455.9265 | 0% | 0 | 3% | 95538455.9265 | 3% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.05833% | 159230759.8775 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 0.4083% | 1114615319.1424 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.4083% | 1114615319.1424 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.05833% | 159230759.8775 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.05833% | 159230759.8775 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 20 | 0.175% | 477692279.6325 | 20% | 95538455.9265 | 0% | 0 | 20% | 95538455.9265 | 20% | 20 | 0
|  | Galva |  |  |  | 0.115% | 313945294.6927 | 3% | 9418358.8408 | 0% | 0 | 3% | 9418358.8408 | 3% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.00575% | 15697264.7346 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 0.04025% | 109880853.1424 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.04025% | 109880853.1424 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.00575% | 15697264.7346 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.00575% | 15697264.7346 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 20 | 0.01725% | 47091794.2039 | 20% | 9418358.8408 | 0% | 0 | 20% | 9418358.8408 | 20% | 20 | 0
|  | Field |  |  |  | 12.56% | 34290382367.0912 | 14.96% | 4580821817.9569 | 0% | 550263822.8548 | 14.96% | 5131085640.8117 | 14.96% |  | 0
|  | Carbon Steel |  |  |  | 6.478% | 17686299122.466 | 17.25% | 2501471718.1284 | 0% | 550263822.8548 | 17.25% | 3051735540.9833 | 17.25% |  | 0
|  | Material Handling From Shop To Field | ID | 56511 | 4391 | 0.3239% | 884314956.1233 | 7.94% | 68712763.3972 | 0% | 1501844.119 | 7.94% | 70214607.5162 | 7.94% | 452 | -3939
|  | Scaffolding | m2 | 8000 | 5245 | 0.8422% | 2299218885.9206 | 83.08% | 1507425382.0817 | 0% | 402765668.3411 | 83.08% | 1910191050.4228 | 83.08% | 2350 | -2895
|  | Erection & Fit Up | ID | 36732 | 947 | 1.231% | 3360396833.2685 | 5.34% | 86635516.7458 | 0% | 92809674.1508 | 5.34% | 179445190.8965 | 5.34% | 452 | -495
|  | Valve Installation | ID | 1 | 0 | 0.3239% | 884314956.1233 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 36732 | 826 | 2.138% | 5836478710.4138 | 3.16% | 131246091.0052 | 0% | 53186636.2439 | 3.16% | 184432727.2491 | 3.16% | 408 | -418
|  | NDT | ID | 36732 | 0 | 0.162% | 442157478.0617 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 36732 | 0 | 0.1944% | 530588973.674 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 36732 | 0 | 0.6155% | 1680198416.6343 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.6478% | 1768629912.2466 | 40% | 707451964.8986 | 0% | 0 | 40% | 707451964.8986 | 40% | 40 | 0
|  | Low Temperature CS |  |  |  | 3.702% | 10106602329.7798 | 12.52% | 1265662443.0112 | 0% | 0 | 12.52% | 1265662443.0112 | 12.52% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.1851% | 505330116.489 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | m2 | 8000 | 5245 | 0.4813% | 1313858302.8714 | 65.56% | 861398349.82 | 0% | 0 | 65.56% | 861398349.82 | 65.56% | 2350 | -2895
|  | Erection & Fit Up | ID | 1 | 0 | 0.7034% | 1920254442.6582 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.1851% | 505330116.489 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 1.222% | 3335178768.8273 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.09255% | 252665058.2445 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.1111% | 303198069.8934 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.3517% | 960127221.3291 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.3702% | 1010660232.978 | 40% | 404264093.1912 | 0% | 0 | 40% | 404264093.1912 | 40% | 40 | 0
|  | Stainless Steel |  |  |  | 2.166% | 5914425738.9493 | 12.52% | 740670928.3208 | 0% | 0 | 12.52% | 740670928.3208 | 12.52% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.1083% | 295721286.9475 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | m2 | 8000 | 5245 | 0.2816% | 768875346.0634 | 65.56% | 504093898.7628 | 0% | 0 | 65.56% | 504093898.7628 | 65.56% | 2350 | -2895
|  | Erection & Fit Up | ID | 1 | 0 | 0.4116% | 1123740890.4004 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.1083% | 295721286.9475 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.7149% | 1951760493.8533 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.05416% | 147860643.4737 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.06499% | 177432772.1685 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.2058% | 561870445.2002 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.2166% | 591442573.8949 | 40% | 236577029.558 | 0% | 0 | 40% | 236577029.558 | 40% | 40 | 0
|  | Galva |  |  |  | 0.2136% | 583055175.896 | 12.52% | 73016728.4964 | 0% | 0 | 12.52% | 73016728.4964 | 12.52% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.01068% | 29152758.7948 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | m2 | 8000 | 5245 | 0.02776% | 75797172.8665 | 65.56% | 49694521.4606 | 0% | 0 | 65.56% | 49694521.4606 | 65.56% | 2350 | -2895
|  | Erection & Fit Up | ID | 1 | 0 | 0.04058% | 110780483.4202 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.01068% | 29152758.7948 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.07048% | 192408208.0457 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.005339% | 14576379.3974 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.006407% | 17491655.2769 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.02029% | 55390241.7101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.02136% | 58305517.5896 | 40% | 23322207.0358 | 0% | 0 | 40% | 23322207.0358 | 40% | 40 | 0
|  | Pipe Support |  |  |  | 0.1995% | 544629472.5515 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Shop |  |  |  | 0.06982% | 190620315.393 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Handling | Kg | 1 | 0 | 0.007681% | 20968234.6932 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | shop drawing | Kg | 1 | 0 | 0.01117% | 30499250.4629 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & assembling | Kg | 1 | 0 | 0.01536% | 41936469.3865 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | Kg | 1 | 0 | 0.03212% | 87685345.0808 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.003491% | 9531015.7697 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Field |  |  |  | 0.1297% | 354009157.1585 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling From Shop To Field | Kg | 1 | 0 | 0.01426% | 38941007.2874 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection | Kg | 1 | 0 | 0.02723% | 74341923.0033 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | Kg | 1 | 0 | 0.06743% | 184084761.7224 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | Kg | 1 | 0 | 0.01426% | 38941007.2874 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.006484% | 17700457.8579 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Painting & Sandblasting |  |  |  | 2.557% | 6981261473.2359 | 7.621% | 459972099.3907 | 0% | 72092077.1985 | 7.621% | 532064176.5893 | 7.621% |  | 0
|  | Pipe |  |  |  | 2.531% | 6909924371.2893 | 7.7% | 459972099.3907 | 0% | 72092077.1985 | 7.7% | 532064176.5893 | 7.7% |  | 0
|  | Sand Blast | m2 | 39250 | 7465 | 0.3797% | 1036488655.6934 | 22% | 197130899.7389 | 0% | 30896604.5137 | 22% | 228027504.2525 | 22% | 1886 | -5579
|  | Primer | m2 | 39250 | 7465 | 0.5062% | 1381984874.2579 | 22% | 262841199.6518 | 0% | 41195472.6849 | 22% | 304036672.3367 | 22% | 1886 | -5579
|  | Middle Paint | m2 | 39250 | 0 | 0.8859% | 2418473529.9513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Paint | m2 | 39250 | 0 | 0.5062% | 1381984874.2579 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Touch Up & Punch | m2 | 39250 | 0 | 0.1266% | 345496218.5645 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.1266% | 345496218.5645 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Support |  |  |  | 0.02613% | 71337101.9466 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Sand Blast | m2 | 1 | 0 | 0.00392% | 10700565.292 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Primer | m2 | 1 | 0 | 0.005226% | 14267420.3893 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Middle Paint | m2 | 1 | 0 | 0.009146% | 24967985.6813 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Paint | m2 | 1 | 0 | 0.005226% | 14267420.3893 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Touch Up & Punch | m2 | 1 | 0 | 0.001307% | 3566855.0973 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.001307% | 3566855.0973 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Steel Structure |  |  |  | 7.466% | 20382161565.2495 | 80.2% | 16346716927.9197 | 0% | 0 | 80.2% | 16346716927.9197 | 80.2% |  | 0
|  | Installation Steel Structure |  |  |  | 7.399% | 20199094247.4445 | 80.93% | 16346716927.9198 | 0% | 0 | 80.93% | 16346716927.9198 | 80.93% |  | 0
|  | 140-IM-A1 |  |  |  | 0.2474% | 675272122.5695 | 95.05% | 641846152.5023 | 0% | 0 | 95.05% | 641846152.5023 | 95.05% |  | 0
|  | Handling | Kg | 94004 | 94004 | 0.02474% | 67527212.2569 | 100% | 67527212.2569 | 0% | 0 | 100% | 67527212.2569 | 100% | 94004 | 0
|  | Chip&Padding | NO | 14 | 14 | 0.01237% | 33763606.1285 | 100% | 33763606.1285 | 0% | 0 | 100% | 33763606.1285 | 100% | 14 | 0
|  | Erection | Kg | 94004 | 94004 | 0.09894% | 270108849.0278 | 100% | 270108849.0278 | 0% | 0 | 100% | 270108849.0278 | 100% | 94004 | 0
|  | Alignment | Kg | 94004 | 94004 | 0.02968% | 81032654.7083 | 100% | 81032654.7083 | 0% | 0 | 100% | 81032654.7083 | 100% | 94004 | 0
|  | Bolt Tightening & Test | Kg | 94004 | 94004 | 0.01979% | 54021769.8056 | 100% | 54021769.8056 | 0% | 0 | 100% | 54021769.8056 | 100% | 94004 | 0
|  | Grouting | NO | 14 | 14 | 0.02474% | 67527212.2569 | 100% | 67527212.2569 | 0% | 0 | 100% | 67527212.2569 | 100% | 14 | 0
|  | Final test & Documents | % | 100 | 67 | 0.0371% | 101290818.3854 | 67% | 67864848.3182 | 0% | 0 | 67% | 67864848.3182 | 67% | 62 | -5
|  | 140-IM-A2 |  |  |  | 0.3595% | 981308229.9461 | 95.05% | 932733472.5637 | 0% | 0 | 95.05% | 932733472.5637 | 95.05% |  | 0
|  | Handling | Kg | 136607 | 136607 | 0.03595% | 98130822.9946 | 100% | 98130822.9946 | 0% | 0 | 100% | 98130822.9946 | 100% | 136607 | 0
|  | Chip&Padding | NO | 16 | 16 | 0.01797% | 49065411.4973 | 100% | 49065411.4973 | 0% | 0 | 100% | 49065411.4973 | 100% | 16 | 0
|  | Erection | Kg | 136607 | 136607 | 0.1438% | 392523291.9784 | 100% | 392523291.9784 | 0% | 0 | 100% | 392523291.9784 | 100% | 136607 | 0
|  | Alignment | Kg | 136607 | 136607 | 0.04313% | 117756987.5935 | 100% | 117756987.5935 | 0% | 0 | 100% | 117756987.5935 | 100% | 136607 | 0
|  | Bolt Tightening & Test | Kg | 136607 | 136607 | 0.02876% | 78504658.3957 | 100% | 78504658.3957 | 0% | 0 | 100% | 78504658.3957 | 100% | 136607 | 0
|  | Grouting | NO | 16 | 16 | 0.03595% | 98130822.9946 | 100% | 98130822.9946 | 0% | 0 | 100% | 98130822.9946 | 100% | 16 | 0
|  | Final test & Documents | % | 100 | 67 | 0.05392% | 147196234.4919 | 67% | 98621477.1096 | 0% | 0 | 67% | 98621477.1096 | 67% | 63 | -4
|  | 140-IM-A3 |  |  |  | 0.2126% | 580421976.7628 | 95.05% | 551691088.9131 | 0% | 0 | 95.05% | 551691088.9131 | 95.05% |  | 0
|  | Handling | Kg | 80800 | 80800 | 0.02126% | 58042197.6763 | 100% | 58042197.6763 | 0% | 0 | 100% | 58042197.6763 | 100% | 80800 | 0
|  | Chip&Padding | NO | 16 | 16 | 0.01063% | 29021098.8381 | 100% | 29021098.8381 | 0% | 0 | 100% | 29021098.8381 | 100% | 16 | 0
|  | Erection | Kg | 80800 | 80800 | 0.08504% | 232168790.7051 | 100% | 232168790.7051 | 0% | 0 | 100% | 232168790.7051 | 100% | 80800 | 0
|  | Alignment | Kg | 80800 | 80800 | 0.02551% | 69650637.2115 | 100% | 69650637.2115 | 0% | 0 | 100% | 69650637.2115 | 100% | 80800 | 0
|  | Bolt Tightening & Test | Kg | 80800 | 80800 | 0.01701% | 46433758.141 | 100% | 46433758.141 | 0% | 0 | 100% | 46433758.141 | 100% | 80800 | 0
|  | Grouting | NO | 16 | 16 | 0.02126% | 58042197.6763 | 100% | 58042197.6763 | 0% | 0 | 100% | 58042197.6763 | 100% | 16 | 0
|  | Final test & Documents | % | 100 | 67 | 0.03189% | 87063296.5144 | 67% | 58332408.6647 | 0% | 0 | 67% | 58332408.6647 | 67% | 63 | -4
|  | 140-IM-A4 |  |  |  | 0.1649% | 450056902.081 | 95.05% | 427779085.428 | 0% | 0 | 95.05% | 427779085.428 | 95.05% |  | 0
|  | Handling | Kg | 62652 | 62652 | 0.01649% | 45005690.2081 | 100% | 45005690.2081 | 0% | 0 | 100% | 45005690.2081 | 100% | 62652 | 0
|  | Chip&Padding | NO | 14 | 14 | 0.008243% | 22502845.1041 | 100% | 22502845.1041 | 0% | 0 | 100% | 22502845.1041 | 100% | 14 | 0
|  | Erection | Kg | 62652 | 62652 | 0.06594% | 180022760.8324 | 100% | 180022760.8324 | 0% | 0 | 100% | 180022760.8324 | 100% | 62652 | 0
|  | Alignment | Kg | 62652 | 62652 | 0.01978% | 54006828.2497 | 100% | 54006828.2497 | 0% | 0 | 100% | 54006828.2497 | 100% | 62652 | 0
|  | Bolt Tightening & Test | Kg | 62652 | 62652 | 0.01319% | 36004552.1665 | 100% | 36004552.1665 | 0% | 0 | 100% | 36004552.1665 | 100% | 62652 | 0
|  | Grouting | NO | 14 | 14 | 0.01649% | 45005690.2081 | 100% | 45005690.2081 | 0% | 0 | 100% | 45005690.2081 | 100% | 14 | 0
|  | Final test & Documents | % | 100 | 67 | 0.02473% | 67508535.3122 | 67% | 45230718.6591 | 0% | 0 | 67% | 45230718.6591 | 67% | 62 | -5
|  | 140-IM-A5 |  |  |  | 0.4729% | 1291050992.5208 | 95.05% | 1227143968.391 | 0% | 0 | 95.05% | 1227143968.391 | 95.05% |  | 0
|  | Handling | Kg | 179726 | 179726 | 0.04729% | 129105099.2521 | 100% | 129105099.2521 | 0% | 0 | 100% | 129105099.2521 | 100% | 179726 | 0
|  | Chip&Padding | NO | 32 | 32 | 0.02365% | 64552549.626 | 100% | 64552549.626 | 0% | 0 | 100% | 64552549.626 | 100% | 32 | 0
|  | Erection | Kg | 179726 | 179726 | 0.1892% | 516420397.0083 | 100% | 516420397.0083 | 0% | 0 | 100% | 516420397.0083 | 100% | 179726 | 0
|  | Alignment | Kg | 179726 | 179726 | 0.05675% | 154926119.1025 | 100% | 154926119.1025 | 0% | 0 | 100% | 154926119.1025 | 100% | 179726 | 0
|  | Bolt Tightening & Test | Kg | 179726 | 179726 | 0.03783% | 103284079.4017 | 100% | 103284079.4017 | 0% | 0 | 100% | 103284079.4017 | 100% | 179726 | 0
|  | Grouting | NO | 32 | 32 | 0.04729% | 129105099.2521 | 100% | 129105099.2521 | 0% | 0 | 100% | 129105099.2521 | 100% | 32 | 0
|  | Final test & Documents | % | 100 | 67 | 0.07094% | 193657648.8781 | 67% | 129750624.7483 | 0% | 0 | 67% | 129750624.7483 | 67% | 64 | -3
|  | 140-IM-A6 |  |  |  | 0.3567% | 973902102.9901 | 94.86% | 923803267.4034 | 0% | 0 | 94.86% | 923803267.4034 | 94.86% |  | 0
|  | Handling | Kg | 135576 | 135200 | 0.03567% | 97390210.299 | 99.72% | 97120112.9435 | 0% | 0 | 99.72% | 97120112.9435 | 99.72% | 135200 | 0
|  | Chip&Padding | NO | 33 | 33 | 0.01784% | 48695105.1495 | 100% | 48695105.1495 | 0% | 0 | 100% | 48695105.1495 | 100% | 33 | 0
|  | Erection | Kg | 135576 | 135200 | 0.1427% | 389560841.196 | 99.72% | 388480451.7739 | 0% | 0 | 99.72% | 388480451.7739 | 99.72% | 135199 | -1
|  | Alignment | Kg | 135576 | 135200 | 0.04281% | 116868252.3588 | 99.72% | 116544135.5322 | 0% | 0 | 99.72% | 116544135.5322 | 99.72% | 135199 | -1
|  | Bolt Tightening & Test | Kg | 135576 | 135200 | 0.02854% | 77912168.2392 | 99.72% | 77696090.3548 | 0% | 0 | 99.72% | 77696090.3548 | 99.72% | 135199 | -1
|  | Grouting | NO | 33 | 33 | 0.03567% | 97390210.299 | 100% | 97390210.299 | 0% | 0 | 100% | 97390210.299 | 100% | 33 | 0
|  | Final test & Documents | % | 100 | 67 | 0.05351% | 146085315.4485 | 67% | 97877161.3505 | 0% | 0 | 67% | 97877161.3505 | 67% | 64 | -3
|  | 140-IM-A7 |  |  |  | 0.1538% | 419843352.152 | 14% | 58778069.3013 | 0% | 0 | 14% | 58778069.3013 | 14% |  | 0
|  | Handling | Kg | 58446 | 58446 | 0.01538% | 41984335.2152 | 100% | 41984335.2152 | 0% | 0 | 100% | 41984335.2152 | 100% | 58446 | 0
|  | Chip&Padding | NO | 16 | 8 | 0.007689% | 20992167.6076 | 50% | 10496083.8038 | 0% | 0 | 50% | 10496083.8038 | 50% | 8 | 0
|  | Erection | Kg | 58446 | 0 | 0.06152% | 167937340.8608 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Alignment | Kg | 58446 | 0 | 0.01845% | 50381202.2582 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 58446 | 0 | 0.0123% | 33587468.1722 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Grouting | NO | 16 | 0 | 0.01538% | 41984335.2152 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 10 | 0.02307% | 62976502.8228 | 10% | 6297650.2823 | 0% | 0 | 10% | 6297650.2823 | 10% | 10 | 0
|  | 140-IM-B1 |  |  |  | 0.1758% | 479853812.4723 | 9.6% | 46068121.0294 | 0% | 0 | 9.6% | 46068121.0294 | 9.6% |  | 0
|  | Handling | Kg | 66800 | 64131 | 0.01758% | 47985381.2472 | 96% | 46068121.0294 | 0% | 0 | 96% | 46068121.0294 | 96% | 64131 | 0
|  | Chip&Padding | NO | 10 | 0 | 0.008789% | 23992690.6236 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Erection | Kg | 66800 | 0 | 0.07031% | 191941524.9889 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Alignment | Kg | 66800 | 0 | 0.02109% | 57582457.4967 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 66800 | 0 | 0.01406% | 38388304.9978 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Grouting | NO | 10 | 0 | 0.01758% | 47985381.2472 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 0 | 0.02637% | 71978071.8708 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7 | 7
|  | 140-IM-B2 |  |  |  | 0.4518% | 1233353599.9792 | 9.944% | 122650778.1367 | 0% | 0 | 9.944% | 122650778.1367 | 9.944% |  | 0
|  | Handling | Kg | 171694 | 170741 | 0.04518% | 123335359.9979 | 99.44% | 122650778.1367 | 0% | 0 | 99.44% | 122650778.1367 | 99.44% | 170741 | 0
|  | Chip&Padding | NO | 12 | 0 | 0.02259% | 61667679.999 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Erection | Kg | 171694 | 0 | 0.1807% | 493341439.9917 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Alignment | Kg | 171694 | 0 | 0.05421% | 148002431.9975 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 171694 | 0 | 0.03614% | 98668287.9983 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Grouting | NO | 12 | 0 | 0.04518% | 123335359.9979 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 0 | 0.06777% | 185003039.9969 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 7 | 7
|  | 140-IM-B3 |  |  |  | 0.4453% | 1215718254.0268 | 93.7% | 1139126854.6727 | 0% | 0 | 93.7% | 1139126854.6727 | 93.7% |  | 0
|  | Handling | Kg | 169239 | 169239 | 0.04453% | 121571825.4027 | 100% | 121571825.4027 | 0% | 0 | 100% | 121571825.4027 | 100% | 167795 | -1444
|  | Chip&Padding | NO | 28 | 28 | 0.02227% | 60785912.7013 | 100% | 60785912.7013 | 0% | 0 | 100% | 60785912.7013 | 100% | 28 | 0
|  | Erection | Kg | 169239 | 169238.6 | 0.1781% | 486287301.6107 | 100% | 486286152.2603 | 0% | 0 | 100% | 486286152.2603 | 100% | 167795 | -1443.6
|  | Alignment | Kg | 169239 | 169239 | 0.05344% | 145886190.4832 | 100% | 145886190.4832 | 0% | 0 | 100% | 145886190.4832 | 100% | 167795 | -1444
|  | Bolt Tightening & Test | Kg | 169239 | 169239 | 0.03563% | 97257460.3221 | 100% | 97257460.3221 | 0% | 0 | 100% | 97257460.3221 | 100% | 0 | -169239
|  | Grouting | NO | 28 | 28 | 0.04453% | 121571825.4027 | 100% | 121571825.4027 | 0% | 0 | 100% | 121571825.4027 | 100% | 0 | -28
|  | Final test & Documents | % | 100 | 58 | 0.0668% | 182357738.104 | 58% | 105767488.1003 | 0% | 0 | 58% | 105767488.1003 | 58% | 48 | -10
|  | 140-IM-B4 |  |  |  | 0.3028% | 826569742.3044 | 94.39% | 780198314.8749 | 0% | 0 | 94.39% | 780198314.8749 | 94.39% |  | 0
|  | Handling | Kg | 115066 | 115066 | 0.03028% | 82656974.2304 | 100% | 82656974.2304 | 0% | 0 | 100% | 82656974.2304 | 100% | 115066 | 0
|  | Chip&Padding | NO | 20 | 20 | 0.01514% | 41328487.1152 | 100% | 41328487.1152 | 0% | 0 | 100% | 41328487.1152 | 100% | 20 | 0
|  | Erection | Kg | 115066 | 114950.6 | 0.1211% | 330627896.9218 | 99.9% | 330296309.3172 | 0% | 0 | 99.9% | 330296309.3172 | 99.9% | 113646 | -1304.6
|  | Alignment | Kg | 115066 | 114951 | 0.03633% | 99188369.0765 | 99.9% | 99089237.6003 | 0% | 0 | 99.9% | 99089237.6003 | 99.9% | 113646 | -1305
|  | Bolt Tightening & Test | Kg | 115066 | 114951 | 0.02422% | 66125579.3844 | 99.9% | 66059491.7335 | 0% | 0 | 99.9% | 66059491.7335 | 99.9% | 113646 | -1305
|  | Grouting | NO | 20 | 20 | 0.03028% | 82656974.2304 | 100% | 82656974.2304 | 0% | 0 | 100% | 82656974.2304 | 100% | 20 | 0
|  | Final test & Documents | % | 100 | 63 | 0.04542% | 123985461.3457 | 63% | 78110840.6478 | 0% | 0 | 63% | 78110840.6478 | 63% | 62 | -1
|  | 140-IM-B5 |  |  |  | 0.1895% | 517250802.7077 | 94.12% | 486838324.6789 | 0% | 0 | 94.12% | 486838324.6789 | 94.12% |  | 0
|  | Handling | Kg | 72807 | 72807 | 0.01895% | 51725080.2708 | 100% | 51725080.2708 | 0% | 0 | 100% | 51725080.2708 | 100% | 72293 | -514
|  | Chip&Padding | NO | 10 | 10 | 0.009473% | 25862540.1354 | 100% | 25862540.1354 | 0% | 0 | 100% | 25862540.1354 | 100% | 10 | 0
|  | Erection | Kg | 72807 | 72407 | 0.07579% | 206900321.0831 | 99.45% | 205763615.4307 | 0% | 0 | 99.45% | 205763615.4307 | 99.45% | 72293 | -114
|  | Alignment | Kg | 72807 | 72407 | 0.02274% | 62070096.3249 | 99.45% | 61729084.6292 | 0% | 0 | 99.45% | 61729084.6292 | 99.45% | 72293 | -114
|  | Bolt Tightening & Test | Kg | 72807 | 72407 | 0.01516% | 41380064.2166 | 99.45% | 41152723.0861 | 0% | 0 | 99.45% | 41152723.0861 | 99.45% | 72293 | -114
|  | Grouting | NO | 10 | 10 | 0.01895% | 51725080.2708 | 100% | 51725080.2708 | 0% | 0 | 100% | 51725080.2708 | 100% | 10 | 0
|  | Final test & Documents | % | 100 | 63 | 0.02842% | 77587620.4062 | 63% | 48880200.8559 | 0% | 0 | 63% | 48880200.8559 | 63% | 62 | -1
|  | 140-IM-B6 |  |  |  | 0.4257% | 1162072321.8181 | 94.37% | 1096599785.4003 | 0% | 0 | 94.37% | 1096599785.4003 | 94.37% |  | 0
|  | Handling | Kg | 161771 | 161771 | 0.04257% | 116207232.1818 | 100% | 116207232.1818 | 0% | 0 | 100% | 116207232.1818 | 100% | 161544 | -227
|  | Chip&Padding | NO | 26 | 26 | 0.02128% | 58103616.0909 | 100% | 58103616.0909 | 0% | 0 | 100% | 58103616.0909 | 100% | 26 | 0
|  | Erection | Kg | 161771 | 161544.3 | 0.1703% | 464828928.7272 | 99.86% | 464177534.3602 | 0% | 0 | 99.86% | 464177534.3602 | 99.86% | 161544 | -0.3
|  | Alignment | Kg | 161771 | 161544 | 0.05108% | 139448678.6182 | 99.86% | 139253001.7042 | 0% | 0 | 99.86% | 139253001.7042 | 99.86% | 161544 | 0
|  | Bolt Tightening & Test | Kg | 161771 | 161544 | 0.03405% | 92965785.7454 | 99.86% | 92835334.4695 | 0% | 0 | 99.86% | 92835334.4695 | 99.86% | 161544 | 0
|  | Grouting | NO | 26 | 26 | 0.04257% | 116207232.1818 | 100% | 116207232.1818 | 0% | 0 | 100% | 116207232.1818 | 100% | 26 | 0
|  | Final test & Documents | % | 100 | 63 | 0.06385% | 174310848.2727 | 63% | 109815834.4118 | 0% | 0 | 63% | 109815834.4118 | 63% | 62 | -1
|  | 140-IM-B7 |  |  |  | 0.2262% | 617610647.2294 | 94.38% | 582901387.877 | 0% | 0 | 94.38% | 582901387.877 | 94.38% |  | 0
|  | Handling | Kg | 85977 | 85977 | 0.02262% | 61761064.7229 | 100% | 61761064.7229 | 0% | 0 | 100% | 61761064.7229 | 100% | 85857 | -120
|  | Chip&Padding | NO | 12 | 12 | 0.01131% | 30880532.3615 | 100% | 30880532.3615 | 0% | 0 | 100% | 30880532.3615 | 100% | 12 | 0
|  | Erection | Kg | 85977 | 85876.7 | 0.09049% | 247044258.8918 | 99.88% | 246756059.2667 | 0% | 0 | 99.88% | 246756059.2667 | 99.88% | 83375 | -2501.7
|  | Alignment | Kg | 85977 | 85877 | 0.02715% | 74113277.6675 | 99.88% | 74027076.3839 | 0% | 0 | 99.88% | 74027076.3839 | 99.88% | 83375 | -2502
|  | Bolt Tightening & Test | Kg | 85977 | 85877 | 0.0181% | 49408851.7784 | 99.88% | 49351384.2559 | 0% | 0 | 99.88% | 49351384.2559 | 99.88% | 83375 | -2502
|  | Grouting | NO | 12 | 12 | 0.02262% | 61761064.7229 | 100% | 61761064.7229 | 0% | 0 | 100% | 61761064.7229 | 100% | 12 | 0
|  | Final test & Documents | % | 100 | 63 | 0.03393% | 92641597.0844 | 63% | 58364206.1632 | 0% | 0 | 63% | 58364206.1632 | 63% | 61 | -2
|  | 140-IM-B8 |  |  |  | 0.2579% | 704070534.7581 | 94.57% | 665818122.4923 | 0% | 0 | 94.57% | 665818122.4923 | 94.57% |  | 0
|  | Handling | Kg | 98013 | 98013 | 0.02579% | 70407053.4758 | 100% | 70407053.4758 | 0% | 0 | 100% | 70407053.4758 | 100% | 97681 | -332
|  | Chip&Padding | NO | 12 | 12 | 0.0129% | 35203526.7379 | 100% | 35203526.7379 | 0% | 0 | 100% | 35203526.7379 | 100% | 12 | 0
|  | Erection | Kg | 98013 | 97714 | 0.1032% | 281628213.9033 | 99.69% | 280769074.4426 | 0% | 0 | 99.69% | 280769074.4426 | 99.69% | 97320 | -394
|  | Alignment | Kg | 98013 | 97714 | 0.03095% | 84488464.171 | 99.69% | 84230722.3328 | 0% | 0 | 99.69% | 84230722.3328 | 99.69% | 97320 | -394
|  | Bolt Tightening & Test | Kg | 98013 | 97714 | 0.02063% | 56325642.7807 | 99.69% | 56153814.8885 | 0% | 0 | 99.69% | 56153814.8885 | 99.69% | 97320 | -394
|  | Grouting | NO | 12 | 12 | 0.02579% | 70407053.4758 | 100% | 70407053.4758 | 0% | 0 | 100% | 70407053.4758 | 100% | 12 | 0
|  | Final test & Documents | % | 100 | 65 | 0.03869% | 105610580.2137 | 65% | 68646877.1389 | 0% | 0 | 65% | 68646877.1389 | 65% | 62 | -3
|  | 140-IM-B9 |  |  |  | 0.1566% | 427414698.235 | 94.45% | 403693182.483 | 0% | 0 | 94.45% | 403693182.483 | 94.45% |  | 0
|  | Handling | Kg | 59500 | 59500 | 0.01566% | 42741469.8235 | 100% | 42741469.8235 | 0% | 0 | 100% | 42741469.8235 | 100% | 59500 | 0
|  | Chip&Padding | NO | 8 | 8 | 0.007828% | 21370734.9118 | 100% | 21370734.9118 | 0% | 0 | 100% | 21370734.9118 | 100% | 8 | 0
|  | Erection | Kg | 59500 | 59500 | 0.06262% | 170965879.294 | 100% | 170965879.294 | 0% | 0 | 100% | 170965879.294 | 100% | 59500 | 0
|  | Alignment | Kg | 59500 | 59500 | 0.01879% | 51289763.7882 | 100% | 51289763.7882 | 0% | 0 | 100% | 51289763.7882 | 100% | 59500 | 0
|  | Bolt Tightening & Test | Kg | 59500 | 59500 | 0.01252% | 34193175.8588 | 100% | 34193175.8588 | 0% | 0 | 100% | 34193175.8588 | 100% | 59500 | 0
|  | Grouting | NO | 8 | 8 | 0.01566% | 42741469.8235 | 100% | 42741469.8235 | 0% | 0 | 100% | 42741469.8235 | 100% | 8 | 0
|  | Final test & Documents | % | 100 | 63 | 0.02348% | 64112204.7353 | 63% | 40390688.9832 | 0% | 0 | 63% | 40390688.9832 | 63% | 62 | -1
|  | 140-IM-B10 |  |  |  | 0.2676% | 730555879.1681 | 73.89% | 539822896.1763 | 0% | 0 | 73.89% | 539822896.1763 | 73.89% |  | 0
|  | Handling | Kg | 101700 | 101700 | 0.02676% | 73055587.9168 | 100% | 73055587.9168 | 0% | 0 | 100% | 73055587.9168 | 100% | 101700 | 0
|  | Chip&Padding | NO | 12 | 12 | 0.01338% | 36527793.9584 | 100% | 36527793.9584 | 0% | 0 | 100% | 36527793.9584 | 100% | 12 | 0
|  | Erection | Kg | 101700 | 80400 | 0.107% | 292222351.6672 | 79.06% | 231019440.2561 | 0% | 0 | 79.06% | 231019440.2561 | 79.06% | 80400 | 0
|  | Alignment | Kg | 101700 | 80400 | 0.03211% | 87666705.5002 | 79.06% | 69305832.0768 | 0% | 0 | 79.06% | 69305832.0768 | 79.06% | 80400 | 0
|  | Bolt Tightening & Test | Kg | 101700 | 64193 | 0.02141% | 58444470.3334 | 63.12% | 36890126.6875 | 0% | 0 | 63.12% | 36890126.6875 | 63.12% | 0 | -64193
|  | Grouting | NO | 12 | 7 | 0.02676% | 73055587.9168 | 58.33% | 42615759.6181 | 0% | 0 | 58.33% | 42615759.6181 | 58.33% | 0 | -7
|  | Final test & Documents | % | 100 | 46 | 0.04014% | 109583381.8752 | 46% | 50408355.6626 | 0% | 0 | 46% | 50408355.6626 | 46% | 42 | -4
|  | 140-IM-B11 |  |  |  | 0.3757% | 1025673157.2788 | 94.45% | 968748297.0499 | 0% | 0 | 94.45% | 968748297.0499 | 94.45% |  | 0
|  | Handling | Kg | 142783 | 142783 | 0.03757% | 102567315.7279 | 100% | 102567315.7279 | 0% | 0 | 100% | 102567315.7279 | 100% | 142783 | 0
|  | Chip&Padding | NO | 24 | 24 | 0.01879% | 51283657.8639 | 100% | 51283657.8639 | 0% | 0 | 100% | 51283657.8639 | 100% | 24 | 0
|  | Erection | Kg | 142783 | 142783 | 0.1503% | 410269262.9115 | 100% | 410269262.9115 | 0% | 0 | 100% | 410269262.9115 | 100% | 142783 | 0
|  | Alignment | Kg | 142783 | 142783 | 0.04508% | 123080778.8735 | 100% | 123080778.8735 | 0% | 0 | 100% | 123080778.8735 | 100% | 142783 | 0
|  | Bolt Tightening & Test | Kg | 142783 | 142783 | 0.03006% | 82053852.5823 | 100% | 82053852.5823 | 0% | 0 | 100% | 82053852.5823 | 100% | 142783 | 0
|  | Grouting | NO | 24 | 24 | 0.03757% | 102567315.7279 | 100% | 102567315.7279 | 0% | 0 | 100% | 102567315.7279 | 100% | 24 | 0
|  | Final test & Documents | % | 100 | 63 | 0.05636% | 153850973.5918 | 63% | 96926113.3628 | 0% | 0 | 63% | 96926113.3628 | 63% | 57 | -6
|  | 140-IM-B12 |  |  |  | 0.2155% | 588323761.1 | 61.15% | 359759979.9126 | 0% | 0 | 61.15% | 359759979.9126 | 61.15% |  | 0
|  | Handling | Kg | 81227 | 81227 | 0.02155% | 58832376.11 | 100% | 58832376.11 | 0% | 0 | 100% | 58832376.11 | 100% | 81169 | -58
|  | Chip&Padding | NO | 6 | 6 | 0.01078% | 29416188.055 | 100% | 29416188.055 | 0% | 0 | 100% | 29416188.055 | 100% | 6 | 0
|  | Erection | Kg | 81227 | 81227 | 0.0862% | 235329504.44 | 100% | 235329504.44 | 0% | 0 | 100% | 235329504.44 | 100% | 81000 | -227
|  | Alignment | Kg | 81227 | 0 | 0.02586% | 70598851.332 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 81227 | 0 | 0.01724% | 47065900.888 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Grouting | NO | 6 | 0 | 0.02155% | 58832376.11 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 41 | 0.03233% | 88248564.165 | 41% | 36181911.3076 | 0% | 0 | 41% | 36181911.3076 | 41% | 41 | 0
|  | 140-IM-B13 |  |  |  | 0.3027% | 826361422.5355 | 46.01% | 380204916.6294 | 0% | 0 | 46.01% | 380204916.6294 | 46.01% |  | 0
|  | Handling | Kg | 115037 | 115037 | 0.03027% | 82636142.2535 | 100% | 82636142.2535 | 0% | 0 | 100% | 82636142.2535 | 100% | 114739 | -298
|  | Chip&Padding | NO | 14 | 14 | 0.01513% | 41318071.1268 | 100% | 41318071.1268 | 0% | 0 | 100% | 41318071.1268 | 100% | 14 | 0
|  | Erection | Kg | 115037 | 75808 | 0.1211% | 330544569.0142 | 65.9% | 217824897.1012 | 0% | 0 | 65.9% | 217824897.1012 | 65.9% | 75656 | -152
|  | Alignment | Kg | 115037 | 0 | 0.03632% | 99163370.7043 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Bolt Tightening & Test | Kg | 115037 | 0 | 0.02422% | 66108913.8028 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Grouting | NO | 14 | 0 | 0.03027% | 82636142.2535 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | Final test & Documents | % | 100 | 31 | 0.0454% | 123954213.3803 | 31% | 38425806.1479 | 0% | 0 | 31% | 38425806.1479 | 31% | 31 | 0
|  | 140-IM-C1 |  |  |  | 0.08789% | 239926906.2361 | 93.4% | 224090581.0741 | 0% | 0 | 93.4% | 224090581.0741 | 93.4% |  | 0
|  | Handling | Kg | 33400 | 33400 | 0.008789% | 23992690.6236 | 100% | 23992690.6236 | 0% | 0 | 100% | 23992690.6236 | 100% | 33400 | 0
|  | Chip&Padding | NO | 12 | 12 | 0.004394% | 11996345.3118 | 100% | 11996345.3118 | 0% | 0 | 100% | 11996345.3118 | 100% | 12 | 0
|  | Erection | Kg | 33400 | 33399.6 | 0.03515% | 95970762.4945 | 100% | 95969613.144 | 0% | 0 | 100% | 95969613.144 | 100% | 33400 | 0.4
|  | Alignment | Kg | 33400 | 33400 | 0.01055% | 28791228.7483 | 100% | 28791228.7483 | 0% | 0 | 100% | 28791228.7483 | 100% | 0 | -33400
|  | Bolt Tightening & Test | Kg | 33400 | 33400 | 0.007031% | 19194152.4989 | 100% | 19194152.4989 | 0% | 0 | 100% | 19194152.4989 | 100% | 0 | -33400
|  | Grouting | NO | 12 | 12 | 0.008789% | 23992690.6236 | 100% | 23992690.6236 | 0% | 0 | 100% | 23992690.6236 | 100% | 0 | -12
|  | Final test & Documents | % | 100 | 56 | 0.01318% | 35989035.9354 | 56% | 20153860.1238 | 0% | 0 | 56% | 20153860.1238 | 56% | 41 | -15
|  | 140-IM-C2 |  |  |  | 0.1658% | 452556739.3077 | 94.45% | 427439840.2761 | 0% | 0 | 94.45% | 427439840.2761 | 94.45% |  | 0
|  | Handling | Kg | 63000 | 63000 | 0.01658% | 45255673.9308 | 100% | 45255673.9308 | 0% | 0 | 100% | 45255673.9308 | 100% | 63000 | 0
|  | Chip&Padding | NO | 22 | 22 | 0.008289% | 22627836.9654 | 100% | 22627836.9654 | 0% | 0 | 100% | 22627836.9654 | 100% | 22 | 0
|  | Erection | Kg | 63000 | 63000 | 0.06631% | 181022695.7231 | 100% | 181022695.7231 | 0% | 0 | 100% | 181022695.7231 | 100% | 61847 | -1153
|  | Alignment | Kg | 63000 | 63000 | 0.01989% | 54306808.7169 | 100% | 54306808.7169 | 0% | 0 | 100% | 54306808.7169 | 100% | 0 | -63000
|  | Bolt Tightening & Test | Kg | 63000 | 63000 | 0.01326% | 36204539.1446 | 100% | 36204539.1446 | 0% | 0 | 100% | 36204539.1446 | 100% | 0 | -63000
|  | Grouting | NO | 22 | 22 | 0.01658% | 45255673.9308 | 100% | 45255673.9308 | 0% | 0 | 100% | 45255673.9308 | 100% | 0 | -22
|  | Final test & Documents | % | 100 | 63 | 0.02487% | 67883510.8961 | 63% | 42766611.8646 | 0% | 0 | 63% | 42766611.8646 | 63% | 41 | -22
|  | 140-IM-C3 |  |  |  | 0.08368% | 228433401.7458 | 94.45% | 215755347.9489 | 0% | 0 | 94.45% | 215755347.9489 | 94.45% |  | 0
|  | Handling | Kg | 31800 | 31800 | 0.008368% | 22843340.1746 | 100% | 22843340.1746 | 0% | 0 | 100% | 22843340.1746 | 100% | 31800 | 0
|  | Chip&Padding | NO | 12 | 12 | 0.004184% | 11421670.0873 | 100% | 11421670.0873 | 0% | 0 | 100% | 11421670.0873 | 100% | 12 | 0
|  | Erection | Kg | 31800 | 31800 | 0.03347% | 91373360.6983 | 100% | 91373360.6983 | 0% | 0 | 100% | 91373360.6983 | 100% | 31800 | 0
|  | Alignment | Kg | 31800 | 31800 | 0.01004% | 27412008.2095 | 100% | 27412008.2095 | 0% | 0 | 100% | 27412008.2095 | 100% | 0 | -31800
|  | Bolt Tightening & Test | Kg | 31800 | 31800 | 0.006694% | 18274672.1397 | 100% | 18274672.1397 | 0% | 0 | 100% | 18274672.1397 | 100% | 0 | -31800
|  | Grouting | NO | 12 | 12 | 0.008368% | 22843340.1746 | 100% | 22843340.1746 | 0% | 0 | 100% | 22843340.1746 | 100% | 0 | -12
|  | Final test & Documents | % | 100 | 63 | 0.01255% | 34265010.2619 | 63% | 21586956.465 | 0% | 0 | 63% | 21586956.465 | 63% | 41 | -22
|  | 140-IM-D1 |  |  |  | 0.1514% | 413428539.9583 | 95.05% | 392963827.2304 | 0% | 0 | 95.05% | 392963827.2304 | 95.05% |  | 0
|  | Handling | Kg | 57553 | 57553 | 0.01514% | 41342853.9958 | 100% | 41342853.9958 | 0% | 0 | 100% | 41342853.9958 | 100% | 57553 | 0
|  | Chip&Padding | NO | 18 | 18 | 0.007572% | 20671426.9979 | 100% | 20671426.9979 | 0% | 0 | 100% | 20671426.9979 | 100% | 18 | 0
|  | Erection | Kg | 57553 | 57553 | 0.06058% | 165371415.9833 | 100% | 165371415.9833 | 0% | 0 | 100% | 165371415.9833 | 100% | 57553 | 0
|  | Alignment | Kg | 57553 | 57553 | 0.01817% | 49611424.795 | 100% | 49611424.795 | 0% | 0 | 100% | 49611424.795 | 100% | 57553 | 0
|  | Bolt Tightening & Test | Kg | 57553 | 57553 | 0.01212% | 33074283.1967 | 100% | 33074283.1967 | 0% | 0 | 100% | 33074283.1967 | 100% | 57533 | -20
|  | Grouting | NO | 18 | 18 | 0.01514% | 41342853.9958 | 100% | 41342853.9958 | 0% | 0 | 100% | 41342853.9958 | 100% | 18 | 0
|  | Final test & Documents | % | 100 | 67 | 0.02272% | 62014280.9937 | 67% | 41549568.2658 | 0% | 0 | 67% | 41549568.2658 | 67% | 61 | -6
|  | 140-IM-D2 |  |  |  | 0.1342% | 366463207.2346 | 95.05% | 348323278.4765 | 0% | 0 | 95.05% | 348323278.4765 | 95.05% |  | 0
|  | Handling | Kg | 51015 | 51015 | 0.01342% | 36646320.7235 | 100% | 36646320.7235 | 0% | 0 | 100% | 36646320.7235 | 100% | 50938 | -77
|  | Chip&Padding | NO | 16 | 16 | 0.006712% | 18323160.3617 | 100% | 18323160.3617 | 0% | 0 | 100% | 18323160.3617 | 100% | 16 | 0
|  | Erection | Kg | 51015 | 51015 | 0.05369% | 146585282.8938 | 100% | 146585282.8938 | 0% | 0 | 100% | 146585282.8938 | 100% | 50588 | -427
|  | Alignment | Kg | 51015 | 51015 | 0.01611% | 43975584.8682 | 100% | 43975584.8682 | 0% | 0 | 100% | 43975584.8682 | 100% | 50588 | -427
|  | Bolt Tightening & Test | Kg | 51015 | 51015 | 0.01074% | 29317056.5788 | 100% | 29317056.5788 | 0% | 0 | 100% | 29317056.5788 | 100% | 50588 | -427
|  | Grouting | NO | 16 | 16 | 0.01342% | 36646320.7235 | 100% | 36646320.7235 | 0% | 0 | 100% | 36646320.7235 | 100% | 16 | 0
|  | Final test & Documents | % | 100 | 67 | 0.02014% | 54969481.0852 | 67% | 36829552.3271 | 0% | 0 | 67% | 36829552.3271 | 67% | 62 | -5
|  | 140-IM-D3 |  |  |  | 0.178% | 486017204.2552 | 95.05% | 461959352.6446 | 0% | 0 | 95.05% | 461959352.6446 | 95.05% |  | 0
|  | Handling | Kg | 67658 | 67658 | 0.0178% | 48601720.4255 | 100% | 48601720.4255 | 0% | 0 | 100% | 48601720.4255 | 100% | 67658 | 0
|  | Chip&Padding | NO | 26 | 26 | 0.008901% | 24300860.2128 | 100% | 24300860.2128 | 0% | 0 | 100% | 24300860.2128 | 100% | 26 | 0
|  | Erection | Kg | 67658 | 67658 | 0.07121% | 194406881.7021 | 100% | 194406881.7021 | 0% | 0 | 100% | 194406881.7021 | 100% | 67658 | 0
|  | Alignment | Kg | 67658 | 67658 | 0.02136% | 58322064.5106 | 100% | 58322064.5106 | 0% | 0 | 100% | 58322064.5106 | 100% | 67658 | 0
|  | Bolt Tightening & Test | Kg | 67658 | 67658 | 0.01424% | 38881376.3404 | 100% | 38881376.3404 | 0% | 0 | 100% | 38881376.3404 | 100% | 67658 | 0
|  | Grouting | NO | 26 | 26 | 0.0178% | 48601720.4255 | 100% | 48601720.4255 | 0% | 0 | 100% | 48601720.4255 | 100% | 26 | 0
|  | Final test & Documents | % | 100 | 67 | 0.0267% | 72902580.6383 | 67% | 48844729.0276 | 0% | 0 | 67% | 48844729.0276 | 67% | 61 | -6
|  | 140-IM-D4 |  |  |  | 0.1544% | 421632028.7883 | 93.4% | 393804314.8883 | 0% | 0 | 93.4% | 393804314.8883 | 93.4% |  | 0
|  | Handling | Kg | 58695 | 58695 | 0.01544% | 42163202.8788 | 100% | 42163202.8788 | 0% | 0 | 100% | 42163202.8788 | 100% | 58695 | 0
|  | Chip&Padding | NO | 18 | 18 | 0.007722% | 21081601.4394 | 100% | 21081601.4394 | 0% | 0 | 100% | 21081601.4394 | 100% | 18 | 0
|  | Erection | Kg | 58695 | 58695 | 0.06178% | 168652811.5153 | 100% | 168652811.5153 | 0% | 0 | 100% | 168652811.5153 | 100% | 58695 | 0
|  | Alignment | Kg | 58695 | 58695 | 0.01853% | 50595843.4546 | 100% | 50595843.4546 | 0% | 0 | 100% | 50595843.4546 | 100% | 0 | -58695
|  | Bolt Tightening & Test | Kg | 58695 | 58695 | 0.01236% | 33730562.3031 | 100% | 33730562.3031 | 0% | 0 | 100% | 33730562.3031 | 100% | 0 | -58695
|  | Grouting | NO | 18 | 18 | 0.01544% | 42163202.8788 | 100% | 42163202.8788 | 0% | 0 | 100% | 42163202.8788 | 100% | 0 | -18
|  | Final test & Documents | % | 100 | 56 | 0.02317% | 63244804.3182 | 56% | 35417090.4182 | 0% | 0 | 56% | 35417090.4182 | 56% | 41 | -15
|  | 140-IM-E1 |  |  |  | 0.1329% | 362763735.4768 | 72.12% | 261630952.7781 | 0% | 0 | 72.12% | 261630952.7781 | 72.12% |  | 0
|  | Handling | Kg | 50500 | 50500 | 0.01329% | 36276373.5477 | 100% | 36276373.5477 | 0% | 0 | 100% | 36276373.5477 | 100% | 50500 | 0
|  | Chip&Padding | NO | 20 | 20 | 0.006644% | 18138186.7738 | 100% | 18138186.7738 | 0% | 0 | 100% | 18138186.7738 | 100% | 20 | 0
|  | Erection | Kg | 50500 | 40451 | 0.05315% | 145105494.1907 | 80.1% | 116230937.5348 | 0% | 0 | 80.1% | 116230937.5348 | 80.1% | 35264 | -5187
|  | Alignment | Kg | 50500 | 30000 | 0.01595% | 43531648.2572 | 59.41% | 25860385.1033 | 0% | 0 | 59.41% | 25860385.1033 | 59.41% | 0 | -30000
|  | Bolt Tightening & Test | Kg | 50500 | 30000 | 0.01063% | 29021098.8381 | 59.41% | 17240256.7355 | 0% | 0 | 59.41% | 17240256.7355 | 59.41% | 0 | -30000
|  | Grouting | NO | 20 | 12 | 0.01329% | 36276373.5477 | 60% | 21765824.1286 | 0% | 0 | 60% | 21765824.1286 | 60% | 0 | -12
|  | Final test & Documents | % | 100 | 48 | 0.01993% | 54414560.3215 | 48% | 26118988.9543 | 0% | 0 | 48% | 26118988.9543 | 48% | 40 | -8
|  | 140-IM-E2 |  |  |  | 0.1702% | 464617735.5822 | 95.05% | 441619157.6709 | 0% | 0 | 95.05% | 441619157.6709 | 95.05% |  | 0
|  | Handling | Kg | 64679 | 64679 | 0.01702% | 46461773.5582 | 100% | 46461773.5582 | 0% | 0 | 100% | 46461773.5582 | 100% | 64431 | -248
|  | Chip&Padding | NO | 26 | 26 | 0.008509% | 23230886.7791 | 100% | 23230886.7791 | 0% | 0 | 100% | 23230886.7791 | 100% | 26 | 0
|  | Erection | Kg | 64679 | 64679 | 0.06808% | 185847094.2329 | 100% | 185847094.2329 | 0% | 0 | 100% | 185847094.2329 | 100% | 63845 | -834
|  | Alignment | Kg | 64679 | 64679 | 0.02042% | 55754128.2699 | 100% | 55754128.2699 | 0% | 0 | 100% | 55754128.2699 | 100% | 63845 | -834
|  | Bolt Tightening & Test | Kg | 64679 | 64679 | 0.01362% | 37169418.8466 | 100% | 37169418.8466 | 0% | 0 | 100% | 37169418.8466 | 100% | 63845 | -834
|  | Grouting | NO | 26 | 26 | 0.01702% | 46461773.5582 | 100% | 46461773.5582 | 0% | 0 | 100% | 46461773.5582 | 100% | 26 | 0
|  | Final test & Documents | % | 100 | 67 | 0.02553% | 69692660.3373 | 67% | 46694082.426 | 0% | 0 | 67% | 46694082.426 | 67% | 62 | -5
|  | 140-IM-E3 |  |  |  | 0.1053% | 287337612.2588 | 79.18% | 227521104.8269 | 0% | 0 | 79.18% | 227521104.8269 | 79.18% |  | 0
|  | Handling | Kg | 40000 | 40000 | 0.01053% | 28733761.2259 | 100% | 28733761.2259 | 0% | 0 | 100% | 28733761.2259 | 100% | 38834 | -1166 | 75.87% | 50.83%
|  | Chip&Padding | NO | 16 | 16 | 0.005263% | 14366880.6129 | 100% | 14366880.6129 | 0% | 0 | 100% | 14366880.6129 | 100% | 16 | 0 | 82.85% | 55.51%
|  | Erection | Kg | 40000 | 39525 | 0.0421% | 114935044.9035 | 98.81% | 113570191.2453 | 0% | 0 | 98.81% | 113570191.2453 | 98.81% | 37088 | -2437 | 87.36% | 58.53%
|  | Alignment | Kg | 40000 | 39525 | 0.01263% | 34480513.4711 | 98.81% | 34071057.3736 | 0% | 0 | 98.81% | 34071057.3736 | 98.81% | 37088 | -2437 | 83.84% | 56.17%
|  | Bolt Tightening & Test | Kg | 40000 | 25000 | 0.00842% | 22987008.9807 | 62.5% | 14366880.6129 | 0% | 0 | 62.5% | 14366880.6129 | 62.5% | 37088 | 12088 | 82.2% | 55.07%
|  | Grouting | NO | 16 | 0 | 0.01053% | 28733761.2259 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 10.5% | 7.035%
|  | Final test & Documents | % | 100 | 52 | 0.01579% | 43100641.8388 | 52% | 22412333.7562 | 0% | 0 | 52% | 22412333.7562 | 52% | 52 | 0 | 95.05% | 63.68%
|  | 140-IM-E4 |  |  |  | 0.03736% | 102004852.3519 | 83.03% | 84691755.5316 | 0% | 0 | 83.03% | 84691755.5316 | 83.03% |  | 0 | 95% | 63.65%
|  | Handling | Kg | 14200 | 14165 | 0.003736% | 10200485.2352 | 99.75% | 10175343.1941 | 0% | 0 | 99.75% | 10175343.1941 | 99.75% | 14200 | 35 | 95% | 63.65%
|  | Chip&Padding | NO | 6 | 6 | 0.001868% | 5100242.6176 | 100% | 5100242.6176 | 0% | 0 | 100% | 5100242.6176 | 100% | 6 | 0 | 95% | 63.65%
|  | Erection | Kg | 14200 | 14200.4 | 0.01495% | 40801940.9408 | 100% | 40803090.2912 | 0% | 0 | 100% | 40803090.2912 | 100% | 14200 | -0.4 | 95% | 63.65%
|  | Alignment | Kg | 14200 | 14165 | 0.004484% | 12240582.2822 | 99.75% | 12210411.8329 | 0% | 0 | 99.75% | 12210411.8329 | 99.75% | 14200 | 35 | 95% | 63.65%
|  | Bolt Tightening & Test | Kg | 14200 | 14165 | 0.002989% | 8160388.1882 | 99.75% | 8140274.5553 | 0% | 0 | 99.75% | 8140274.5553 | 99.75% | 14200 | 35 | 14% | 9.38%
|  | Grouting | NO | 6 | 0 | 0.003736% | 10200485.2352 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 11% | 7.37%
|  | Final test & Documents | % | 100 | 54 | 0.005605% | 15300727.8528 | 54% | 8262393.0405 | 0% | 0 | 54% | 8262393.0405 | 54% | 54 | 0 | 11% | 7.37%
|  | 140-IM-F1 |  |  |  | 0.0942% | 257167162.9717 | 62.2% | 159958550.0436 | 0% | 0 | 62.2% | 159958550.0436 | 62.2% |  | 0 | 95% | 63.65%
|  | Handling | Kg | 35800 | 35800 | 0.00942% | 25716716.2972 | 100% | 25716716.2972 | 0% | 0 | 100% | 25716716.2972 | 100% | 35800 | 0 | 95% | 63.65%
|  | Chip&Padding | NO | 20 | 20 | 0.00471% | 12858358.1486 | 100% | 12858358.1486 | 0% | 0 | 100% | 12858358.1486 | 100% | 20 | 0 | 95% | 63.65%
|  | Erection | Kg | 35800 | 35800.2 | 0.03768% | 102866865.1887 | 100% | 102867439.8639 | 0% | 0 | 100% | 102867439.8639 | 100% | 34945 | -855.2 | 95% | 63.65%
|  | Alignment | Kg | 35800 | 0 | 0.0113% | 30860059.5566 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 95% | 63.65%
|  | Bolt Tightening & Test | Kg | 35800 | 0 | 0.007536% | 20573373.0377 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 95% | 63.65%
|  | Grouting | NO | 20 | 0 | 0.00942% | 25716716.2972 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0 | 95% | 63.65%
|  | Final test & Documents | % | 100 | 48 | 0.01413% | 38575074.4457 | 48% | 18516035.734 | 0% | 0 | 48% | 18516035.734 | 48% | 48 | 0 | 79% | 52.93%
|  | 140-IM-F2 |  |  |  | 0.1429% | 390060808.6414 | 95.05% | 370752798.6136 | 0% | 0 | 95.05% | 370752798.6136 | 95.05% |  | 0 | 95% | 63.65%
|  | Handling | Kg | 54300 | 54300 | 0.01429% | 39006080.8641 | 100% | 39006080.8641 | 0% | 0 | 100% | 39006080.8641 | 100% | 54300 | 0 | 68% | 45.56%
|  | Chip&Padding | NO | 22 | 22 | 0.007144% | 19503040.4321 | 100% | 19503040.4321 | 0% | 0 | 100% | 19503040.4321 | 100% | 22 | 0 | 50% | 33.5%
|  | Erection | Kg | 54300 | 54300 | 0.05715% | 156024323.4565 | 100% | 156024323.4565 | 0% | 0 | 100% | 156024323.4565 | 100% | 54300 | 0 | 93% | 62.31%
|  | Alignment | Kg | 54300 | 54300 | 0.01715% | 46807297.037 | 100% | 46807297.037 | 0% | 0 | 100% | 46807297.037 | 100% | 0 | -54300 | 95% | 63.65%
|  | Bolt Tightening & Test | Kg | 54300 | 54300 | 0.01143% | 31204864.6913 | 100% | 31204864.6913 | 0% | 0 | 100% | 31204864.6913 | 100% | 0 | -54300 | 95% | 63.65%
|  | Grouting | NO | 22 | 22 | 0.01429% | 39006080.8641 | 100% | 39006080.8641 | 0% | 0 | 100% | 39006080.8641 | 100% | 0 | -22 | 95% | 63.65%
|  | Final test & Documents | % | 100 | 67 | 0.02143% | 58509121.2962 | 67% | 39201111.2685 | 0% | 0 | 67% | 39201111.2685 | 67% | 55 | -12 | 95% | 63.65%
|  | Fireproofing |  |  |  | 0.06706% | 183067317.805 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0 | 95% | 63.65%
|  | Fireproofing | m2 | 200 | 0 | 0.06706% | 183067317.805 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0 | 94% | 62.98%
|  | Insulation |  |  |  | 0.212% | 578848995.2813 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0 | 82% | 54.94%
|  | Cold Insulation | m2 | 1 | 0 | 0.106% | 289424497.6406 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0 | 95% | 63.65%
|  | Hot Insulation | m2 | 1 | 0 | 0.106% | 289424497.6406 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0 | 80% | 53.6%
|  | Equipment Packages |  |  |  | 5.941% | 16218830438.2731 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0 | 83% | 55.61%
|  | Static Equipment |  |  |  | 3.268% | 8921681095.6512 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0 | 83% | 55.61%
|  | HP FLARE 140-X-101 |  |  |  | 0.7275% | 1986140653.5802 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0 | 95% | 63.65%
|  | Material Handling | Kg | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.2546% | 695149228.7531 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.1091% | 297921098.037 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.1091% | 297921098.037 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.1455% | 397228130.716 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP FLARE 140-X-201 |  |  |  | 0.7275% | 1986140653.5802 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.2546% | 695149228.7531 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.1091% | 297921098.037 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.1091% | 297921098.037 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.1455% | 397228130.716 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LP FLARE 140-X-102 |  |  |  | 0.08424% | 229974180.9409 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.004212% | 11498709.047 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.004212% | 11498709.047 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.02948% | 80490963.3293 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.01264% | 34496127.1411 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.01264% | 34496127.1411 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.01685% | 45994836.1882 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.004212% | 11498709.047 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LP FLARE 140-X-202 |  |  |  | 0.08424% | 229974180.9409 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.004212% | 11498709.047 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.004212% | 11498709.047 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.02948% | 80490963.3293 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.01264% | 34496127.1411 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.01264% | 34496127.1411 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.01685% | 45994836.1882 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.004212% | 11498709.047 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | MP FLARE 140-X-103 |  |  |  | 0.7275% | 1986140653.5802 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.2546% | 695149228.7531 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.1091% | 297921098.037 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.1091% | 297921098.037 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.1455% | 397228130.716 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | MP FLARE 140-X-203 |  |  |  | 0.7275% | 1986140653.5802 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.2546% | 695149228.7531 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.1091% | 297921098.037 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.1091% | 297921098.037 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.1455% | 397228130.716 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.03638% | 99307032.679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-101 |  |  |  | 0.0009343% | 2550622.7341 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.000327% | 892717.9569 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.0001401% | 382593.4101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.0001401% | 382593.4101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.0001869% | 510124.5468 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-103 |  |  |  | 0.0009343% | 2550622.7341 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.000327% | 892717.9569 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.0001401% | 382593.4101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.0001401% | 382593.4101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.0001869% | 510124.5468 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Cold Flare K.O. Drum Heater 140-DH-104 |  |  |  | 0.0009534% | 2602889.5934 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 4.767e-05% | 130144.4797 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 4.767e-05% | 130144.4797 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.0003337% | 911011.3577 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.000143% | 390433.439 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.000143% | 390433.439 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.0001907% | 520577.9187 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 4.767e-05% | 130144.4797 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Wet Flare K.O. Drum Heater 140-DH-201 |  |  |  | 0.0009343% | 2550622.7341 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.000327% | 892717.9569 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.0001401% | 382593.4101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.0001401% | 382593.4101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.0001869% | 510124.5468 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | MP Flare K.O. Drum Heater 140-DH-203 |  |  |  | 0.0009343% | 2550622.7341 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.000327% | 892717.9569 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.0001401% | 382593.4101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.0001401% | 382593.4101 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.0001869% | 510124.5468 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 4.671e-05% | 127531.1367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Cold Flare K.O. Drum Heater 140-DH-204 |  |  |  | 0.0009534% | 2602889.5934 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 4.767e-05% | 130144.4797 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 4.767e-05% | 130144.4797 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.0003337% | 911011.3577 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.000143% | 390433.439 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.000143% | 390433.439 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.0001907% | 520577.9187 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 4.767e-05% | 130144.4797 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-105 |  |  |  | 0.04595% | 125440462.3314 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.01608% | 43904161.816 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.006892% | 18816069.3497 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.006892% | 18816069.3497 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.00919% | 25088092.4663 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-106 |  |  |  | 0.04595% | 125440462.3314 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.01608% | 43904161.816 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.006892% | 18816069.3497 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.006892% | 18816069.3497 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.00919% | 25088092.4663 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-205 |  |  |  | 0.04595% | 125440462.3314 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.01608% | 43904161.816 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.006892% | 18816069.3497 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.006892% | 18816069.3497 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.00919% | 25088092.4663 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP Flare Stack K.O. Drum Heater 140-DH-206 |  |  |  | 0.04595% | 125440462.3314 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.01608% | 43904161.816 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.006892% | 18816069.3497 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.006892% | 18816069.3497 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.00919% | 25088092.4663 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.002297% | 6272023.1166 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Rotary Equipment |  |  |  | 2.673% | 7297149342.6219 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-104A |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-104B |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LP FLARE STACKS PUMPS, 140-P-105A |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LP FLARE STACKS PUMPS, 140-P-105B |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | MP FLARE STACKS PUMPS, 140-P-106A |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | MP FLARE STACKS PUMPS, 140-P-106B |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-204A |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HP FLARE STACKS PUMPS, 140-P-204B |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LP FLARE STACKS PUMPS, 140-P-205A |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LP FLARE STACKS PUMPS, 140-P-205B |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | MP FLARE STACKS PUMPS, 140-P-206A |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | MP FLARE STACKS PUMPS, 140-P-206B |  |  |  | 0.2227% | 608095778.5518 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling | Kg | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation | Kg | 1 | 0 | 0.07796% | 212833522.4931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment | Kg | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting | % | 1 | 0 | 0.03341% | 91214366.7828 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation | Kg | 1 | 0 | 0.04455% | 121619155.7104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection | % | 1 | 0 | 0.01114% | 30404788.9276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Unit 143 |  |  |  | 15.14% | 41341563063.6 | 8.298% | 2460970448.6631 | -0.0005898% | 969350734.4455 | 8.298% | 3430321183.1086 | 8.298% |  | 0
|  | Welding & NDT Procedures |  |  |  | 1.15% | 3139525627.6862 | 45.2% | 665579433.0695 | 0% | 753486150.6447 | 45.2% | 1419065583.7142 | 45.2% |  | 0
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100 | 100 | 0.00575% | 15697628.1384 | 100% | 15697628.1384 | 0% | 0 | 100% | 15697628.1384 | 100% | 100 | 0
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100 | 100 | 0.00575% | 15697628.1384 | 100% | 15697628.1384 | 0% | 0 | 100% | 15697628.1384 | 100% | 100 | 0
|  | Qualification of Welding Equipments | % | 100 | 100 | 0.00575% | 15697628.1384 | 100% | 15697628.1384 | 0% | 0 | 100% | 15697628.1384 | 100% | 100 | 0
|  | Maintaining Welder Qualification Records | % | 100 | 100 | 0.00575% | 15697628.1384 | 100% | 15697628.1384 | 0% | 0 | 100% | 15697628.1384 | 100% | 100 | 0
|  | Monitoring Welder Performance | % | 100 | 100 | 0.00575% | 15697628.1384 | 100% | 15697628.1384 | 0% | 0 | 100% | 15697628.1384 | 100% | 100 | 0
|  | Prepare NDT Procedures & Obtain Certification | % | 100 | 20 | 0.345% | 941857688.3059 | 100% | 188371537.6612 | 0% | 753486150.6447 | 100% | 941857688.3059 | 100% |  | -20
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100 | 20 | 0.00575% | 15697628.1384 | 20% | 3139525.6277 | 0% | 0 | 20% | 3139525.6277 | 20% |  | -20
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100 | 20 | 0.00575% | 15697628.1384 | 20% | 3139525.6277 | 0% | 0 | 20% | 3139525.6277 | 20% |  | -20
|  | Perform NDT as per the Procedures | % | 100 | 20 | 0.092% | 251162050.2149 | 20% | 50232410.043 | 0% | 0 | 20% | 50232410.043 | 20% |  | -20
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100 | 100 | 0.092% | 251162050.2149 | 100% | 251162050.2149 | 0% | 0 | 100% | 251162050.2149 | 100% | 100 | 0
|  | Prepare PWHT Procedures & Obtain Certification | % | 100 | 0 | 0.2875% | 784881406.9215 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Perform PWHT Testing | % | 100 | 0 | 0.1495% | 408138331.5992 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 0.138% | 376743075.3223 | 20% | 75348615.0645 | 0% | 0 | 20% | 75348615.0645 | 20% |  | -20
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100 | 0.00575% | 15697628.1384 | 100% | 15697628.1384 | 0% | 0 | 100% | 15697628.1384 | 100% | 100 | 0
|  | Piping |  |  |  | 8.885% | 24255844700.7655 | 6.369% | 1328728319.4555 | -0.001005% | 215864583.8008 | 6.368% | 1544592903.2563 | 6.369% |  | 0
|  | AG Piping |  |  |  | 8.794% | 24007989542.6608 | 6.435% | 1328728319.4555 | -0.001016% | 215864583.8008 | 6.434% | 1544592903.2563 | 6.435% |  | 0
|  | Shop |  |  |  | 3.078% | 8402908177.3817 | 10.43% | 708276870.9967 | 0% | 168451164.8049 | 10.43% | 876728035.8015 | 10.43% |  | 0
|  | Carbon Steel |  |  |  | 2.083% | 5685553544.743 | 13.63% | 606376072.2727 | 0% | 168451164.8049 | 13.63% | 774827237.0776 | 13.63% |  | 0
|  | Material Handling From Lay down To Shop | ID | 33738 | 5220 | 0.1041% | 284277677.2372 | 24.24% | 43983919.4729 | 0% | 24924989.4893 | 24.24% | 68908908.9623 | 24.24% | 2000 | -3220
|  | Cutting & Bevelling & Fit Up | ID | 11808 | 1172 | 0.7289% | 1989943740.6601 | 12.94% | 197511353.6631 | 0% | 59987366.3783 | 12.94% | 257498720.0414 | 12.94% |  | -1172
|  | Welding | ID | 11808 | 900 | 0.7289% | 1989943740.6601 | 11.82% | 151672541.2088 | 0% | 83538808.9372 | 11.82% | 235211350.146 | 11.82% |  | -900
|  | NDT | ID | 11808 | 0 | 0.1041% | 284277677.2372 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 11808 | 0 | 0.1041% | 284277677.2372 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 0.3124% | 852833031.7115 | 25% | 213208257.9279 | 0% | 0 | 25% | 213208257.9279 | 25% | 25 | 0
|  | Low Temperature CS |  |  |  | 0.3407% | 930220028.2164 | 3.75% | 34883251.0581 | 0% | 0 | 3.75% | 34883251.0581 | 3.75% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.01704% | 46511001.4108 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 0.1193% | 325577009.8757 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.1193% | 325577009.8757 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.01704% | 46511001.4108 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.01704% | 46511001.4108 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 0.05111% | 139533004.2325 | 25% | 34883251.0581 | 0% | 0 | 25% | 34883251.0581 | 25% | 25 | 0
|  | Stainless Steel |  |  |  | 0.0001235% | 337036.0158 | 3.75% | 12638.8506 | 0% | 0 | 3.75% | 12638.8506 | 3.75% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 6.173e-06% | 16851.8008 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 4.321e-05% | 117962.6055 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 4.321e-05% | 117962.6055 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 6.173e-06% | 16851.8008 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 6.173e-06% | 16851.8008 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 1.852e-05% | 50555.4024 | 25% | 12638.8506 | 0% | 0 | 25% | 12638.8506 | 25% | 25 | 0
|  | Galva |  |  |  | 0.1825% | 498139662.717 | 3.75% | 18680237.3519 | 0% | 0 | 3.75% | 18680237.3519 | 3.75% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.009123% | 24906983.1359 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 0.06386% | 174348881.951 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.06386% | 174348881.951 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.009123% | 24906983.1359 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.009123% | 24906983.1359 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 0.02737% | 74720949.4076 | 25% | 18680237.3519 | 0% | 0 | 25% | 18680237.3519 | 25% | 25 | 0
|  | CU-NI |  |  |  | 0.472% | 1288657905.6894 | 3.75% | 48324671.4634 | 0% | 0 | 3.75% | 48324671.4634 | 3.75% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.0236% | 64432895.2845 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 0.1652% | 451030266.9913 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.1652% | 451030266.9913 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.0236% | 64432895.2845 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.0236% | 64432895.2845 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 0.07081% | 193298685.8534 | 25% | 48324671.4634 | 0% | 0 | 25% | 48324671.4634 | 25% | 25 | 0
|  | Field |  |  |  | 5.716% | 15605081365.2791 | 4.281% | 620451448.4588 | -0.001563% | 47413418.9959 | 4.28% | 667864867.4548 | 4.281% |  | 0
|  | Carbon Steel |  |  |  | 3.868% | 10558567291.634 | 5.133% | 494288596.6177 | -0.00231% | 47413418.9959 | 5.13% | 541702015.6136 | 5.133% |  | 0
|  | Material Handling From Shop To Field | ID | 33738 | 1488 | 0.1934% | 527928364.5817 | 5.89% | 23284053.782 | 0% | 7810926.8918 | 5.89% | 31094980.6739 | 5.89% | 1072 | -416
|  | Scaffolding | M2 | 1 | 0 | 0.5028% | 1372613747.9124 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 21930 | 966 | 0.7348% | 2006127785.4105 | 6.06% | 88368419.5489 | 0% | 33202924.247 | 6.06% | 121571343.7959 | 6.06% | 756 | -210
|  | Valve Installation | ID | 1 | 0 | 0.1934% | 527928364.5817 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 21930 | 706 | 1.276% | 3484327206.2392 | 3.41% | 112172138.9697 | 0% | 6643418.7631 | 3.41% | 118815557.7328 | 3.41% | 756 | 50
|  | NDT | ID | 21930 | 540 | 0.09669% | 263964182.2908 | 2.462% | 6499802.0263 | -0.09238% | -243850.906 | 2.37% | 6255951.1203 | 2.462% |  | -540
|  | PWHT | ID | 21930 | 0 | 0.116% | 316757018.749 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 21930 | 0 | 0.3674% | 1003063892.7052 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 0.3868% | 1055856729.1634 | 25% | 263964182.2908 | 0% | 0 | 25% | 263964182.2908 | 25% | 25 | 0
|  | Low Temperature CS |  |  |  | 0.6328% | 1727550993.0259 | 2.5% | 43188774.8256 | 0% | 0 | 2.5% | 43188774.8256 | 2.5% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.03164% | 86377549.6513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | M2 | 1 | 0 | 0.08226% | 224581629.0934 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 1 | 0 | 0.1202% | 328234688.6749 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.03164% | 86377549.6513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.2088% | 570091827.6985 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.01582% | 43188774.8256 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.01898% | 51826529.7908 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.06012% | 164117344.3375 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 0.06328% | 172755099.3026 | 25% | 43188774.8256 | 0% | 0 | 25% | 43188774.8256 | 25% | 25 | 0
|  | Stainless Steel |  |  |  | 0.0002293% | 625924.3082 | 2.5% | 15648.1077 | 0% | 0 | 2.5% | 15648.1077 | 2.5% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 1.146e-05% | 31296.2154 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | M2 | 1 | 0 | 2.981e-05% | 81370.1601 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 1 | 0 | 4.356e-05% | 118925.6186 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 1.146e-05% | 31296.2154 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 7.566e-05% | 206555.0217 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 5.732e-06% | 15648.1077 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 6.878e-06% | 18777.7292 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 2.178e-05% | 59462.8093 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 2.293e-05% | 62592.4308 | 25% | 15648.1077 | 0% | 0 | 25% | 15648.1077 | 25% | 25 | 0
|  | Galva |  |  |  | 0.3389% | 925116098.2338 | 2.5% | 23127902.4558 | 0% | 0 | 2.5% | 23127902.4558 | 2.5% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.01694% | 46255804.9117 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | M2 | 1 | 0 | 0.04405% | 120265092.7704 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 1 | 0 | 0.06439% | 175772058.6644 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.01694% | 46255804.9117 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.1118% | 305288312.4172 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.008472% | 23127902.4558 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.01017% | 27753482.947 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.03219% | 87886029.3322 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 0.03389% | 92511609.8234 | 25% | 23127902.4558 | 0% | 0 | 25% | 23127902.4558 | 25% | 25 | 0
|  | CU-NI |  |  |  | 0.8766% | 2393221058.0772 | 2.5% | 59830526.4519 | 0% | 0 | 2.5% | 59830526.4519 | 2.5% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.04383% | 119661052.9039 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | M2 | 1 | 0 | 0.114% | 311118737.55 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 1 | 0 | 0.1666% | 454712001.0347 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.04383% | 119661052.9039 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.2893% | 789762949.1655 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.02192% | 59830526.4519 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.0263% | 71796631.7423 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.08328% | 227356000.5173 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 25 | 0.08766% | 239322105.8077 | 25% | 59830526.4519 | 0% | 0 | 25% | 59830526.4519 | 25% | 25 | 0
|  | Pipe Support |  |  |  | 0.09079% | 247855158.1047 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Shop |  |  |  | 0.03178% | 86749305.3367 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Handling | Kg | 1 | 0 | 0.003495% | 9542423.587 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | shop drawing | Kg | 1 | 0 | 0.005084% | 13879888.8539 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & assembling | Kg | 1 | 0 | 0.006991% | 19084847.1741 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | Kg | 1 | 0 | 0.01462% | 39904680.4549 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.001589% | 4337465.2668 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Field |  |  |  | 0.05901% | 161105852.7681 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling From Shop To Field | Kg | 1 | 0 | 0.006491% | 17721643.8045 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection | Kg | 1 | 0 | 0.01239% | 33832229.0813 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | Kg | 1 | 0 | 0.03069% | 83775043.4394 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | Kg | 1 | 0 | 0.006491% | 17721643.8045 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.002951% | 8055292.6384 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Painting & Sandblasting |  |  |  | 1.164% | 3177098841.37 | 14.69% | 466662696.1381 | 0% | 0 | 14.69% | 466662696.1381 | 14.69% |  | 0
|  | Pipe |  |  |  | 1.152% | 3144634074.8217 | 14.84% | 466662696.1381 | 0% | 0 | 14.84% | 466662696.1381 | 14.84% |  | 0
|  | Sand Blast | m2 | 11000 | 4663.99 | 0.1728% | 471695111.2232 | 42.4% | 199998298.3449 | 0% | 0 | 42.4% | 199998298.3449 | 42.4% | 3480 | -1183.99
|  | Primer | m2 | 11000 | 4663.99 | 0.2304% | 628926814.9643 | 42.4% | 266664397.7932 | 0% | 0 | 42.4% | 266664397.7932 | 42.4% | 3480 | -1183.99
|  | Middle Paint | m2 | 11000 | 0 | 0.4032% | 1100621926.1876 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Paint | m2 | 11000 | 0 | 0.2304% | 628926814.9643 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Touch Up & Punch | m2 | 11000 | 0 | 0.05759% | 157231703.7411 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.05759% | 157231703.7411 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Support |  |  |  | 0.01189% | 32464766.5483 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Sand Blast | m2 | 1 | 0 | 0.001784% | 4869714.9822 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Primer | m2 | 1 | 0 | 0.002378% | 6492953.3097 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Middle Paint | m2 | 1 | 0 | 0.004162% | 11362668.2919 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Paint | m2 | 1 | 0 | 0.002378% | 6492953.3097 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Touch Up & Punch | m2 | 1 | 0 | 0.0005946% | 1623238.3274 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 1 | 0 | 0.0005946% | 1623238.3274 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Insulation |  |  |  | 0.09649% | 263428103.83 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cold Insulation | M2 | 1 | 0 | 0.04825% | 131714051.915 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hot Insulation | M2 | 1 | 0 | 0.04825% | 131714051.915 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Equipment Packages |  |  |  | 3.848% | 10505665789.9483 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Static Equipment |  |  |  | 0.2516% | 686784589.7888 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Sump Drum 143-D-101 |  |  |  | 0.1962% | 535524143.1012 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.009808% | 26776207.1551 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.009808% | 26776207.1551 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.06866% | 187433450.0854 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.02942% | 80328621.4652 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.02942% | 80328621.4652 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.03923% | 107104828.6202 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.009808% | 26776207.1551 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Degassing Boot 143-D-102 |  |  |  | 0.05541% | 151260446.6875 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.00277% | 7563022.3344 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.00277% | 7563022.3344 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.01939% | 52941156.3406 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.008311% | 22689067.0031 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.008311% | 22689067.0031 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.01108% | 30252089.3375 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.00277% | 7563022.3344 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Rotary Equipment |  |  |  | 3.597% | 9818881200.1595 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 143-P-101 |  |  |  | 0.5136% | 1402226422.1186 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.02568% | 70111321.1059 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.02568% | 70111321.1059 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.1798% | 490779247.7415 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.07705% | 210333963.3178 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.07705% | 210333963.3178 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.1027% | 280445284.4237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.02568% | 70111321.1059 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 143-P-102 |  |  |  | 0.9399% | 2566053397.8266 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.047% | 128302669.8913 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.047% | 128302669.8913 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.329% | 898118689.2393 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.141% | 384908009.674 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.141% | 384908009.674 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.188% | 513210679.5653 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.047% | 128302669.8913 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 143-P-103 A |  |  |  | 0.6093% | 1663492615.214 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.2133% | 582222415.3249 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.0914% | 249523892.2821 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.0914% | 249523892.2821 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.1219% | 332698523.0428 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 143-P-103 B |  |  |  | 0.6093% | 1663492615.214 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.2133% | 582222415.3249 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.0914% | 249523892.2821 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.0914% | 249523892.2821 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.1219% | 332698523.0428 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 143-P-103 C |  |  |  | 0.6093% | 1663492615.214 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.2133% | 582222415.3249 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.0914% | 249523892.2821 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.0914% | 249523892.2821 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.1219% | 332698523.0428 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.03047% | 83174630.7607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 143-P-104 |  |  |  | 0.3151% | 860123534.5724 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.01575% | 43006176.7286 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.01575% | 43006176.7286 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.1103% | 301043237.1003 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.04726% | 129018530.1859 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.04726% | 129018530.1859 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.06301% | 172024706.9145 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.01575% | 43006176.7286 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Unit 147/148 |  |  |  | 21.87% | 59717020241.5502 | 5.205% | 2200221689.6717 | 0.06969% | 949775143.7353 | 5.275% | 3149996833.407 | 5.205% |  | 0
|  | Welding & NDT Procedures |  |  |  | 1.323% | 3611775149.1724 | 45.2% | 765696343.5704 | 0% | 866826035.8014 | 45.2% | 1632522379.3718 | 45.2% |  | 0
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % | 100 | 100 | 0.006615% | 18058875.7459 | 100% | 18058875.7459 | 0% | 0 | 100% | 18058875.7459 | 100% | 100 | 0
|  | Qualification of Welders including Lab Testing For Structural & Piping | % | 100 | 100 | 0.006615% | 18058875.7459 | 100% | 18058875.7459 | 0% | 0 | 100% | 18058875.7459 | 100% | 100 | 0
|  | Qualification of Welding Equipments | % | 100 | 100 | 0.006615% | 18058875.7459 | 100% | 18058875.7459 | 0% | 0 | 100% | 18058875.7459 | 100% | 100 | 0
|  | Maintaining Welder Qualification Records | % | 100 | 100 | 0.006615% | 18058875.7459 | 100% | 18058875.7459 | 0% | 0 | 100% | 18058875.7459 | 100% | 100 | 0
|  | Monitoring Welder Performance | % | 100 | 100 | 0.006615% | 18058875.7459 | 100% | 18058875.7459 | 0% | 0 | 100% | 18058875.7459 | 100% | 100 | 0
|  | Prepare NDT Procedures & Obtain Certification | % | 100 | 20 | 0.3969% | 1083532544.7517 | 100% | 216706508.9503 | 0% | 866826035.8014 | 100% | 1083532544.7517 | 100% |  | -20
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % | 100 | 20 | 0.006615% | 18058875.7459 | 20% | 3611775.1492 | 0% | 0 | 20% | 3611775.1492 | 20% |  | -20
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % | 100 | 20 | 0.006615% | 18058875.7459 | 20% | 3611775.1492 | 0% | 0 | 20% | 3611775.1492 | 20% |  | -20
|  | Perform NDT as per the Procedures | % | 100 | 20 | 0.1058% | 288942011.9338 | 20% | 57788402.3868 | 0% | 0 | 20% | 57788402.3868 | 20% |  | -20
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % | 100 | 100 | 0.1058% | 288942011.9338 | 100% | 288942011.9338 | 0% | 0 | 100% | 288942011.9338 | 100% | 100 | 0
|  | Prepare PWHT Procedures & Obtain Certification | % | 100 | 0 | 0.3307% | 902943787.2931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Perform PWHT Testing | % | 100 | 0 | 0.172% | 469530769.3924 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Provide and maintain secure storage for radioactive sources | % | 100 | 20 | 0.1588% | 433413017.9007 | 20% | 86682603.5801 | 0% | 0 | 20% | 86682603.5801 | 20% |  | -20
|  | Implement specific safety procedures relating to radioactive sources | % | 100 | 100.0001 | 0.006615% | 18058875.7459 | 100% | 18058887.6918 | 0% | 0 | 100% | 18058887.6918 | 100% | 100 | -6.615e-05
|  | Piping |  |  |  | 10.22% | 27904424904.1455 | 4.891% | 1323433645.6412 | 0.1491% | 82949107.9339 | 5.04% | 1406382753.5751 | 4.891% |  | 0
|  | AG Piping |  |  |  | 10.12% | 27619287209.2204 | 4.941% | 1323433645.6412 | 0.1507% | 82949107.9339 | 5.092% | 1406382753.5751 | 4.941% |  | 0
|  | Shop |  |  |  | 3.541% | 9666845143.5505 | 6.69% | 605335963.0144 | 0.4305% | 82949107.9339 | 7.12% | 688285070.9483 | 6.69% |  | 0
|  | Carbon Steel |  |  |  | 0.3889% | 1061617436.3693 | 12.28% | 89022300.5835 | 3.92% | 82949107.9339 | 16.2% | 171971408.5175 | 12.28% |  | 0
|  | Material Handling From Lay down To Shop | ID | 6223 | 1369 | 0.01944% | 53080871.8185 | 23.03% | 11677280.0128 | 0% | 547244.767 | 23.03% | 12224524.7798 | 23.03% | 600 | -769
|  | Cutting & Bevelling & Fit Up | ID | 2178 | 80 | 0.1361% | 371566102.7293 | 14.65% | 13647974.3886 | 0% | 40786459.6613 | 14.65% | 54434434.0498 | 14.65% |  | -80
|  | Welding | ID | 2178 | 0 | 0.1361% | 371566102.7293 | 0% | 0 | 11.2% | 41615403.5057 | 11.2% | 41615403.5057 | 0% |  | 0
|  | NDT | ID | 2178 | 0 | 0.01944% | 53080871.8185 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 2178 | 0 | 0.01944% | 53080871.8185 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.05833% | 159242615.4554 | 40% | 63697046.1822 | 0% | 0 | 40% | 63697046.1822 | 40% | 40 | 0
|  | Low Temperature CS |  |  |  | 2.875% | 7849078235.7091 | 6% | 470944694.1425 | 0% | 0 | 6% | 470944694.1425 | 6% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.1438% | 392453911.7855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 1.006% | 2747177382.4982 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 1.006% | 2747177382.4982 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.1438% | 392453911.7855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.1438% | 392453911.7855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.4313% | 1177361735.3564 | 40% | 470944694.1425 | 0% | 0 | 40% | 470944694.1425 | 40% | 40 | 0
|  | Galva |  |  |  | 0.04255% | 116160078.9811 | 6% | 6969604.7389 | 0% | 0 | 6% | 6969604.7389 | 6% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.002127% | 5808003.9491 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 0.01489% | 40656027.6434 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.01489% | 40656027.6434 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.002127% | 5808003.9491 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.002127% | 5808003.9491 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.006382% | 17424011.8472 | 40% | 6969604.7389 | 0% | 0 | 40% | 6969604.7389 | 40% | 40 | 0
|  | Copper Alloys |  |  |  | 0.2344% | 639989392.491 | 6% | 38399363.5495 | 0% | 0 | 6% | 38399363.5495 | 6% |  | 0
|  | Material Handling From Lay down To Shop | ID | 1 | 0 | 0.01172% | 31999469.6245 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & Bevelling & Fit Up | ID | 1 | 0 | 0.08205% | 223996287.3718 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.08205% | 223996287.3718 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.01172% | 31999469.6245 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.01172% | 31999469.6245 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.03516% | 95998408.8736 | 40% | 38399363.5495 | 0% | 0 | 40% | 38399363.5495 | 40% | 40 | 0
|  | Field |  |  |  | 6.576% | 17952442065.6699 | 4% | 718097682.6268 | 0% | 0 | 4% | 718097682.6268 | 4% |  | 0
|  | Carbon Steel |  |  |  | 0.7134% | 1947698717.1325 | 4% | 77907948.6853 | 0% | 0 | 4% | 77907948.6853 | 4% |  | 0
|  | Material Handling From Shop To Field | ID | 6223 | 0 | 0.03567% | 97384935.8566 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | m2 | 1 | 0 | 0.09275% | 253200833.2272 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 4045 | 0 | 0.1356% | 370062756.2552 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.03567% | 97384935.8566 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 4045 | 0 | 0.2354% | 642740576.6537 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 4045 | 0 | 0.01784% | 48692467.9283 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 4045 | 0 | 0.0214% | 58430961.514 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 4045 | 0 | 0.06778% | 185031378.1276 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.07134% | 194769871.7132 | 40% | 77907948.6853 | 0% | 0 | 40% | 77907948.6853 | 40% | 40 | 0
|  | Low Temperature CS |  |  |  | 5.276% | 14402265721.1655 | 4% | 576090628.8466 | 0% | 0 | 4% | 576090628.8466 | 4% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.2638% | 720113286.0583 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | m2 | 1 | 0 | 0.6858% | 1872294543.7515 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 1 | 0 | 1.002% | 2736430487.0215 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.2638% | 720113286.0583 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 1.741% | 4752747687.9846 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.1319% | 360056643.0291 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.1583% | 432067971.635 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.5012% | 1368215243.5107 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.5276% | 1440226572.1166 | 40% | 576090628.8466 | 0% | 0 | 40% | 576090628.8466 | 40% | 40 | 0
|  | Galva |  |  |  | 0.07807% | 213142019.066 | 4% | 8525680.7626 | 0% | 0 | 4% | 8525680.7626 | 4% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.003904% | 10657100.9533 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | m2 | 1 | 0 | 0.01015% | 27708462.4786 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 1 | 0 | 0.01483% | 40496983.6225 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.003904% | 10657100.9533 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.02576% | 70336866.2918 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.001952% | 5328550.4766 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.002342% | 6394260.572 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.007417% | 20248491.8113 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.007807% | 21314201.9066 | 40% | 8525680.7626 | 0% | 0 | 40% | 8525680.7626 | 40% | 40 | 0
|  | GRE |  |  |  | 0.07876% | 215019884.7006 | 4% | 8600795.388 | 0% | 0 | 4% | 8600795.388 | 4% |  | 0
|  | Scoffolding | m2 | 1 | 0 | 0.01024% | 27952585.0111 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling To Field | ID | 1 | 0 | 0.004726% | 12901193.082 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fittup | ID | 1 | 0 | 0.01496% | 40853778.0931 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Bonding | ID | 1 | 0 | 0.0315% | 86007953.8802 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.009451% | 25802386.1641 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.007876% | 21501988.4701 | 40% | 8600795.388 | 0% | 0 | 40% | 8600795.388 | 40% | 40 | 0
|  | Copper Alloys |  |  |  | 0.4302% | 1174315723.6053 | 4% | 46972628.9442 | 0% | 0 | 4% | 46972628.9442 | 4% |  | 0
|  | Material Handling From Shop To Field | ID | 1 | 0 | 0.02151% | 58715786.1803 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Scaffolding | m2 | 1 | 0 | 0.05592% | 152661044.0687 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection & Fit Up | ID | 1 | 0 | 0.08173% | 223119987.485 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Valve Installation | ID | 1 | 0 | 0.02151% | 58715786.1803 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | ID | 1 | 0 | 0.142% | 387524188.7898 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | ID | 1 | 0 | 0.01075% | 29357893.0901 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PWHT | ID | 1 | 0 | 0.0129% | 35229471.7082 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hydro test | ID | 1 | 0 | 0.04086% | 111559993.7425 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 40 | 0.04302% | 117431572.3605 | 40% | 46972628.9442 | 0% | 0 | 40% | 46972628.9442 | 40% | 40 | 0
|  | Pipe Support |  |  |  | 0.1044% | 285137694.9251 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Shop |  |  |  | 0.03656% | 99798193.2238 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Handling | Kg | 1 | 0 | 0.004021% | 10977801.2546 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | shop drawing | Kg | 1 | 0 | 0.005849% | 15967710.9158 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cutting & assembling | Kg | 1 | 0 | 0.008042% | 21955602.5092 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | Kg | 1 | 0 | 0.01682% | 45907168.8829 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.001828% | 4989909.6612 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Field |  |  |  | 0.06789% | 185339501.7013 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling From Shop To Field | Kg | 1 | 0 | 0.01086% | 29654320.2722 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Erection | Kg | 1 | 0 | 0.01426% | 38921295.3573 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Welding | Kg | 1 | 0 | 0.02851% | 77842590.7146 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | NDT | Kg | 1 | 0 | 0.01086% | 29654320.2722 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.003394% | 9266975.0851 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Painting & Sandblasting |  |  |  | 1.339% | 3655000150.5104 | 2.858% | 104448224.9743 | 0% | 0 | 2.858% | 104448224.9743 | 2.858% |  | 0
|  | Pipe |  |  |  | 1.325% | 3617652012.3048 | 2.887% | 104448224.9743 | 0% | 0 | 2.887% | 104448224.9743 | 2.887% |  | 0
|  | Sand Blast | m2 | 5200 | 429 | 0.1988% | 542647801.8457 | 8.25% | 44768443.6523 | 0% | 0 | 8.25% | 44768443.6523 | 8.25% | 415 | -14
|  | Primer | m2 | 5201 | 429 | 0.265% | 723530402.461 | 8.248% | 59679781.322 | 0% | 0 | 8.248% | 59679781.322 | 8.248% | 415 | -14
|  | Middle Paint | m2 | 5202 | 0 | 0.4638% | 1266178204.3067 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Paint | m2 | 5203 | 0 | 0.265% | 723530402.461 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Touch Up & Punch | m2 | 5204 | 0 | 0.06626% | 180882600.6152 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 100 | 0 | 0.06626% | 180882600.6152 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Support |  |  |  | 0.01368% | 37348138.2056 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Sand Blast | m2 | 1 | 0 | 0.002052% | 5602220.7308 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Primer | m2 | 1 | 0 | 0.002736% | 7469627.6411 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Middle Paint | m2 | 1 | 0 | 0.004788% | 13071848.372 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Paint | m2 | 1 | 0 | 0.002736% | 7469627.6411 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Touch Up & Punch | m2 | 1 | 0 | 0.000684% | 1867406.9103 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Certificate | % | 1 | 0 | 0.000684% | 1867406.9103 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Insulation |  |  |  | 0.111% | 303053133.4468 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Cold Insulation | m2 | 1 | 0 | 0.0555% | 151526566.7234 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Hot Insulation | m2 | 1 | 0 | 0.0555% | 151526566.7234 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Equipment Packages |  |  |  | 8.88% | 24242766904.2749 | 0.0274% | 6643475.4858 | 0% | 0 | 0.0274% | 6643475.4858 | 0.0274% |  | 0
|  | Static Equipment |  |  |  | 1.217% | 3321872656.5425 | 0.2% | 6643475.4858 | 0% | 0 | 0.2% | 6643475.4858 | 0.2% |  | 0
|  | Air cooler 147-A-101 |  |  |  | 0.7488% | 2044146303.3148 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.03744% | 102207315.1657 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.03744% | 102207315.1657 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.2621% | 715451206.1602 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.1123% | 306621945.4972 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.1123% | 306621945.4972 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.1498% | 408829260.663 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.03744% | 102207315.1657 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Vert.) 147-D-101 A |  |  |  | 0.03062% | 83605583.8056 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001531% | 4180279.1903 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001531% | 4180279.1903 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.01072% | 29261954.332 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.004594% | 12540837.5708 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.004594% | 12540837.5708 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.006125% | 16721116.7611 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001531% | 4180279.1903 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Vert.) 147-D-101 B |  |  |  | 0.03062% | 83605583.8056 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001531% | 4180279.1903 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001531% | 4180279.1903 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.01072% | 29261954.332 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.004594% | 12540837.5708 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.004594% | 12540837.5708 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.006125% | 16721116.7611 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001531% | 4180279.1903 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Vert.) 147-D-102 A |  |  |  | 0.0161% | 43949145.5213 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0008049% | 2197457.2761 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0008049% | 2197457.2761 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.005635% | 15382200.9324 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002415% | 6592371.8282 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002415% | 6592371.8282 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.00322% | 8789829.1043 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0008049% | 2197457.2761 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Vert.) 147-D-102 B |  |  |  | 0.0161% | 43949145.5213 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0008049% | 2197457.2761 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0008049% | 2197457.2761 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.005635% | 15382200.9324 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002415% | 6592371.8282 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002415% | 6592371.8282 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.00322% | 8789829.1043 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0008049% | 2197457.2761 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Vert.) 147-D-103 A |  |  |  | 0.01662% | 45380047.9336 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0008311% | 2269002.3967 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0008311% | 2269002.3967 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.005818% | 15883016.7768 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002493% | 6807007.19 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002493% | 6807007.19 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.003325% | 9076009.5867 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0008311% | 2269002.3967 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Vert.) 147-D-103 B |  |  |  | 0.01662% | 45380047.9336 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0008311% | 2269002.3967 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0008311% | 2269002.3967 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.005818% | 15883016.7768 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002493% | 6807007.19 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002493% | 6807007.19 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.003325% | 9076009.5867 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0008311% | 2269002.3967 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Hori) 147-D-104 |  |  |  | 0.0912% | 248977019.7437 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.00456% | 12448850.9872 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.00456% | 12448850.9872 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.03192% | 87141956.9103 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.01368% | 37346552.9616 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.01368% | 37346552.9616 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.01824% | 49795403.9487 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.00456% | 12448850.9872 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Vert.) 147-D-105 |  |  |  | 0.01977% | 53965462.4075 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0009884% | 2698273.1204 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0009884% | 2698273.1204 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.006919% | 18887911.8426 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002965% | 8094819.3611 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002965% | 8094819.3611 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.003954% | 10793092.4815 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0009884% | 2698273.1204 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Hori) 147-D-106 |  |  |  | 0.01018% | 27800389.7251 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005092% | 1390019.4863 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005092% | 1390019.4863 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003564% | 9730136.4038 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001527% | 4170058.4588 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001527% | 4170058.4588 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002037% | 5560077.945 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005092% | 1390019.4863 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Hori) 147-D-107 |  |  |  | 0.01947% | 53147803.8862 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0009734% | 2657390.1943 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0009734% | 2657390.1943 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.006814% | 18601731.3602 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.00292% | 7972170.5829 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.00292% | 7972170.5829 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.003894% | 10629560.7772 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0009734% | 2657390.1943 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Hori) 147-D-108 |  |  |  | 0.0001498% | 408829.2607 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 7.488e-06% | 20441.463 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 7.488e-06% | 20441.463 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 5.241e-05% | 143090.2412 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 2.246e-05% | 61324.3891 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 2.246e-05% | 61324.3891 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 2.995e-05% | 81765.8521 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 7.488e-06% | 20441.463 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Hori.) in Sump 147-D-109 |  |  |  | 0.02462% | 67211530.453 | 9.884% | 6643475.4858 | 0% | 0 | 9.884% | 6643475.4858 | 9.884% |  | 0
|  | Material Handling | Kg | 16440 | 16060 | 0.001231% | 3360576.5226 | 97.69% | 3282898.9631 | 0% | 0 | 97.69% | 3282898.9631 | 97.69% |  | -16060
|  | Chipping & Padding | % | 100 | 100 | 0.001231% | 3360576.5226 | 100% | 3360576.5226 | 0% | 0 | 100% | 3360576.5226 | 100% |  | -100
|  | Installation |  | 1 | 0 | 0.008617% | 23524035.6585 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.003693% | 10081729.5679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.003693% | 10081729.5679 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.004924% | 13442306.0906 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001231% | 3360576.5226 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Drum (Hori) on St. 147-D-110 |  |  |  | 0.05272% | 143928341.2164 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.002636% | 7196417.0608 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.002636% | 7196417.0608 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.01845% | 50374919.4257 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.007908% | 21589251.1825 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.007908% | 21589251.1825 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.01054% | 28785668.2433 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.002636% | 7196417.0608 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LP FLARE K.O. DRUM 147-D-111 |  |  |  | 0.007937% | 21667950.8151 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0003968% | 1083397.5408 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0003968% | 1083397.5408 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.002778% | 7583782.7853 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001191% | 3250192.6223 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001191% | 3250192.6223 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.001587% | 4333590.163 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0003968% | 1083397.5408 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Electric Heater 147-DH-107 |  |  |  | 0.0001857% | 506948.2832 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 9.285e-06% | 25347.4142 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 9.285e-06% | 25347.4142 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 6.499e-05% | 177431.8991 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 2.785e-05% | 76042.2425 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 2.785e-05% | 76042.2425 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 3.714e-05% | 101389.6566 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 9.285e-06% | 25347.4142 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Electric Heater 147-DH-108 |  |  |  | 0.0003519% | 960748.7626 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 1.76e-05% | 48037.4381 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 1.76e-05% | 48037.4381 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.0001232% | 336262.0669 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 5.279e-05% | 144112.3144 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 5.279e-05% | 144112.3144 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 7.038e-05% | 192149.7525 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 1.76e-05% | 48037.4381 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Electric Heater 147-DH-109 |  |  |  | 0.000292% | 797217.0583 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 1.46e-05% | 39860.8529 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 1.46e-05% | 39860.8529 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.0001022% | 279025.9704 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 4.38e-05% | 119582.5587 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 4.38e-05% | 119582.5587 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 5.84e-05% | 159443.4117 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 1.46e-05% | 39860.8529 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Electric Heater 147-DH-110 |  |  |  | 0.0003654% | 997543.396 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 1.827e-05% | 49877.1698 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 1.827e-05% | 49877.1698 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.0001279% | 349140.1886 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 5.481e-05% | 149631.5094 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 5.481e-05% | 149631.5094 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 7.308e-05% | 199508.6792 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 1.827e-05% | 49877.1698 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LPG TANK FLARE 147-X-101 |  |  |  | 0.03744% | 102207315.1657 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001872% | 5110365.7583 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001872% | 5110365.7583 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.0131% | 35772560.308 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.005616% | 15331097.2749 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.005616% | 15331097.2749 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.007488% | 20441463.0331 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001872% | 5110365.7583 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | LOW PRESSURE PROPANE CHILLER 147-E-101 |  |  |  | 0.01481% | 40433213.8796 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0007405% | 2021660.694 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0007405% | 2021660.694 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.005184% | 14151624.8578 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002222% | 6064982.0819 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002222% | 6064982.0819 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002962% | 8086642.7759 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0007405% | 2021660.694 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | MEDUIM PRESSURE PROPANE CHILLER 147-E-102 |  |  |  | 0.031% | 84627656.9572 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.00155% | 4231382.8479 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.00155% | 4231382.8479 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.01085% | 29619679.935 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.00465% | 12694148.5436 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.00465% | 12694148.5436 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.0062% | 16925531.3914 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.00155% | 4231382.8479 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | HIGH PRESSURE PROPANE CHILLER 147-E-103 |  |  |  | 0.02037% | 55600779.4502 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001018% | 2780038.9725 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001018% | 2780038.9725 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.007128% | 19460272.8076 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.003055% | 8340116.9175 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.003055% | 8340116.9175 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.004073% | 11120155.89 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001018% | 2780038.9725 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | PROPANE BOIL OFF GAS CONDENSER 147-E-104 |  |  |  | 0.01048% | 28618048.2464 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005241% | 1430902.4123 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005241% | 1430902.4123 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003669% | 10016316.8862 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001572% | 4292707.237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001572% | 4292707.237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002097% | 5723609.6493 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005241% | 1430902.4123 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Rotary Equipment |  |  |  | 7.663% | 20920894247.7324 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Compressor 147-K-101A |  |  |  | 2.677% | 7308349409.6104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.1339% | 365417470.4805 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.1339% | 365417470.4805 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.937% | 2557922293.3636 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.4016% | 1096252411.4416 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.4016% | 1096252411.4416 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.5354% | 1461669881.9221 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.1339% | 365417470.4805 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Compressor 147-K-101B |  |  |  | 2.677% | 7308349409.6104 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.1339% | 365417470.4805 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.1339% | 365417470.4805 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.937% | 2557922293.3636 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.4016% | 1096252411.4416 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.4016% | 1096252411.4416 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.5354% | 1461669881.9221 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.1339% | 365417470.4805 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Compressor 147-K-102A |  |  |  | 0.9691% | 2645556347.3703 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.04845% | 132277817.3685 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.04845% | 132277817.3685 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.3392% | 925944721.5796 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.1454% | 396833452.1055 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.1454% | 396833452.1055 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.1938% | 529111269.4741 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.04845% | 132277817.3685 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Compressor 147-K-101B |  |  |  | 0.9691% | 2645556347.3703 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.04845% | 132277817.3685 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.04845% | 132277817.3685 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.3392% | 925944721.5796 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.1454% | 396833452.1055 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.1454% | 396833452.1055 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.1938% | 529111269.4741 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.04845% | 132277817.3685 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-101A |  |  |  | 0.03634% | 99208363.0264 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.01272% | 34722927.0592 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.005451% | 14881254.454 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.005451% | 14881254.454 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.007268% | 19841672.6053 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-101B |  |  |  | 0.03634% | 99208363.0264 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.01272% | 34722927.0592 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.005451% | 14881254.454 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.005451% | 14881254.454 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.007268% | 19841672.6053 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-101C |  |  |  | 0.03634% | 99208363.0264 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.01272% | 34722927.0592 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.005451% | 14881254.454 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.005451% | 14881254.454 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.007268% | 19841672.6053 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001817% | 4960418.1513 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-102 |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-103A |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-103B |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-103C |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-104 |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-106 |  |  |  | 0.02261% | 61729648.1053 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001131% | 3086482.4053 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001131% | 3086482.4053 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.007914% | 21605376.8369 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.003392% | 9259447.2158 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.003392% | 9259447.2158 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.004522% | 12345929.6211 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001131% | 3086482.4053 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-107 |  |  |  | 0.02112% | 57651082.0698 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001056% | 2882554.1035 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001056% | 2882554.1035 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.007391% | 20177878.7244 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.003168% | 8647662.3105 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.003168% | 8647662.3105 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.004224% | 11530216.414 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001056% | 2882554.1035 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-108 |  |  |  | 0.01928% | 52635548.1612 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.000964% | 2631777.4081 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.000964% | 2631777.4081 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.006748% | 18422441.8564 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002892% | 7895332.2242 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002892% | 7895332.2242 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.003856% | 10527109.6322 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.000964% | 2631777.4081 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-109A |  |  |  | 0.01878% | 51257654.2303 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0009388% | 2562882.7115 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0009388% | 2562882.7115 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.006571% | 17940178.9806 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002816% | 7688648.1345 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002816% | 7688648.1345 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.003755% | 10251530.8461 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0009388% | 2562882.7115 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 147-P-109B |  |  |  | 0.01878% | 51257654.2303 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0009388% | 2562882.7115 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0009388% | 2562882.7115 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.006571% | 17940178.9806 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.002816% | 7688648.1345 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.002816% | 7688648.1345 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.003755% | 10251530.8461 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0009388% | 2562882.7115 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 148-P-101A |  |  |  | 0.02019% | 55115757.2369 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.007066% | 19290515.0329 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.003028% | 8267363.5855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.003028% | 8267363.5855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.004038% | 11023151.4474 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 148-P-101B |  |  |  | 0.02019% | 55115757.2369 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.007066% | 19290515.0329 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.003028% | 8267363.5855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.003028% | 8267363.5855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.004038% | 11023151.4474 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 148-P-101C |  |  |  | 0.02019% | 55115757.2369 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.007066% | 19290515.0329 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.003028% | 8267363.5855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.003028% | 8267363.5855 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.004038% | 11023151.4474 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.001009% | 2755787.8618 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 148-P-102 |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 148-P-103A |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 148-P-103B |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 148-P-103C |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Pump 148-P-104 |  |  |  | 0.01009% | 27557878.6184 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Material Handling |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Chipping & Padding |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Installation |  | 1 | 0 | 0.003533% | 9645257.5165 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Alignment |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Grouting |  | 1 | 0 | 0.001514% | 4133681.7928 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | External Installation |  | 1 | 0 | 0.002019% | 5511575.7237 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
|  | Final Inspection |  | 1 | 0 | 0.0005047% | 1377893.9309 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | 0
0
0

## checked (3)
South Pars Gas Field Development Phase 14
Description |  |  | Unit | Estimate | Work Performed | W.F
|  | Package NO.2 |  |  |  | 100%
|  | Procurement |  |  |  | 15%
|  | fire proof |  |  |  | 0.1987% | 15%
|  | PO Placement | m2 |  |  | 0.04968% | 0.1987%
|  | Fabrication & Test | m2 |  |  | 0.1192%
|  | Delivery | m2 |  |  | 0.02981%
|  | Rebar |  |  |  | 4.373%
|  | PO Placement | Kg |  |  | 1.093%
|  | Fabrication & Test | Kg |  |  | 2.624%
|  | Delivery | Kg |  |  | 0.6559%
|  | Piping Support |  |  |  | 0.934%
|  | PO Placement | Kg |  |  | 0.2335%
|  | Fabrication & Test | Kg |  |  | 0.5604%
|  | Delivery | Kg |  |  | 0.1401%
|  | Cold Insulating |  |  |  | 0.7797%
|  | PO Placement | m2 |  |  | 0.1949%
|  | Fabrication & Test | m2 |  |  | 0.4678%
|  | Delivery | m2 |  |  | 0.117%
|  | Warm Insulating |  |  |  | 0.5209%
|  | PO Placement | m2 |  |  | 0.1302%
|  | Fabrication & Test | m2 |  |  | 0.3125%
|  | Delivery | m2 |  |  | 0.07813%
|  | Paint |  |  |  | 5.56%
|  | PO Placement | Kg |  |  | 4.17%
|  | Delivery | Kg |  |  | 1.39%
|  | Electrode |  |  |  | 2.634%
|  | PO Placement | Kg |  |  | 0.6584%
|  | Fabrication & Test | Kg |  |  | 1.58%
|  | Delivery | Kg |  |  | 0.3951%
|  | Plant Construction |  |  |  | 85%
|  | General |  |  |  | 3.599%
|  | mobolization |  |  |  | 3.249%
|  | primary mobilozation | % |  |  | 1.3%
|  | countiuse mobilization | % |  |  | 1.95%
|  | Demobilizaton |  |  |  | 0.3496%
|  | Demobilizaton | % |  |  | 0.3496%
|  | Gate House |  |  |  | 0.6452%
|  | civil |  |  |  | 0.1613%
| ` | Foundation | % |  |  | 0.04839%
|  | columns | % |  |  | 0.04839%
|  | Wall | % |  |  | 0.01613%
|  | Floor | % |  |  | 0.01613%
|  | Roof | % |  |  | 0.03226%
|  | Mechanical |  |  |  | 0.06452%
|  | Piping | % |  |  | 0.04516%
|  | Installation | % |  |  | 0.01936%
|  | electrical |  |  |  | 0.06452%
|  | Cabling | % |  |  | 0.04516%
|  | Installation | % |  |  | 0.01936%
|  | telecom |  |  |  | 0.129%
|  | telecom | % |  |  | 0.129%
|  | architect |  |  |  | 0.1936%
|  | architect | % |  |  | 0.1936%
|  | final works |  |  |  | 0.03226%
|  | final works | % |  |  | 0.03226%
|  | Unit 140 |  |  |  | 43.74%
|  | Welding & NDT Procedures |  |  |  | 2.527%
|  | Prepare and qualify welding procedures (welding procedures qualfication tests (WPQT) including lab. Tests) for structural and pipe welding | % |  |  | 0.01263%
|  | Qualification of welders including lab testing for structural and pipe welding | % |  |  | 0.01263%
|  | Qualification of welding equipment | % |  |  | 0.01263%
|  | Maintaining welder qualification records | % |  |  | 0.01263%
|  | Monitoring welder performance | % |  |  | 0.01263%
|  | Prepare and NDT Procedures and obtain certification | % |  |  | 0.7581%
|  | Qualification of NDT equipment and dimensional control (UT, RT, MT,...) | % |  |  | 0.01263%
|  | Qualification of equipment operators for NDT and dimensional control | % |  |  | 0.01263%
|  | Perform NDT as per the procedures | % |  |  | 0.2022%
|  | Supply of associated Elec. Power, consumables, Materials construction equipments | % |  |  | 0.2022%
|  | Prepare PWHT procedure and obtain certification | % |  |  | 0.6317%
|  | Perform PWHT testing | % |  |  | 0.3285%
|  | Provide and maintain secure storage for radioactive sources | % |  |  | 0.3032%
|  | Implement specific safety procedures relating to radioactive sources | % |  |  | 0.01263%
|  | Civil |  |  |  | 5.511%
|  | Plat Form |  |  |  | 2.567%
|  | West HP |  |  |  | 1.097%
|  | excavation | m3 |  |  | 0.08773%
|  | level&compact | m2 |  |  | 0.02193%
|  | lean | m3 |  |  | 0.01097%
|  | footing rebar | Kg |  |  | 0.1535%
|  | footing form | m2 |  |  | 0.1151%
|  | foting concrete | m3 |  |  | 0.2303%
|  | ped rebar | Kg |  |  | 0.0658%
|  | ped form | m2 |  |  | 0.04935%
|  | anchor | NO. |  |  | 0.05483%
|  | ped concrete | m3 |  |  | 0.09869%
|  | curing | % |  |  | 0.01097%
|  | coating | m2 |  |  | 0.0329%
|  | back fill | m3 |  |  | 0.1097%
|  | Final Certificate | % |  |  | 0.05483%
|  | East HP |  |  |  | 1.078%
|  | excavation | m3 |  |  | 0.08621%
|  | level&compact | m2 |  |  | 0.02155%
|  | lean | m3 |  |  | 0.01078%
|  | footing rebar | Kg |  |  | 0.1509%
|  | footing form | m2 |  |  | 0.1132%
|  | foting concrete | m3 |  |  | 0.2263%
|  | ped rebar | Kg |  |  | 0.06466%
|  | ped form | m2 |  |  | 0.04849%
|  | anchor | NO. |  |  | 0.05388%
|  | ped concrete | m3 |  |  | 0.09699%
|  | curing | % |  |  | 0.01078%
|  | coating | m2 |  |  | 0.03233%
|  | back fill | m3 |  |  | 0.1078%
|  | Final Certificate | % |  |  | 0.05388%
|  | West LP |  |  |  | 0.1705%
|  | excavation | m3 |  |  | 0.01364%
|  | level&compact | m2 |  |  | 0.003411%
|  | lean | m3 |  |  | 0.001705%
|  | footing rebar | Kg |  |  | 0.02387%
|  | footing form | m2 |  |  | 0.01791%
|  | foting concrete | m3 |  |  | 0.03581%
|  | ped rebar | Kg |  |  | 0.01023%
|  | ped form | m2 |  |  | 0.007674%
|  | anchor | NO. |  |  | 0.008526%
|  | ped concrete | m3 |  |  | 0.01535%
|  | curing | % |  |  | 0.001705%
|  | coating | m2 |  |  | 0.005116%
|  | back fill | m3 |  |  | 0.01705%
|  | Final Certificate | % |  |  | 0.008526%
|  | East LP |  |  |  | 0.2226%
|  | excavation | m3 |  |  | 0.01781%
|  | level&compact | m2 |  |  | 0.004453%
|  | lean | m3 |  |  | 0.002226%
|  | footing rebar | Kg |  |  | 0.03117%
|  | footing form | m2 |  |  | 0.02338%
|  | foting concrete | m3 |  |  | 0.04675%
|  | ped rebar | Kg |  |  | 0.01336%
|  | ped form | m2 |  |  | 0.01002%
|  | anchor | NO. |  |  | 0.01113%
|  | ped concrete | m3 |  |  | 0.02004%
|  | curing | % |  |  | 0.002226%
|  | coating | m2 |  |  | 0.006679%
|  | back fill | m3 |  |  | 0.02226%
|  | Final Certificate | % |  |  | 0.01113%
|  | Retaining wall |  |  |  | 2.849%
|  | Retaining wall 7 |  |  |  | 1.902%
|  | excavation | m3 |  |  | 0.1522%
|  | level&compact | m2 |  |  | 0.03805%
|  | lean | m3 |  |  | 0.01902%
|  | footing rebar | Kg |  |  | 0.2663%
|  | footing form | m2 |  |  | 0.1997%
|  | foting concrete | m3 |  |  | 0.3995%
|  | Wall rebar | Kg |  |  | 0.1141%
|  | Wall form | m2 |  |  | 0.08561%
|  | Wall concrete | m3 |  |  | 0.2663%
|  | curing | % |  |  | 0.01902%
|  | coating | m2 |  |  | 0.05707%
|  | back fill | m3 |  |  | 0.1902%
|  | Final Certificate | % |  |  | 0.09512%
|  | Retaining wall 9 |  |  |  | 0.2292%
|  | excavation | m3 |  |  | 0.01834%
|  | level&compact | m2 |  |  | 0.004584%
|  | lean | m3 |  |  | 0.002292%
|  | footing rebar | Kg |  |  | 0.03209%
|  | footing form | m2 |  |  | 0.02407%
|  | foting concrete | m3 |  |  | 0.04813%
|  | Wall rebar | Kg |  |  | 0.01375%
|  | Wall form | m2 |  |  | 0.01031%
|  | Wall concrete | m3 |  |  | 0.03209%
|  | curing | % |  |  | 0.002292%
|  | coating | m2 |  |  | 0.006876%
|  | back fill | m3 |  |  | 0.02292%
|  | Final Certificate | % |  |  | 0.01146%
|  | Retaining wall 11 |  |  |  | 0.2292%
|  | excavation | m3 |  |  | 0.01834%
|  | level&compact | m2 |  |  | 0.004584%
|  | lean | m3 |  |  | 0.002292%
|  | footing rebar | Kg |  |  | 0.03209%
|  | footing form | m2 |  |  | 0.02407%
|  | foting concrete | m3 |  |  | 0.04813%
|  | Wall rebar | Kg |  |  | 0.01375%
|  | Wall form | m2 |  |  | 0.01031%
|  | Wall concrete | m3 |  |  | 0.03209%
|  | curing | % |  |  | 0.002292%
|  | coating | m2 |  |  | 0.006876%
|  | back fill | m3 |  |  | 0.02292%
|  | Final Certificate | % |  |  | 0.01146%
|  | Retaining wall 12 |  |  |  | 0.3438%
|  | excavation | m3 |  |  | 0.0275%
|  | level&compact | m2 |  |  | 0.006876%
|  | lean | m3 |  |  | 0.003438%
|  | footing rebar | Kg |  |  | 0.04813%
|  | footing form | m2 |  |  | 0.0361%
|  | foting concrete | m3 |  |  | 0.0722%
|  | Wall rebar | Kg |  |  | 0.02063%
|  | Wall form | m2 |  |  | 0.01547%
|  | Wall concrete | m3 |  |  | 0.04813%
|  | curing | % |  |  | 0.003438%
|  | coating | m2 |  |  | 0.01031%
|  | back fill | m3 |  |  | 0.03438%
|  | Final Certificate | % |  |  | 0.01719%
|  | Retaining wall 13 |  |  |  | 0.1444%
|  | excavation | m3 |  |  | 0.01155%
|  | level&compact | m2 |  |  | 0.002888%
|  | lean | m3 |  |  | 0.001444%
|  | footing rebar | Kg |  |  | 0.02022%
|  | footing form | m2 |  |  | 0.01516%
|  | foting concrete | m3 |  |  | 0.03032%
|  | Wall rebar | Kg |  |  | 0.008664%
|  | Wall form | m2 |  |  | 0.006498%
|  | Wall concrete | m3 |  |  | 0.02022%
|  | curing | % |  |  | 0.001444%
|  | coating | m2 |  |  | 0.004332%
|  | back fill | m3 |  |  | 0.01444%
|  | Final Certificate | % |  |  | 0.00722%
|  | Base & Burn Pit |  |  |  | 0.095%
|  | Piping |  |  |  | 19.52%
|  | AG Piping |  |  |  | 19.32%
|  | Shop |  |  |  | 6.763%
|  | Carbon Steel |  |  |  | 3.489%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.1744%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 1.221%
|  | Welding | ID |  |  | 1.221%
|  | NDT | ID |  |  | 0.1744%
|  | PWHT | ID |  |  | 0.1744%
|  | Final Certificate | % |  |  | 0.5233%
|  | Low Temperature CS |  |  |  | 1.993%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.09967%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.6977%
|  | Welding | ID |  |  | 0.6977%
|  | NDT | ID |  |  | 0.09967%
|  | PWHT | ID |  |  | 0.09967%
|  | Final Certificate | % |  |  | 0.299%
|  | Stainless Steel |  |  |  | 1.167%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.05833%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.4083%
|  | Welding | ID |  |  | 0.4083%
|  | NDT | ID |  |  | 0.05833%
|  | PWHT | ID |  |  | 0.05833%
|  | Final Certificate | % |  |  | 0.175%
|  | Galva |  |  |  | 0.115%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.00575%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.04025%
|  | Welding | ID |  |  | 0.04025%
|  | NDT | ID |  |  | 0.00575%
|  | PWHT | ID |  |  | 0.00575%
|  | Final Certificate | % |  |  | 0.01725%
|  | Field |  |  |  | 12.56%
|  | Carbon Steel |  |  |  | 6.478%
|  | Material Handling From Shop To Field | ID |  |  | 0.3239%
|  | Scaffolding | m2 |  |  | 0.8422%
|  | Erection & Fit Up | ID |  |  | 1.231%
|  | Valve Installation | ID |  |  | 0.3239%
|  | Welding | ID |  |  | 2.138%
|  | NDT | ID |  |  | 0.162%
|  | PWHT | ID |  |  | 0.1944%
|  | Hydro test | ID |  |  | 0.6155%
|  | Final Certificate | % |  |  | 0.6478%
|  | Low Temperature CS |  |  |  | 3.702%
|  | Material Handling From Shop To Field | ID |  |  | 0.1851%
|  | Scaffolding | m2 |  |  | 0.4813%
|  | Erection & Fit Up | ID |  |  | 0.7034%
|  | Valve Installation | ID |  |  | 0.1851%
|  | Welding | ID |  |  | 1.222%
|  | NDT | ID |  |  | 0.09255%
|  | PWHT | ID |  |  | 0.1111%
|  | Hydro test | ID |  |  | 0.3517%
|  | Final Certificate | % |  |  | 0.3702%
|  | Stainless Steel |  |  |  | 2.166%
|  | Material Handling From Shop To Field | ID |  |  | 0.1083%
|  | Scaffolding | m2 |  |  | 0.2816%
|  | Erection & Fit Up | ID |  |  | 0.4116%
|  | Valve Installation | ID |  |  | 0.1083%
|  | Welding | ID |  |  | 0.7149%
|  | NDT | ID |  |  | 0.05416%
|  | PWHT | ID |  |  | 0.06499%
|  | Hydro test | ID |  |  | 0.2058%
|  | Final Certificate | % |  |  | 0.2166%
|  | Galva |  |  |  | 0.2136%
|  | Material Handling From Shop To Field | ID |  |  | 0.01068%
|  | Scaffolding | m2 |  |  | 0.02776%
|  | Erection & Fit Up | ID |  |  | 0.04058%
|  | Valve Installation | ID |  |  | 0.01068%
|  | Welding | ID |  |  | 0.07048%
|  | NDT | ID |  |  | 0.005339%
|  | PWHT | ID |  |  | 0.006407%
|  | Hydro test | ID |  |  | 0.02029%
|  | Final Certificate | % |  |  | 0.02136%
|  | Pipe Support |  |  |  | 0.1995%
|  | Shop |  |  |  | 0.06982%
|  | Handling | Kg |  |  | 0.007681%
|  | shop drawing | Kg |  |  | 0.01117%
|  | Cutting & assembling | Kg |  |  | 0.01536%
|  | Welding | Kg |  |  | 0.03212%
|  | Final Certificate | % |  |  | 0.003491%
|  | Field |  |  |  | 0.1297%
|  | Material Handling From Shop To Field | Kg |  |  | 0.01426%
|  | Erection | Kg |  |  | 0.02723%
|  | Welding | Kg |  |  | 0.06743%
|  | NDT | Kg |  |  | 0.01426%
|  | Final Certificate | % |  |  | 0.006484%
|  | Painting & Sandblasting |  |  |  | 2.557%
|  | Pipe |  |  |  | 2.531%
|  | Sand Blast | m2 |  |  | 0.3797%
|  | Primer | m2 |  |  | 0.5062%
|  | Middle Paint | m2 |  |  | 0.8859%
|  | Final Paint | m2 |  |  | 0.5062%
|  | Touch Up & Punch | m2 |  |  | 0.1266%
|  | Final Certificate | % |  |  | 0.1266%
|  | Support |  |  |  | 0.02613%
|  | Sand Blast | m2 |  |  | 0.00392%
|  | Primer | m2 |  |  | 0.005226%
|  | Middle Paint | m2 |  |  | 0.009146%
|  | Final Paint | m2 |  |  | 0.005226%
|  | Touch Up & Punch | m2 |  |  | 0.001307%
|  | Final Certificate | % |  |  | 0.001307%
|  | Steel Structure |  |  |  | 7.466%
|  | Installation Steel Structure |  |  |  | 7.399%
|  | 140-IM-A1 |  |  |  | 0.2474%
|  | Handling | Kg |  |  | 0.02474%
|  | Chip&Padding | NO |  |  | 0.01237%
|  | Erection | Kg |  |  | 0.09894%
|  | Alignment | Kg |  |  | 0.02968%
|  | Bolt Tightening & Test | Kg |  |  | 0.01979%
|  | Grouting | NO |  |  | 0.02474%
|  | Final test & Documents | % |  |  | 0.0371%
|  | 140-IM-A2 |  |  |  | 0.3595%
|  | Handling | Kg |  |  | 0.03595%
|  | Chip&Padding | NO |  |  | 0.01797%
|  | Erection | Kg |  |  | 0.1438%
|  | Alignment | Kg |  |  | 0.04313%
|  | Bolt Tightening & Test | Kg |  |  | 0.02876%
|  | Grouting | NO |  |  | 0.03595%
|  | Final test & Documents | % |  |  | 0.05392%
|  | 140-IM-A3 |  |  |  | 0.2126%
|  | Handling | Kg |  |  | 0.02126%
|  | Chip&Padding | NO |  |  | 0.01063%
|  | Erection | Kg |  |  | 0.08504%
|  | Alignment | Kg |  |  | 0.02551%
|  | Bolt Tightening & Test | Kg |  |  | 0.01701%
|  | Grouting | NO |  |  | 0.02126%
|  | Final test & Documents | % |  |  | 0.03189%
|  | 140-IM-A4 |  |  |  | 0.1649%
|  | Handling | Kg |  |  | 0.01649%
|  | Chip&Padding | NO |  |  | 0.008243%
|  | Erection | Kg |  |  | 0.06594%
|  | Alignment | Kg |  |  | 0.01978%
|  | Bolt Tightening & Test | Kg |  |  | 0.01319%
|  | Grouting | NO |  |  | 0.01649%
|  | Final test & Documents | % |  |  | 0.02473%
|  | 140-IM-A5 |  |  |  | 0.4729%
|  | Handling | Kg |  |  | 0.04729%
|  | Chip&Padding | NO |  |  | 0.02365%
|  | Erection | Kg |  |  | 0.1892%
|  | Alignment | Kg |  |  | 0.05675%
|  | Bolt Tightening & Test | Kg |  |  | 0.03783%
|  | Grouting | NO |  |  | 0.04729%
|  | Final test & Documents | % |  |  | 0.07094%
|  | 140-IM-A6 |  |  |  | 0.3567%
|  | Handling | Kg |  |  | 0.03567%
|  | Chip&Padding | NO |  |  | 0.01784%
|  | Erection | Kg |  |  | 0.1427%
|  | Alignment | Kg |  |  | 0.04281%
|  | Bolt Tightening & Test | Kg |  |  | 0.02854%
|  | Grouting | NO |  |  | 0.03567%
|  | Final test & Documents | % |  |  | 0.05351%
|  | 140-IM-A7 |  |  |  | 0.1538%
|  | Handling | Kg |  |  | 0.01538%
|  | Chip&Padding | NO |  |  | 0.007689%
|  | Erection | Kg |  |  | 0.06152%
|  | Alignment | Kg |  |  | 0.01845%
|  | Bolt Tightening & Test | Kg |  |  | 0.0123%
|  | Grouting | NO |  |  | 0.01538%
|  | Final test & Documents | % |  |  | 0.02307%
|  | 140-IM-B1 |  |  |  | 0.1758%
|  | Handling | Kg |  |  | 0.01758%
|  | Chip&Padding | NO |  |  | 0.008789%
|  | Erection | Kg |  |  | 0.07031%
|  | Alignment | Kg |  |  | 0.02109%
|  | Bolt Tightening & Test | Kg |  |  | 0.01406%
|  | Grouting | NO |  |  | 0.01758%
|  | Final test & Documents | % |  |  | 0.02637%
|  | 140-IM-B2 |  |  |  | 0.4518%
|  | Handling | Kg |  |  | 0.04518%
|  | Chip&Padding | NO |  |  | 0.02259%
|  | Erection | Kg |  |  | 0.1807%
|  | Alignment | Kg |  |  | 0.05421%
|  | Bolt Tightening & Test | Kg |  |  | 0.03614%
|  | Grouting | NO |  |  | 0.04518%
|  | Final test & Documents | % |  |  | 0.06777%
|  | 140-IM-B3 |  |  |  | 0.4453%
|  | Handling | Kg |  |  | 0.04453%
|  | Chip&Padding | NO |  |  | 0.02227%
|  | Erection | Kg |  |  | 0.1781%
|  | Alignment | Kg |  |  | 0.05344%
|  | Bolt Tightening & Test | Kg |  |  | 0.03563%
|  | Grouting | NO |  |  | 0.04453%
|  | Final test & Documents | % |  |  | 0.0668%
|  | 140-IM-B4 |  |  |  | 0.3028%
|  | Handling | Kg |  |  | 0.03028%
|  | Chip&Padding | NO |  |  | 0.01514%
|  | Erection | Kg |  |  | 0.1211%
|  | Alignment | Kg |  |  | 0.03633%
|  | Bolt Tightening & Test | Kg |  |  | 0.02422%
|  | Grouting | NO |  |  | 0.03028%
|  | Final test & Documents | % |  |  | 0.04542%
|  | 140-IM-B5 |  |  |  | 0.1895%
|  | Handling | Kg |  |  | 0.01895%
|  | Chip&Padding | NO |  |  | 0.009473%
|  | Erection | Kg |  |  | 0.07579%
|  | Alignment | Kg |  |  | 0.02274%
|  | Bolt Tightening & Test | Kg |  |  | 0.01516%
|  | Grouting | NO |  |  | 0.01895%
|  | Final test & Documents | % |  |  | 0.02842%
|  | 140-IM-B6 |  |  |  | 0.4257%
|  | Handling | Kg |  |  | 0.04257%
|  | Chip&Padding | NO |  |  | 0.02128%
|  | Erection | Kg |  |  | 0.1703%
|  | Alignment | Kg |  |  | 0.05108%
|  | Bolt Tightening & Test | Kg |  |  | 0.03405%
|  | Grouting | NO |  |  | 0.04257%
|  | Final test & Documents | % |  |  | 0.06385%
|  | 140-IM-B7 |  |  |  | 0.2262%
|  | Handling | Kg |  |  | 0.02262%
|  | Chip&Padding | NO |  |  | 0.01131%
|  | Erection | Kg |  |  | 0.09049%
|  | Alignment | Kg |  |  | 0.02715%
|  | Bolt Tightening & Test | Kg |  |  | 0.0181%
|  | Grouting | NO |  |  | 0.02262%
|  | Final test & Documents | % |  |  | 0.03393%
|  | 140-IM-B8 |  |  |  | 0.2579%
|  | Handling | Kg |  |  | 0.02579%
|  | Chip&Padding | NO |  |  | 0.0129%
|  | Erection | Kg |  |  | 0.1032%
|  | Alignment | Kg |  |  | 0.03095%
|  | Bolt Tightening & Test | Kg |  |  | 0.02063%
|  | Grouting | NO |  |  | 0.02579%
|  | Final test & Documents | % |  |  | 0.03869%
|  | 140-IM-B9 |  |  |  | 0.1566%
|  | Handling | Kg |  |  | 0.01566%
|  | Chip&Padding | NO |  |  | 0.007828%
|  | Erection | Kg |  |  | 0.06262%
|  | Alignment | Kg |  |  | 0.01879%
|  | Bolt Tightening & Test | Kg |  |  | 0.01252%
|  | Grouting | NO |  |  | 0.01566%
|  | Final test & Documents | % |  |  | 0.02348%
|  | 140-IM-B10 |  |  |  | 0.2676%
|  | Handling | Kg |  |  | 0.02676%
|  | Chip&Padding | NO |  |  | 0.01338%
|  | Erection | Kg |  |  | 0.107%
|  | Alignment | Kg |  |  | 0.03211%
|  | Bolt Tightening & Test | Kg |  |  | 0.02141%
|  | Grouting | NO |  |  | 0.02676%
|  | Final test & Documents | % |  |  | 0.04014%
|  | 140-IM-B11 |  |  |  | 0.3757%
|  | Handling | Kg |  |  | 0.03757%
|  | Chip&Padding | NO |  |  | 0.01879%
|  | Erection | Kg |  |  | 0.1503%
|  | Alignment | Kg |  |  | 0.04508%
|  | Bolt Tightening & Test | Kg |  |  | 0.03006%
|  | Grouting | NO |  |  | 0.03757%
|  | Final test & Documents | % |  |  | 0.05636%
|  | 140-IM-B12 |  |  |  | 0.2155%
|  | Handling | Kg |  |  | 0.02155%
|  | Chip&Padding | NO |  |  | 0.01078%
|  | Erection | Kg |  |  | 0.0862%
|  | Alignment | Kg |  |  | 0.02586%
|  | Bolt Tightening & Test | Kg |  |  | 0.01724%
|  | Grouting | NO |  |  | 0.02155%
|  | Final test & Documents | % |  |  | 0.03233%
|  | 140-IM-B13 |  |  |  | 0.3027%
|  | Handling | Kg |  |  | 0.03027%
|  | Chip&Padding | NO |  |  | 0.01513%
|  | Erection | Kg |  |  | 0.1211%
|  | Alignment | Kg |  |  | 0.03632%
|  | Bolt Tightening & Test | Kg |  |  | 0.02422%
|  | Grouting | NO |  |  | 0.03027%
|  | Final test & Documents | % |  |  | 0.0454%
|  | 140-IM-C1 |  |  |  | 0.08789%
|  | Handling | Kg |  |  | 0.008789%
|  | Chip&Padding | NO |  |  | 0.004394%
|  | Erection | Kg |  |  | 0.03515%
|  | Alignment | Kg |  |  | 0.01055%
|  | Bolt Tightening & Test | Kg |  |  | 0.007031%
|  | Grouting | NO |  |  | 0.008789%
|  | Final test & Documents | % |  |  | 0.01318%
|  | 140-IM-C2 |  |  |  | 0.1658%
|  | Handling | Kg |  |  | 0.01658%
|  | Chip&Padding | NO |  |  | 0.008289%
|  | Erection | Kg |  |  | 0.06631%
|  | Alignment | Kg |  |  | 0.01989%
|  | Bolt Tightening & Test | Kg |  |  | 0.01326%
|  | Grouting | NO |  |  | 0.01658%
|  | Final test & Documents | % |  |  | 0.02487%
|  | 140-IM-C3 |  |  |  | 0.08368%
|  | Handling | Kg |  |  | 0.008368%
|  | Chip&Padding | NO |  |  | 0.004184%
|  | Erection | Kg |  |  | 0.03347%
|  | Alignment | Kg |  |  | 0.01004%
|  | Bolt Tightening & Test | Kg |  |  | 0.006694%
|  | Grouting | NO |  |  | 0.008368%
|  | Final test & Documents | % |  |  | 0.01255%
|  | 140-IM-D1 |  |  |  | 0.1514%
|  | Handling | Kg |  |  | 0.01514%
|  | Chip&Padding | NO |  |  | 0.007572%
|  | Erection | Kg |  |  | 0.06058%
|  | Alignment | Kg |  |  | 0.01817%
|  | Bolt Tightening & Test | Kg |  |  | 0.01212%
|  | Grouting | NO |  |  | 0.01514%
|  | Final test & Documents | % |  |  | 0.02272%
|  | 140-IM-D2 |  |  |  | 0.1342%
|  | Handling | Kg |  |  | 0.01342%
|  | Chip&Padding | NO |  |  | 0.006712%
|  | Erection | Kg |  |  | 0.05369%
|  | Alignment | Kg |  |  | 0.01611%
|  | Bolt Tightening & Test | Kg |  |  | 0.01074%
|  | Grouting | NO |  |  | 0.01342%
|  | Final test & Documents | % |  |  | 0.02014%
|  | 140-IM-D3 |  |  |  | 0.178%
|  | Handling | Kg |  |  | 0.0178%
|  | Chip&Padding | NO |  |  | 0.008901%
|  | Erection | Kg |  |  | 0.07121%
|  | Alignment | Kg |  |  | 0.02136%
|  | Bolt Tightening & Test | Kg |  |  | 0.01424%
|  | Grouting | NO |  |  | 0.0178%
|  | Final test & Documents | % |  |  | 0.0267%
|  | 140-IM-D4 |  |  |  | 0.1544%
|  | Handling | Kg |  |  | 0.01544%
|  | Chip&Padding | NO |  |  | 0.007722%
|  | Erection | Kg |  |  | 0.06178%
|  | Alignment | Kg |  |  | 0.01853%
|  | Bolt Tightening & Test | Kg |  |  | 0.01236%
|  | Grouting | NO |  |  | 0.01544%
|  | Final test & Documents | % |  |  | 0.02317%
|  | 140-IM-E1 |  |  |  | 0.1329%
|  | Handling | Kg |  |  | 0.01329%
|  | Chip&Padding | NO |  |  | 0.006644%
|  | Erection | Kg |  |  | 0.05315%
|  | Alignment | Kg |  |  | 0.01595%
|  | Bolt Tightening & Test | Kg |  |  | 0.01063%
|  | Grouting | NO |  |  | 0.01329%
|  | Final test & Documents | % |  |  | 0.01993%
|  | 140-IM-E2 |  |  |  | 0.1702%
|  | Handling | Kg |  |  | 0.01702%
|  | Chip&Padding | NO |  |  | 0.008509%
|  | Erection | Kg |  |  | 0.06808%
|  | Alignment | Kg |  |  | 0.02042%
|  | Bolt Tightening & Test | Kg |  |  | 0.01362%
|  | Grouting | NO |  |  | 0.01702%
|  | Final test & Documents | % |  |  | 0.02553%
|  | 140-IM-E3 |  |  |  | 0.1053%
|  | Handling | Kg |  |  | 0.01053%
|  | Chip&Padding | NO |  |  | 0.005263%
|  | Erection | Kg |  |  | 0.0421%
|  | Alignment | Kg |  |  | 0.01263%
|  | Bolt Tightening & Test | Kg |  |  | 0.00842%
|  | Grouting | NO |  |  | 0.01053%
|  | Final test & Documents | % |  |  | 0.01579%
|  | 140-IM-E4 |  |  |  | 0.03736%
|  | Handling | Kg |  |  | 0.003736%
|  | Chip&Padding | NO |  |  | 0.001868%
|  | Erection | Kg |  |  | 0.01495%
|  | Alignment | Kg |  |  | 0.004484%
|  | Bolt Tightening & Test | Kg |  |  | 0.002989%
|  | Grouting | NO |  |  | 0.003736%
|  | Final test & Documents | % |  |  | 0.005605%
|  | 140-IM-F1 |  |  |  | 0.0942%
|  | Handling | Kg |  |  | 0.00942%
|  | Chip&Padding | NO |  |  | 0.00471%
|  | Erection | Kg |  |  | 0.03768%
|  | Alignment | Kg |  |  | 0.0113%
|  | Bolt Tightening & Test | Kg |  |  | 0.007536%
|  | Grouting | NO |  |  | 0.00942%
|  | Final test & Documents | % |  |  | 0.01413%
|  | 140-IM-F2 |  |  |  | 0.1429%
|  | Handling | Kg |  |  | 0.01429%
|  | Chip&Padding | NO |  |  | 0.007144%
|  | Erection | Kg |  |  | 0.05715%
|  | Alignment | Kg |  |  | 0.01715%
|  | Bolt Tightening & Test | Kg |  |  | 0.01143%
|  | Grouting | NO |  |  | 0.01429%
|  | Final test & Documents | % |  |  | 0.02143%
|  | Fireproofing |  |  |  | 0.06706%
|  | Fireproofing | m2 |  |  | 0.06706%
|  | Insulation |  |  |  | 0.212%
|  | Cold Insulation | m2 |  |  | 0.106%
|  | Hot Insulation | m2 |  |  | 0.106%
|  | Equipment Packages |  |  |  | 5.941%
|  | Static Equipment |  |  |  | 3.268%
|  | HP FLARE 140-X-101 |  |  |  | 0.7275%
|  | Material Handling | Kg |  |  | 0.03638%
|  | Chipping & Padding | % |  |  | 0.03638%
|  | Installation | Kg |  |  | 0.2546%
|  | Alignment | Kg |  |  | 0.1091%
|  | Grouting | % |  |  | 0.1091%
|  | External Installation | Kg |  |  | 0.1455%
|  | Final Inspection | % |  |  | 0.03638%
|  | HP FLARE 140-X-201 |  |  |  | 0.7275%
|  | Material Handling | Kg |  |  | 0.03638%
|  | Chipping & Padding | % |  |  | 0.03638%
|  | Installation | Kg |  |  | 0.2546%
|  | Alignment | Kg |  |  | 0.1091%
|  | Grouting | % |  |  | 0.1091%
|  | External Installation | Kg |  |  | 0.1455%
|  | Final Inspection | % |  |  | 0.03638%
|  | LP FLARE 140-X-102 |  |  |  | 0.08424%
|  | Material Handling | Kg |  |  | 0.004212%
|  | Chipping & Padding | % |  |  | 0.004212%
|  | Installation | Kg |  |  | 0.02948%
|  | Alignment | Kg |  |  | 0.01264%
|  | Grouting | % |  |  | 0.01264%
|  | External Installation | Kg |  |  | 0.01685%
|  | Final Inspection | % |  |  | 0.004212%
|  | LP FLARE 140-X-202 |  |  |  | 0.08424%
|  | Material Handling | Kg |  |  | 0.004212%
|  | Chipping & Padding | % |  |  | 0.004212%
|  | Installation | Kg |  |  | 0.02948%
|  | Alignment | Kg |  |  | 0.01264%
|  | Grouting | % |  |  | 0.01264%
|  | External Installation | Kg |  |  | 0.01685%
|  | Final Inspection | % |  |  | 0.004212%
|  | MP FLARE 140-X-103 |  |  |  | 0.7275%
|  | Material Handling | Kg |  |  | 0.03638%
|  | Chipping & Padding | % |  |  | 0.03638%
|  | Installation | Kg |  |  | 0.2546%
|  | Alignment | Kg |  |  | 0.1091%
|  | Grouting | % |  |  | 0.1091%
|  | External Installation | Kg |  |  | 0.1455%
|  | Final Inspection | % |  |  | 0.03638%
|  | MP FLARE 140-X-203 |  |  |  | 0.7275%
|  | Material Handling | Kg |  |  | 0.03638%
|  | Chipping & Padding | % |  |  | 0.03638%
|  | Installation | Kg |  |  | 0.2546%
|  | Alignment | Kg |  |  | 0.1091%
|  | Grouting | % |  |  | 0.1091%
|  | External Installation | Kg |  |  | 0.1455%
|  | Final Inspection | % |  |  | 0.03638%
|  | HP Wet Flare K.O. Drum Heater 140-DH-101 |  |  |  | 0.0009343%
|  | Material Handling | Kg |  |  | 4.671e-05%
|  | Chipping & Padding | % |  |  | 4.671e-05%
|  | Installation | Kg |  |  | 0.000327%
|  | Alignment | Kg |  |  | 0.0001401%
|  | Grouting | % |  |  | 0.0001401%
|  | External Installation | Kg |  |  | 0.0001869%
|  | Final Inspection | % |  |  | 4.671e-05%
|  | HP Wet Flare K.O. Drum Heater 140-DH-103 |  |  |  | 0.0009343%
|  | Material Handling | Kg |  |  | 4.671e-05%
|  | Chipping & Padding | % |  |  | 4.671e-05%
|  | Installation | Kg |  |  | 0.000327%
|  | Alignment | Kg |  |  | 0.0001401%
|  | Grouting | % |  |  | 0.0001401%
|  | External Installation | Kg |  |  | 0.0001869%
|  | Final Inspection | % |  |  | 4.671e-05%
|  | HP Cold Flare K.O. Drum Heater 140-DH-104 |  |  |  | 0.0009534%
|  | Material Handling | Kg |  |  | 4.767e-05%
|  | Chipping & Padding | % |  |  | 4.767e-05%
|  | Installation | Kg |  |  | 0.0003337%
|  | Alignment | Kg |  |  | 0.000143%
|  | Grouting | % |  |  | 0.000143%
|  | External Installation | Kg |  |  | 0.0001907%
|  | Final Inspection | % |  |  | 4.767e-05%
|  | HP Wet Flare K.O. Drum Heater 140-DH-201 |  |  |  | 0.0009343%
|  | Material Handling | Kg |  |  | 4.671e-05%
|  | Chipping & Padding | % |  |  | 4.671e-05%
|  | Installation | Kg |  |  | 0.000327%
|  | Alignment | Kg |  |  | 0.0001401%
|  | Grouting | % |  |  | 0.0001401%
|  | External Installation | Kg |  |  | 0.0001869%
|  | Final Inspection | % |  |  | 4.671e-05%
|  | MP Flare K.O. Drum Heater 140-DH-203 |  |  |  | 0.0009343%
|  | Material Handling | Kg |  |  | 4.671e-05%
|  | Chipping & Padding | % |  |  | 4.671e-05%
|  | Installation | Kg |  |  | 0.000327%
|  | Alignment | Kg |  |  | 0.0001401%
|  | Grouting | % |  |  | 0.0001401%
|  | External Installation | Kg |  |  | 0.0001869%
|  | Final Inspection | % |  |  | 4.671e-05%
|  | HP Cold Flare K.O. Drum Heater 140-DH-204 |  |  |  | 0.0009534%
|  | Material Handling | Kg |  |  | 4.767e-05%
|  | Chipping & Padding | % |  |  | 4.767e-05%
|  | Installation | Kg |  |  | 0.0003337%
|  | Alignment | Kg |  |  | 0.000143%
|  | Grouting | % |  |  | 0.000143%
|  | External Installation | Kg |  |  | 0.0001907%
|  | Final Inspection | % |  |  | 4.767e-05%
|  | HP Flare Stack K.O. Drum Heater 140-DH-105 |  |  |  | 0.04595%
|  | Material Handling | Kg |  |  | 0.002297%
|  | Chipping & Padding | % |  |  | 0.002297%
|  | Installation | Kg |  |  | 0.01608%
|  | Alignment | Kg |  |  | 0.006892%
|  | Grouting | % |  |  | 0.006892%
|  | External Installation | Kg |  |  | 0.00919%
|  | Final Inspection | % |  |  | 0.002297%
|  | HP Flare Stack K.O. Drum Heater 140-DH-106 |  |  |  | 0.04595%
|  | Material Handling | Kg |  |  | 0.002297%
|  | Chipping & Padding | % |  |  | 0.002297%
|  | Installation | Kg |  |  | 0.01608%
|  | Alignment | Kg |  |  | 0.006892%
|  | Grouting | % |  |  | 0.006892%
|  | External Installation | Kg |  |  | 0.00919%
|  | Final Inspection | % |  |  | 0.002297%
|  | HP Flare Stack K.O. Drum Heater 140-DH-205 |  |  |  | 0.04595%
|  | Material Handling | Kg |  |  | 0.002297%
|  | Chipping & Padding | % |  |  | 0.002297%
|  | Installation | Kg |  |  | 0.01608%
|  | Alignment | Kg |  |  | 0.006892%
|  | Grouting | % |  |  | 0.006892%
|  | External Installation | Kg |  |  | 0.00919%
|  | Final Inspection | % |  |  | 0.002297%
|  | HP Flare Stack K.O. Drum Heater 140-DH-206 |  |  |  | 0.04595%
|  | Material Handling | Kg |  |  | 0.002297%
|  | Chipping & Padding | % |  |  | 0.002297%
|  | Installation | Kg |  |  | 0.01608%
|  | Alignment | Kg |  |  | 0.006892%
|  | Grouting | % |  |  | 0.006892%
|  | External Installation | Kg |  |  | 0.00919%
|  | Final Inspection | % |  |  | 0.002297%
|  | Rotary Equipment |  |  |  | 2.673%
|  | HP FLARE STACKS PUMPS, 140-P-104A |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | HP FLARE STACKS PUMPS, 140-P-104B |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | LP FLARE STACKS PUMPS, 140-P-105A |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | LP FLARE STACKS PUMPS, 140-P-105B |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | MP FLARE STACKS PUMPS, 140-P-106A |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | MP FLARE STACKS PUMPS, 140-P-106B |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | HP FLARE STACKS PUMPS, 140-P-204A |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | HP FLARE STACKS PUMPS, 140-P-204B |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | LP FLARE STACKS PUMPS, 140-P-205A |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | LP FLARE STACKS PUMPS, 140-P-205B |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | MP FLARE STACKS PUMPS, 140-P-206A |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | MP FLARE STACKS PUMPS, 140-P-206B |  |  |  | 0.2227%
|  | Material Handling | Kg |  |  | 0.01114%
|  | Chipping & Padding | % |  |  | 0.01114%
|  | Installation | Kg |  |  | 0.07796%
|  | Alignment | Kg |  |  | 0.03341%
|  | Grouting | % |  |  | 0.03341%
|  | External Installation | Kg |  |  | 0.04455%
|  | Final Inspection | % |  |  | 0.01114%
|  | Unit 143 |  |  |  | 15.14%
|  | Welding & NDT Procedures |  |  |  | 1.15%
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % |  |  | 0.00575%
|  | Qualification of Welders including Lab Testing For Structural & Piping | % |  |  | 0.00575%
|  | Qualification of Welding Equipments | % |  |  | 0.00575%
|  | Maintaining Welder Qualification Records | % |  |  | 0.00575%
|  | Monitoring Welder Performance | % |  |  | 0.00575%
|  | Prepare NDT Procedures & Obtain Certification | % |  |  | 0.345%
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % |  |  | 0.00575%
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % |  |  | 0.00575%
|  | Perform NDT as per the Procedures | % |  |  | 0.092%
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % |  |  | 0.092%
|  | Prepare PWHT Procedures & Obtain Certification | % |  |  | 0.2875%
|  | Perform PWHT Testing | % |  |  | 0.1495%
|  | Provide and maintain secure storage for radioactive sources | % |  |  | 0.138%
|  | Implement specific safety procedures relating to radioactive sources | % |  |  | 0.00575%
|  | Piping |  |  |  | 8.885%
|  | AG Piping |  |  |  | 8.794%
|  | Shop |  |  |  | 3.078%
|  | Carbon Steel |  |  |  | 2.083%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.1041%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.7289%
|  | Welding | ID |  |  | 0.7289%
|  | NDT | ID |  |  | 0.1041%
|  | PWHT | ID |  |  | 0.1041%
|  | Final Certificate | % |  |  | 0.3124%
|  | Low Temperature CS |  |  |  | 0.3407%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.01704%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.1193%
|  | Welding | ID |  |  | 0.1193%
|  | NDT | ID |  |  | 0.01704%
|  | PWHT | ID |  |  | 0.01704%
|  | Final Certificate | % |  |  | 0.05111%
|  | Stainless Steel |  |  |  | 0.0001235%
|  | Material Handling From Lay down To Shop | ID |  |  | 6.173e-06%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 4.321e-05%
|  | Welding | ID |  |  | 4.321e-05%
|  | NDT | ID |  |  | 6.173e-06%
|  | PWHT | ID |  |  | 6.173e-06%
|  | Final Certificate | % |  |  | 1.852e-05%
|  | Galva |  |  |  | 0.1825%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.009123%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.06386%
|  | Welding | ID |  |  | 0.06386%
|  | NDT | ID |  |  | 0.009123%
|  | PWHT | ID |  |  | 0.009123%
|  | Final Certificate | % |  |  | 0.02737%
|  | CU-NI |  |  |  | 0.472%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.0236%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.1652%
|  | Welding | ID |  |  | 0.1652%
|  | NDT | ID |  |  | 0.0236%
|  | PWHT | ID |  |  | 0.0236%
|  | Final Certificate | % |  |  | 0.07081%
|  | Field |  |  |  | 5.716%
|  | Carbon Steel |  |  |  | 3.868%
|  | Material Handling From Shop To Field | ID |  |  | 0.2223%
|  | Erection & Fit Up | ID |  |  | 0.8446%
|  | Valve Installation | ID |  |  | 0.2223%
|  | Welding | ID |  |  | 1.467%
|  | NDT | ID |  |  | 0.1111%
|  | PWHT | ID |  |  | 0.1334%
|  | Hydro test | ID |  |  | 0.4223%
|  | Final Certificate | % |  |  | 0.4446%
|  | Low Temperature CS |  |  |  | 0.6328%
|  | Material Handling From Shop To Field | ID |  |  | 0.03637%
|  | Erection & Fit Up | ID |  |  | 0.1382%
|  | Valve Installation | ID |  |  | 0.03637%
|  | Welding | ID |  |  | 0.24%
|  | NDT | ID |  |  | 0.01818%
|  | PWHT | ID |  |  | 0.02182%
|  | Hydro test | ID |  |  | 0.0691%
|  | Final Certificate | % |  |  | 0.07274%
|  | Stainless Steel |  |  |  | 0.0002293%
|  | Material Handling From Shop To Field | ID |  |  | 1.318e-05%
|  | Erection & Fit Up | ID |  |  | 5.007e-05%
|  | Valve Installation | ID |  |  | 1.318e-05%
|  | Welding | ID |  |  | 8.697e-05%
|  | NDT | ID |  |  | 6.588e-06%
|  | PWHT | ID |  |  | 7.906e-06%
|  | Hydro test | ID |  |  | 2.504e-05%
|  | Final Certificate | % |  |  | 2.635e-05%
|  | Galva |  |  |  | 0.3389%
|  | Material Handling From Shop To Field | ID |  |  | 0.01948%
|  | Erection & Fit Up | ID |  |  | 0.07401%
|  | Valve Installation | ID |  |  | 0.01948%
|  | Welding | ID |  |  | 0.1285%
|  | NDT | ID |  |  | 0.009738%
|  | PWHT | ID |  |  | 0.01169%
|  | Hydro test | ID |  |  | 0.037%
|  | Final Certificate | % |  |  | 0.03895%
|  | CU-NI |  |  |  | 0.8766%
|  | Material Handling From Shop To Field | ID |  |  | 0.05038%
|  | Erection & Fit Up | ID |  |  | 0.1914%
|  | Valve Installation | ID |  |  | 0.05038%
|  | Welding | ID |  |  | 0.3325%
|  | NDT | ID |  |  | 0.02519%
|  | PWHT | ID |  |  | 0.03023%
|  | Hydro test | ID |  |  | 0.09572%
|  | Final Certificate | % |  |  | 0.1008%
|  | Pipe Support |  |  |  | 0.09079%
|  | Shop |  |  |  | 0.03178%
|  | Handling | Kg |  |  | 0.003495%
|  | shop drawing | Kg |  |  | 0.005084%
|  | Cutting & assembling | Kg |  |  | 0.006991%
|  | Welding | Kg |  |  | 0.01462%
|  | Final Certificate | % |  |  | 0.001589%
|  | Field |  |  |  | 0.05901%
|  | Material Handling From Shop To Field | Kg |  |  | 0.006491%
|  | Erection | Kg |  |  | 0.01239%
|  | Welding | Kg |  |  | 0.03069%
|  | NDT | Kg |  |  | 0.006491%
|  | Final Certificate | % |  |  | 0.002951%
|  | Painting & Sandblasting |  |  |  | 1.164%
|  | Pipe |  |  |  | 1.152%
|  | Sand Blast | m2 |  |  | 0.1728%
|  | Primer | m2 |  |  | 0.2304%
|  | Middle Paint | m2 |  |  | 0.4032%
|  | Final Paint | m2 |  |  | 0.2304%
|  | Touch Up & Punch | m2 |  |  | 0.05759%
|  | Final Certificate | % |  |  | 0.05759%
|  | Support |  |  |  | 0.01189%
|  | Sand Blast | m2 |  |  | 0.001784%
|  | Primer | m2 |  |  | 0.002378%
|  | Middle Paint | m2 |  |  | 0.004162%
|  | Final Paint | m2 |  |  | 0.002378%
|  | Touch Up & Punch | m2 |  |  | 0.0005946%
|  | Final Certificate | % |  |  | 0.0005946%
|  | Insulation |  |  |  | 0.09649%
|  | Cold Insulation | M2 |  |  | 0.04825%
|  | Hot Insulation | M2 |  |  | 0.04825%
|  | Equipment Packages |  |  |  | 3.848%
|  | Static Equipment |  |  |  | 0.2516%
|  | Sump Drum 143-D-101 |  |  |  | 0.1962%
|  | Material Handling |  |  |  | 0.009808%
|  | Chipping & Padding |  |  |  | 0.009808%
|  | Installation |  |  |  | 0.06866%
|  | Alignment |  |  |  | 0.02942%
|  | Grouting |  |  |  | 0.02942%
|  | External Installation |  |  |  | 0.03923%
|  | Final Inspection |  |  |  | 0.009808%
|  | Degassing Boot 143-D-102 |  |  |  | 0.05541%
|  | Material Handling |  |  |  | 0.00277%
|  | Chipping & Padding |  |  |  | 0.00277%
|  | Installation |  |  |  | 0.01939%
|  | Alignment |  |  |  | 0.008311%
|  | Grouting |  |  |  | 0.008311%
|  | External Installation |  |  |  | 0.01108%
|  | Final Inspection |  |  |  | 0.00277%
|  | Rotary Equipment |  |  |  | 3.597%
|  | Pump 143-P-101 |  |  |  | 0.5136%
|  | Material Handling |  |  |  | 0.02568%
|  | Chipping & Padding |  |  |  | 0.02568%
|  | Installation |  |  |  | 0.1798%
|  | Alignment |  |  |  | 0.07705%
|  | Grouting |  |  |  | 0.07705%
|  | External Installation |  |  |  | 0.1027%
|  | Final Inspection |  |  |  | 0.02568%
|  | Pump 143-P-102 |  |  |  | 0.9399%
|  | Material Handling |  |  |  | 0.047%
|  | Chipping & Padding |  |  |  | 0.047%
|  | Installation |  |  |  | 0.329%
|  | Alignment |  |  |  | 0.141%
|  | Grouting |  |  |  | 0.141%
|  | External Installation |  |  |  | 0.188%
|  | Final Inspection |  |  |  | 0.047%
|  | Pump 143-P-103 A |  |  |  | 0.6093%
|  | Material Handling |  |  |  | 0.03047%
|  | Chipping & Padding |  |  |  | 0.03047%
|  | Installation |  |  |  | 0.2133%
|  | Alignment |  |  |  | 0.0914%
|  | Grouting |  |  |  | 0.0914%
|  | External Installation |  |  |  | 0.1219%
|  | Final Inspection |  |  |  | 0.03047%
|  | Pump 143-P-103 B |  |  |  | 0.6093%
|  | Material Handling |  |  |  | 0.03047%
|  | Chipping & Padding |  |  |  | 0.03047%
|  | Installation |  |  |  | 0.2133%
|  | Alignment |  |  |  | 0.0914%
|  | Grouting |  |  |  | 0.0914%
|  | External Installation |  |  |  | 0.1219%
|  | Final Inspection |  |  |  | 0.03047%
|  | Pump 143-P-103 C |  |  |  | 0.6093%
|  | Material Handling |  |  |  | 0.03047%
|  | Chipping & Padding |  |  |  | 0.03047%
|  | Installation |  |  |  | 0.2133%
|  | Alignment |  |  |  | 0.0914%
|  | Grouting |  |  |  | 0.0914%
|  | External Installation |  |  |  | 0.1219%
|  | Final Inspection |  |  |  | 0.03047%
|  | Pump 143-P-104 |  |  |  | 0.3151%
|  | Material Handling |  |  |  | 0.01575%
|  | Chipping & Padding |  |  |  | 0.01575%
|  | Installation |  |  |  | 0.1103%
|  | Alignment |  |  |  | 0.04726%
|  | Grouting |  |  |  | 0.04726%
|  | External Installation |  |  |  | 0.06301%
|  | Final Inspection |  |  |  | 0.01575%
|  | Unit 147/148 |  |  |  | 21.87%
|  | Welding & NDT Procedures |  |  |  | 1.323%
|  | Prepare & Qualify Welding Procedures for Structural & Pipe Welding | % |  |  | 0.006615%
|  | Qualification of Welders including Lab Testing For Structural & Piping | % |  |  | 0.006615%
|  | Qualification of Welding Equipments | % |  |  | 0.006615%
|  | Maintaining Welder Qualification Records | % |  |  | 0.006615%
|  | Monitoring Welder Performance | % |  |  | 0.006615%
|  | Prepare NDT Procedures & Obtain Certification | % |  |  | 0.3969%
|  | Qualification of NDT Equipment & Dimensional Control (UT,RT,MT) | % |  |  | 0.006615%
|  | Qualification of Equipment Operators for NDT & Dimensional Control | % |  |  | 0.006615%
|  | Perform NDT as per the Procedures | % |  |  | 0.1058%
|  | Supply of Associated Elec.,Power, Consumables, Milts Construction Equipments | % |  |  | 0.1058%
|  | Prepare PWHT Procedures & Obtain Certification | % |  |  | 0.3307%
|  | Perform PWHT Testing | % |  |  | 0.172%
|  | Provide and maintain secure storage for radioactive sources | % |  |  | 0.1588%
|  | Implement specific safety procedures relating to radioactive sources | % |  |  | 0.006615%
|  | Piping |  |  |  | 10.22%
|  | AG Piping |  |  |  | 10.12%
|  | Shop |  |  |  | 3.541%
|  | Carbon Steel |  |  |  | 0.3889%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.01944%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.1361%
|  | Welding | ID |  |  | 0.1361%
|  | NDT | ID |  |  | 0.01944%
|  | PWHT | ID |  |  | 0.01944%
|  | Final Certificate | % |  |  | 0.05833%
|  | Low Temperature CS |  |  |  | 2.875%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.1438%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 1.006%
|  | Welding | ID |  |  | 1.006%
|  | NDT | ID |  |  | 0.1438%
|  | PWHT | ID |  |  | 0.1438%
|  | Final Certificate | % |  |  | 0.4313%
|  | Galva |  |  |  | 0.04255%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.002127%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.01489%
|  | Welding | ID |  |  | 0.01489%
|  | NDT | ID |  |  | 0.002127%
|  | PWHT | ID |  |  | 0.002127%
|  | Final Certificate | % |  |  | 0.006382%
|  | Copper Alloys |  |  |  | 0.2344%
|  | Material Handling From Lay down To Shop | ID |  |  | 0.01172%
|  | Cutting & Bevelling & Fit Up | ID |  |  | 0.08205%
|  | Welding | ID |  |  | 0.08205%
|  | NDT | ID |  |  | 0.01172%
|  | PWHT | ID |  |  | 0.01172%
|  | Final Certificate | % |  |  | 0.03516%
|  | Field |  |  |  | 6.576%
|  | Carbon Steel |  |  |  | 0.7134%
|  | Material Handling From Shop To Field | ID |  |  | 0.03567%
|  | Scaffolding | m2 |  |  | 0.09275%
|  | Erection & Fit Up | ID |  |  | 0.1356%
|  | Valve Installation | ID |  |  | 0.03567%
|  | Welding | ID |  |  | 0.2354%
|  | NDT | ID |  |  | 0.01784%
|  | PWHT | ID |  |  | 0.0214%
|  | Hydro test | ID |  |  | 0.06778%
|  | Final Certificate | % |  |  | 0.07134%
|  | Low Temperature CS |  |  |  | 5.276%
|  | Material Handling From Shop To Field | ID |  |  | 0.2638%
|  | Scaffolding | m2 |  |  | 0.6858%
|  | Erection & Fit Up | ID |  |  | 1.002%
|  | Valve Installation | ID |  |  | 0.2638%
|  | Welding | ID |  |  | 1.741%
|  | NDT | ID |  |  | 0.1319%
|  | PWHT | ID |  |  | 0.1583%
|  | Hydro test | ID |  |  | 0.5012%
|  | Final Certificate | % |  |  | 0.5276%
|  | Galva |  |  |  | 0.07807%
|  | Material Handling From Shop To Field | ID |  |  | 0.003904%
|  | Scaffolding | m2 |  |  | 0.01015%
|  | Erection & Fit Up | ID |  |  | 0.01483%
|  | Valve Installation | ID |  |  | 0.003904%
|  | Welding | ID |  |  | 0.02576%
|  | NDT | ID |  |  | 0.001952%
|  | PWHT | ID |  |  | 0.002342%
|  | Hydro test | ID |  |  | 0.007417%
|  | Final Certificate | % |  |  | 0.007807%
|  | GRE |  |  |  | 0.07876%
|  | Scoffolding | m2 |  |  | 0.01024%
|  | Material Handling To Field | ID |  |  | 0.004726%
|  | Erection & Fittup | ID |  |  | 0.01496%
|  | Bonding | ID |  |  | 0.0315%
|  | Hydro test | ID |  |  | 0.009451%
|  | Final Certificate | % |  |  | 0.007876%
|  | Copper Alloys |  |  |  | 0.4302%
|  | Material Handling From Shop To Field | ID |  |  | 0.02151%
|  | Scaffolding | m2 |  |  | 0.05592%
|  | Erection & Fit Up | ID |  |  | 0.08173%
|  | Valve Installation | ID |  |  | 0.02151%
|  | Welding | ID |  |  | 0.142%
|  | NDT | ID |  |  | 0.01075%
|  | PWHT | ID |  |  | 0.0129%
|  | Hydro test | ID |  |  | 0.04086%
|  | Final Certificate | % |  |  | 0.04302%
|  | Pipe Support |  |  |  | 0.1044%
|  | Shop |  |  |  | 0.03656%
|  | Handling | Kg |  |  | 0.004021%
|  | shop drawing | Kg |  |  | 0.005849%
|  | Cutting & assembling | Kg |  |  | 0.008042%
|  | Welding | Kg |  |  | 0.01682%
|  | Final Certificate | % |  |  | 0.001828%
|  | Field |  |  |  | 0.06789%
|  | Material Handling From Shop To Field | Kg |  |  | 0.01086%
|  | Erection | Kg |  |  | 0.01426%
|  | Welding | Kg |  |  | 0.02851%
|  | NDT | Kg |  |  | 0.01086%
|  | Final Certificate | % |  |  | 0.003394%
|  | Painting & Sandblasting |  |  |  | 1.339%
|  | Pipe |  |  |  | 1.325%
|  | Sand Blast | m2 |  |  | 0.1988%
|  | Primer | m2 |  |  | 0.265%
|  | Middle Paint | m2 |  |  | 0.4638%
|  | Final Paint | m2 |  |  | 0.265%
|  | Touch Up & Punch | m2 |  |  | 0.06626%
|  | Final Certificate | % |  |  | 0.06626%
|  | Support |  |  |  | 0.01368%
|  | Sand Blast | m2 |  |  | 0.002052%
|  | Primer | m2 |  |  | 0.002736%
|  | Middle Paint | m2 |  |  | 0.004788%
|  | Final Paint | m2 |  |  | 0.002736%
|  | Touch Up & Punch | m2 |  |  | 0.000684%
|  | Final Certificate | % |  |  | 0.000684%
|  | Insulation |  |  |  | 0.111%
|  | Cold Insulation | m2 |  |  | 0.0555%
|  | Hot Insulation | m2 |  |  | 0.0555%
|  | Equipment Packages |  |  |  | 8.88%
|  | Static Equipment |  |  |  | 1.217%
|  | Air cooler 147-A-101 |  |  |  | 0.7488%
|  | Material Handling |  |  |  | 0.03744%
|  | Chipping & Padding |  |  |  | 0.03744%
|  | Installation |  |  |  | 0.2621%
|  | Alignment |  |  |  | 0.1123%
|  | Grouting |  |  |  | 0.1123%
|  | External Installation |  |  |  | 0.1498%
|  | Final Inspection |  |  |  | 0.03744%
|  | Drum (Vert.) 147-D-101 A |  |  |  | 0.03062%
|  | Material Handling |  |  |  | 0.001531%
|  | Chipping & Padding |  |  |  | 0.001531%
|  | Installation |  |  |  | 0.01072%
|  | Alignment |  |  |  | 0.004594%
|  | Grouting |  |  |  | 0.004594%
|  | External Installation |  |  |  | 0.006125%
|  | Final Inspection |  |  |  | 0.001531%
|  | Drum (Vert.) 147-D-101 B |  |  |  | 0.03062%
|  | Material Handling |  |  |  | 0.001531%
|  | Chipping & Padding |  |  |  | 0.001531%
|  | Installation |  |  |  | 0.01072%
|  | Alignment |  |  |  | 0.004594%
|  | Grouting |  |  |  | 0.004594%
|  | External Installation |  |  |  | 0.006125%
|  | Final Inspection |  |  |  | 0.001531%
|  | Drum (Vert.) 147-D-102 A |  |  |  | 0.0161%
|  | Material Handling |  |  |  | 0.0008049%
|  | Chipping & Padding |  |  |  | 0.0008049%
|  | Installation |  |  |  | 0.005635%
|  | Alignment |  |  |  | 0.002415%
|  | Grouting |  |  |  | 0.002415%
|  | External Installation |  |  |  | 0.00322%
|  | Final Inspection |  |  |  | 0.0008049%
|  | Drum (Vert.) 147-D-102 B |  |  |  | 0.0161%
|  | Material Handling |  |  |  | 0.0008049%
|  | Chipping & Padding |  |  |  | 0.0008049%
|  | Installation |  |  |  | 0.005635%
|  | Alignment |  |  |  | 0.002415%
|  | Grouting |  |  |  | 0.002415%
|  | External Installation |  |  |  | 0.00322%
|  | Final Inspection |  |  |  | 0.0008049%
|  | Drum (Vert.) 147-D-103 A |  |  |  | 0.01662%
|  | Material Handling |  |  |  | 0.0008311%
|  | Chipping & Padding |  |  |  | 0.0008311%
|  | Installation |  |  |  | 0.005818%
|  | Alignment |  |  |  | 0.002493%
|  | Grouting |  |  |  | 0.002493%
|  | External Installation |  |  |  | 0.003325%
|  | Final Inspection |  |  |  | 0.0008311%
|  | Drum (Vert.) 147-D-103 B |  |  |  | 0.01662%
|  | Material Handling |  |  |  | 0.0008311%
|  | Chipping & Padding |  |  |  | 0.0008311%
|  | Installation |  |  |  | 0.005818%
|  | Alignment |  |  |  | 0.002493%
|  | Grouting |  |  |  | 0.002493%
|  | External Installation |  |  |  | 0.003325%
|  | Final Inspection |  |  |  | 0.0008311%
|  | Drum (Hori) 147-D-104 |  |  |  | 0.0912%
|  | Material Handling |  |  |  | 0.00456%
|  | Chipping & Padding |  |  |  | 0.00456%
|  | Installation |  |  |  | 0.03192%
|  | Alignment |  |  |  | 0.01368%
|  | Grouting |  |  |  | 0.01368%
|  | External Installation |  |  |  | 0.01824%
|  | Final Inspection |  |  |  | 0.00456%
|  | Drum (Vert.) 147-D-105 |  |  |  | 0.01977%
|  | Material Handling |  |  |  | 0.0009884%
|  | Chipping & Padding |  |  |  | 0.0009884%
|  | Installation |  |  |  | 0.006919%
|  | Alignment |  |  |  | 0.002965%
|  | Grouting |  |  |  | 0.002965%
|  | External Installation |  |  |  | 0.003954%
|  | Final Inspection |  |  |  | 0.0009884%
|  | Drum (Hori) 147-D-106 |  |  |  | 0.01018%
|  | Material Handling |  |  |  | 0.0005092%
|  | Chipping & Padding |  |  |  | 0.0005092%
|  | Installation |  |  |  | 0.003564%
|  | Alignment |  |  |  | 0.001527%
|  | Grouting |  |  |  | 0.001527%
|  | External Installation |  |  |  | 0.002037%
|  | Final Inspection |  |  |  | 0.0005092%
|  | Drum (Hori) 147-D-107 |  |  |  | 0.01947%
|  | Material Handling |  |  |  | 0.0009734%
|  | Chipping & Padding |  |  |  | 0.0009734%
|  | Installation |  |  |  | 0.006814%
|  | Alignment |  |  |  | 0.00292%
|  | Grouting |  |  |  | 0.00292%
|  | External Installation |  |  |  | 0.003894%
|  | Final Inspection |  |  |  | 0.0009734%
|  | Drum (Hori) 147-D-108 |  |  |  | 0.0001498%
|  | Material Handling |  |  |  | 7.488e-06%
|  | Chipping & Padding |  |  |  | 7.488e-06%
|  | Installation |  |  |  | 5.241e-05%
|  | Alignment |  |  |  | 2.246e-05%
|  | Grouting |  |  |  | 2.246e-05%
|  | External Installation |  |  |  | 2.995e-05%
|  | Final Inspection |  |  |  | 7.488e-06%
|  | Drum (Hori.) in Sump 147-D-109 |  |  |  | 0.02462%
|  | Material Handling | Kg |  |  | 0.001231%
|  | Chipping & Padding | % |  |  | 0.001231%
|  | Installation |  |  |  | 0.008617%
|  | Alignment |  |  |  | 0.003693%
|  | Grouting |  |  |  | 0.003693%
|  | External Installation |  |  |  | 0.004924%
|  | Final Inspection |  |  |  | 0.001231%
|  | Drum (Hori) on St. 147-D-110 |  |  |  | 0.05272%
|  | Material Handling |  |  |  | 0.002636%
|  | Chipping & Padding |  |  |  | 0.002636%
|  | Installation |  |  |  | 0.01845%
|  | Alignment |  |  |  | 0.007908%
|  | Grouting |  |  |  | 0.007908%
|  | External Installation |  |  |  | 0.01054%
|  | Final Inspection |  |  |  | 0.002636%
|  | LP FLARE K.O. DRUM 147-D-111 |  |  |  | 0.007937%
|  | Material Handling |  |  |  | 0.0003968%
|  | Chipping & Padding |  |  |  | 0.0003968%
|  | Installation |  |  |  | 0.002778%
|  | Alignment |  |  |  | 0.001191%
|  | Grouting |  |  |  | 0.001191%
|  | External Installation |  |  |  | 0.001587%
|  | Final Inspection |  |  |  | 0.0003968%
|  | Electric Heater 147-DH-107 |  |  |  | 0.0001857%
|  | Material Handling |  |  |  | 9.285e-06%
|  | Chipping & Padding |  |  |  | 9.285e-06%
|  | Installation |  |  |  | 6.499e-05%
|  | Alignment |  |  |  | 2.785e-05%
|  | Grouting |  |  |  | 2.785e-05%
|  | External Installation |  |  |  | 3.714e-05%
|  | Final Inspection |  |  |  | 9.285e-06%
|  | Electric Heater 147-DH-108 |  |  |  | 0.0003519%
|  | Material Handling |  |  |  | 1.76e-05%
|  | Chipping & Padding |  |  |  | 1.76e-05%
|  | Installation |  |  |  | 0.0001232%
|  | Alignment |  |  |  | 5.279e-05%
|  | Grouting |  |  |  | 5.279e-05%
|  | External Installation |  |  |  | 7.038e-05%
|  | Final Inspection |  |  |  | 1.76e-05%
|  | Electric Heater 147-DH-109 |  |  |  | 0.000292%
|  | Material Handling |  |  |  | 1.46e-05%
|  | Chipping & Padding |  |  |  | 1.46e-05%
|  | Installation |  |  |  | 0.0001022%
|  | Alignment |  |  |  | 4.38e-05%
|  | Grouting |  |  |  | 4.38e-05%
|  | External Installation |  |  |  | 5.84e-05%
|  | Final Inspection |  |  |  | 1.46e-05%
|  | Electric Heater 147-DH-110 |  |  |  | 0.0003654%
|  | Material Handling |  |  |  | 1.827e-05%
|  | Chipping & Padding |  |  |  | 1.827e-05%
|  | Installation |  |  |  | 0.0001279%
|  | Alignment |  |  |  | 5.481e-05%
|  | Grouting |  |  |  | 5.481e-05%
|  | External Installation |  |  |  | 7.308e-05%
|  | Final Inspection |  |  |  | 1.827e-05%
|  | LPG TANK FLARE 147-X-101 |  |  |  | 0.03744%
|  | Material Handling |  |  |  | 0.001872%
|  | Chipping & Padding |  |  |  | 0.001872%
|  | Installation |  |  |  | 0.0131%
|  | Alignment |  |  |  | 0.005616%
|  | Grouting |  |  |  | 0.005616%
|  | External Installation |  |  |  | 0.007488%
|  | Final Inspection |  |  |  | 0.001872%
|  | LOW PRESSURE PROPANE CHILLER 147-E-101 |  |  |  | 0.01481%
|  | Material Handling |  |  |  | 0.0007405%
|  | Chipping & Padding |  |  |  | 0.0007405%
|  | Installation |  |  |  | 0.005184%
|  | Alignment |  |  |  | 0.002222%
|  | Grouting |  |  |  | 0.002222%
|  | External Installation |  |  |  | 0.002962%
|  | Final Inspection |  |  |  | 0.0007405%
|  | MEDUIM PRESSURE PROPANE CHILLER 147-E-102 |  |  |  | 0.031%
|  | Material Handling |  |  |  | 0.00155%
|  | Chipping & Padding |  |  |  | 0.00155%
|  | Installation |  |  |  | 0.01085%
|  | Alignment |  |  |  | 0.00465%
|  | Grouting |  |  |  | 0.00465%
|  | External Installation |  |  |  | 0.0062%
|  | Final Inspection |  |  |  | 0.00155%
|  | HIGH PRESSURE PROPANE CHILLER 147-E-103 |  |  |  | 0.02037%
|  | Material Handling |  |  |  | 0.001018%
|  | Chipping & Padding |  |  |  | 0.001018%
|  | Installation |  |  |  | 0.007128%
|  | Alignment |  |  |  | 0.003055%
|  | Grouting |  |  |  | 0.003055%
|  | External Installation |  |  |  | 0.004073%
|  | Final Inspection |  |  |  | 0.001018%
|  | PROPANE BOIL OFF GAS CONDENSER 147-E-104 |  |  |  | 0.01048%
|  | Material Handling |  |  |  | 0.0005241%
|  | Chipping & Padding |  |  |  | 0.0005241%
|  | Installation |  |  |  | 0.003669%
|  | Alignment |  |  |  | 0.001572%
|  | Grouting |  |  |  | 0.001572%
|  | External Installation |  |  |  | 0.002097%
|  | Final Inspection |  |  |  | 0.0005241%
|  | Rotary Equipment |  |  |  | 7.663%
|  | Compressor 147-K-101A |  |  |  | 2.677%
|  | Material Handling |  |  |  | 0.1339%
|  | Chipping & Padding |  |  |  | 0.1339%
|  | Installation |  |  |  | 0.937%
|  | Alignment |  |  |  | 0.4016%
|  | Grouting |  |  |  | 0.4016%
|  | External Installation |  |  |  | 0.5354%
|  | Final Inspection |  |  |  | 0.1339%
|  | Compressor 147-K-101B |  |  |  | 2.677%
|  | Material Handling |  |  |  | 0.1339%
|  | Chipping & Padding |  |  |  | 0.1339%
|  | Installation |  |  |  | 0.937%
|  | Alignment |  |  |  | 0.4016%
|  | Grouting |  |  |  | 0.4016%
|  | External Installation |  |  |  | 0.5354%
|  | Final Inspection |  |  |  | 0.1339%
|  | Compressor 147-K-102A |  |  |  | 0.9691%
|  | Material Handling |  |  |  | 0.04845%
|  | Chipping & Padding |  |  |  | 0.04845%
|  | Installation |  |  |  | 0.3392%
|  | Alignment |  |  |  | 0.1454%
|  | Grouting |  |  |  | 0.1454%
|  | External Installation |  |  |  | 0.1938%
|  | Final Inspection |  |  |  | 0.04845%
|  | Compressor 147-K-101B |  |  |  | 0.9691%
|  | Material Handling |  |  |  | 0.04845%
|  | Chipping & Padding |  |  |  | 0.04845%
|  | Installation |  |  |  | 0.3392%
|  | Alignment |  |  |  | 0.1454%
|  | Grouting |  |  |  | 0.1454%
|  | External Installation |  |  |  | 0.1938%
|  | Final Inspection |  |  |  | 0.04845%
|  | Pump 147-P-101A |  |  |  | 0.03634%
|  | Material Handling |  |  |  | 0.001817%
|  | Chipping & Padding |  |  |  | 0.001817%
|  | Installation |  |  |  | 0.01272%
|  | Alignment |  |  |  | 0.005451%
|  | Grouting |  |  |  | 0.005451%
|  | External Installation |  |  |  | 0.007268%
|  | Final Inspection |  |  |  | 0.001817%
|  | Pump 147-P-101B |  |  |  | 0.03634%
|  | Material Handling |  |  |  | 0.001817%
|  | Chipping & Padding |  |  |  | 0.001817%
|  | Installation |  |  |  | 0.01272%
|  | Alignment |  |  |  | 0.005451%
|  | Grouting |  |  |  | 0.005451%
|  | External Installation |  |  |  | 0.007268%
|  | Final Inspection |  |  |  | 0.001817%
|  | Pump 147-P-101C |  |  |  | 0.03634%
|  | Material Handling |  |  |  | 0.001817%
|  | Chipping & Padding |  |  |  | 0.001817%
|  | Installation |  |  |  | 0.01272%
|  | Alignment |  |  |  | 0.005451%
|  | Grouting |  |  |  | 0.005451%
|  | External Installation |  |  |  | 0.007268%
|  | Final Inspection |  |  |  | 0.001817%
|  | Pump 147-P-102 |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 147-P-103A |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 147-P-103B |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 147-P-103C |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 147-P-104 |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 147-P-106 |  |  |  | 0.02261%
|  | Material Handling |  |  |  | 0.001131%
|  | Chipping & Padding |  |  |  | 0.001131%
|  | Installation |  |  |  | 0.007914%
|  | Alignment |  |  |  | 0.003392%
|  | Grouting |  |  |  | 0.003392%
|  | External Installation |  |  |  | 0.004522%
|  | Final Inspection |  |  |  | 0.001131%
|  | Pump 147-P-107 |  |  |  | 0.02112%
|  | Material Handling |  |  |  | 0.001056%
|  | Chipping & Padding |  |  |  | 0.001056%
|  | Installation |  |  |  | 0.007391%
|  | Alignment |  |  |  | 0.003168%
|  | Grouting |  |  |  | 0.003168%
|  | External Installation |  |  |  | 0.004224%
|  | Final Inspection |  |  |  | 0.001056%
|  | Pump 147-P-108 |  |  |  | 0.01928%
|  | Material Handling |  |  |  | 0.000964%
|  | Chipping & Padding |  |  |  | 0.000964%
|  | Installation |  |  |  | 0.006748%
|  | Alignment |  |  |  | 0.002892%
|  | Grouting |  |  |  | 0.002892%
|  | External Installation |  |  |  | 0.003856%
|  | Final Inspection |  |  |  | 0.000964%
|  | Pump 147-P-109A |  |  |  | 0.01878%
|  | Material Handling |  |  |  | 0.0009388%
|  | Chipping & Padding |  |  |  | 0.0009388%
|  | Installation |  |  |  | 0.006571%
|  | Alignment |  |  |  | 0.002816%
|  | Grouting |  |  |  | 0.002816%
|  | External Installation |  |  |  | 0.003755%
|  | Final Inspection |  |  |  | 0.0009388%
|  | Pump 147-P-109B |  |  |  | 0.01878%
|  | Material Handling |  |  |  | 0.0009388%
|  | Chipping & Padding |  |  |  | 0.0009388%
|  | Installation |  |  |  | 0.006571%
|  | Alignment |  |  |  | 0.002816%
|  | Grouting |  |  |  | 0.002816%
|  | External Installation |  |  |  | 0.003755%
|  | Final Inspection |  |  |  | 0.0009388%
|  | Pump 148-P-101A |  |  |  | 0.02019%
|  | Material Handling |  |  |  | 0.001009%
|  | Chipping & Padding |  |  |  | 0.001009%
|  | Installation |  |  |  | 0.007066%
|  | Alignment |  |  |  | 0.003028%
|  | Grouting |  |  |  | 0.003028%
|  | External Installation |  |  |  | 0.004038%
|  | Final Inspection |  |  |  | 0.001009%
|  | Pump 148-P-101B |  |  |  | 0.02019%
|  | Material Handling |  |  |  | 0.001009%
|  | Chipping & Padding |  |  |  | 0.001009%
|  | Installation |  |  |  | 0.007066%
|  | Alignment |  |  |  | 0.003028%
|  | Grouting |  |  |  | 0.003028%
|  | External Installation |  |  |  | 0.004038%
|  | Final Inspection |  |  |  | 0.001009%
|  | Pump 148-P-101C |  |  |  | 0.02019%
|  | Material Handling |  |  |  | 0.001009%
|  | Chipping & Padding |  |  |  | 0.001009%
|  | Installation |  |  |  | 0.007066%
|  | Alignment |  |  |  | 0.003028%
|  | Grouting |  |  |  | 0.003028%
|  | External Installation |  |  |  | 0.004038%
|  | Final Inspection |  |  |  | 0.001009%
|  | Pump 148-P-102 |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 148-P-103A |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 148-P-103B |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 148-P-103C |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%
|  | Pump 148-P-104 |  |  |  | 0.01009%
|  | Material Handling |  |  |  | 0.0005047%
|  | Chipping & Padding |  |  |  | 0.0005047%
|  | Installation |  |  |  | 0.003533%
|  | Alignment |  |  |  | 0.001514%
|  | Grouting |  |  |  | 0.001514%
|  | External Installation |  |  |  | 0.002019%
|  | Final Inspection |  |  |  | 0.0005047%

## Sheet2 (hidden)
Maroonkaran Planning Manager | Maroonkaran Project Manager | IPMI Planning Manager | IPMI Supervisor | IPMI Area Manager | IPMI Site Manager
Name : | Name : | Name : | Name : | Name : | Name :
M.Babadi | K.Changalvaie | H.Bijan |  | Mr.Bagheri | Mr.Ghanad Pour
Date : | Date : | Date : | Date : | Date : | Date :
Sige : | Sige : | Sige : | Sige : | Sige : | Sige :